## Overview
Legend | Description
NA | Related to general Query or UI changes.
Testing Date: | 2025-01-09
|  | Status Summary | (All)
Column Labels
|  |  | Fail | NA | Pass | Grand Total
|  | Count | 10 | 12 | 56 | 78

## Test Summary
NEL1902 FAT Test Status
Equipment Management Module
|  | Test Status |  |  |  | Defects |  |  |  | Updated Date: 03/10/2024
Test ID | Test Description | Pass | Fail Minor | Fail Major | Fail Critical | Test Specifications Version | Date of Test | PR ID | PR Status | Remarks
FAT_MASTERDM_0001.0001 | Validate Migrated Assets related data into Maximo |  | ✔ |  |  |  | 2024-09-30 |  |  | 1. The Coswin Equipment Topographical Count is different from Maximo Asset Count. 2. Meter Start Date when mapped to Asset Meter does not match. It is displaying 1/1/1970 12:00 AM. 3. How to view the Asset Meter Total Reading if the Meter Type is changed to Delta instead of Actual. Unable to view the Meter Reading History from Asset Meter. 4.1) Found the value 1899-12-31 in Maximo Asset Table. INSTALLDATE, ESTENDOFLIFE. It is incorrect. 2) Asset Move History is different from Coswin 3) Maximo Maintenance Entity not displayed in Asset Main Tab. The Maintenance Entity is showing in Associate Users and Custodians under Associate Group. 4) The GL Account is incorrect. The Dept Component of the GL Account for 3711100 is “SYS”. It should be “POW” 5) Coswin Equipment with EQ_LEVL = 0 should not be created as Assets as they are Assets Group. These Equipment should only be created as Maximo Route.
FAT_MASTERDM_0002.0001 | Validate Migrated Locations Data into Maximo |  | ✔ |  |  |  | 2024-09-27 |  |  | 1. SBST requested the Facility Codes to be migrated to Maximo as Location running number instead of migrating the Coswin FM_FACILITY.FM_CODE to Maximo LOCATIONS.LOCATION. The FM_CODE is to be migrated to LOCATIONS.STE_LOCCODE. All Facility Tracks with East and West to migrate only one single Track Location. For example S10E and S10W, to only create one S10 Location in Maximo. The “East” and “West” text within the description to be removed. The Location Type for Coswin Facility is to be created as DEPOTTRK. 2. Coswin Stores Count and Maximo Storeroom count matches 3.The EQP_TOPO.EQ_LOCT should not be migrated to Maximo as an operating Location. The EQP_TOPO.EQ_LOCT is to be stored in a new field STE_CSWNEQLOCT in the Maximo Asset table. 4. The Facility Rate, Sharable and Time Unit to be migrated to new fields in Maximo Locations, STE_CSWNxx fields. These fields are currently not migrated. 5. Coswin displays the Opening, Receipts, Issues, Adjusted, Transfer and Closed Values by periods (Monthly, Quarterly, Half-Yearly, Yearly and Up to Date). How is this represented in Maximo? There is no mapping for the above mentioned values in the mapping table. Checked for Storeroom ML_SIG and found 2 additional items not found in Coswin Store Item List. SIGNAL/CBI/03/58 SIGNAL/CBI/03/59
FAT_MASTERDM_0003.0001 | Validate Migrated Routes Data into Maximo |  | ✔ |  |  |  | 30/09/2024 02/10/2024 |  |  | 1. The Coswin Entity is not mapped to the Maximo Maintenance Entity. STE to check the mapping. There is no mapping for Coswin Zone, Category, Function, WP Type, Cost Centre. The fields are to be mapped to new customized fields in the Maximo Route Table. 2. SBST requested for the Behaviour of the Route Stops to be entries in the Work Order Multi Asset, Location and CI Table when the Route is applied to a Work Order.
FAT_MASTERDM_0004.0001 | Validate Migrated Person Data into Maximo | ✔ |  |  |  |  | 01/10/2024 02/10/2024 |  |  | 1. Coswin Employee Details Supervisor not migrated to Maximo Person. STE to rectify. 2. In Maximo, there are about 1400 person records beginning with “USR######”. These records are not from the Coswin Employee or User Table. STE to check and verify the source of these person and to check if these persons can be associated to existing Employee or Users. 3. Current SSIS Migration creates Person Records from the Supervisor (RES_SUPV) table. SBST confirms that the records within this table do not need to be created as a Person record in Maximo.
FAT_MASTERDM_0005.0001 | Validate Migrated Item Data into Maximo |  | ✔ |  |  |  | 2024-09-25 |  |  | 1. Unable to verify Coswin Item Group. Value not shown in screen or in downloaded excel. According to mapping table, the Coswin Item Group is mapped over to Maximo.STE_ITEMGROUP. If the field is not shown on UI, how is the Coswin functionality replicated in Maximo. The item group is used to identify items belonging to the same group. 2. STE to clarify on how the Coswin Item Type 0, 1 and 2 is represented in Maximo. 3. Coswin Last Modified on Date Time is stored incorrectly in Maximo. Maximo is only displaying the date of Last Modifed On, time 12:00AM. 4. Coswin Item Main Store is mapped to a new field STE_CSWNMAINSTORE. This field is not displayed on screen 5. Coswin Item Decimal is not available for Verification. The field is not mapped to Maximo. 6. To clarify how Coswin Shelf Life Type is mapped to Maximo Item Lot Type. 7. Coswin Criticality not mapped correctly to Maximo Critical. Item COMMS/ELC/CT/03A is a critical item in Coswin but non-critical item in Maximo.
FAT_MASTERDM_0006.0001 | Validate Migrated Meter Data into Maximo |  | ✔ |  |  |  | 2024-09-25 |  |  | 1) The Maximo METER.STE_CSWNDEFAULTVALUE is displaying 3.14159. The value is incorrect. 2) The MT_CU_RUNT field is 0 / 1 / 2. There should be Cumulative Total, Cumulative Increment. Meters ending with “MDKM” are Cumulative Increment, which is Maximo Delta. Not all meters are ACTUAL Reading. 3) Frequency of Measurement not displayed on screen. Need to verify whether data is stored correctly.
FAT_MASTERDM_0007.0001 | Validate Migrated Tools Data into Maximo | ✔ |  |  |  |  | 2024-09-25 |  |  | Tools and Tools Inventory data is migrated as Items and Inventory data in Item Master and Inventory applications in Maximo. It is covered as part of FAT_MASTERDM_0005.0001 - To Validate Item Master Data.
FAT_MASTERDM_0008.0001 | Validate Migrated Currency Data into Maximo | ✔ |  |  |  |  | 2024-09-24 |  |  | 1. Mas Manage comes with a default set of currencies in the system. Hence the count of the currency record in Maximo does not tally with the count of currency in Coswin. 2. Only currencies that are not present in Maximo are migrated over from Coswin. SBST requested that STE_CSWNCTRYCD, STE_CSWNCTRYNAME, STE_CSWNDPT to be patched for existing currencies. 3. Exchange Rates from SBST Finance do not have an expiry date. The Conversion Rates will be downloaded from Finance every Monday. STE to check how to enter the conversion rates for Currencies moving forward.
FAT_MASTERDM_0009.0001 | Validate Migrated Exchange Rates Data into Maximo | ✔ |  |  |  |  | 2024-09-24 |  |  | 1. Coswin Buy and Sell Rate for the Exchange Rate is all 0s. Coswin is using the Average Rate as the conversion rate from 1 currency to another currency. The current mapping of CRNCY_CONV.CONV_BUY_RATE to EXCHANGE. EXCHANGERATE is incorrect. To re-map the CRNCY_CONV. CONV_AVG_RATE to EXCHANGE.EXCHANGERATE. 2. EXCHANGE.CHANGEDATE is not shown in the downloaded data. To include the EXCHANGE.CHANGEDATE in the downloaded data. 3.Expiration Date is mapped to the CRNCY_CONV. DT_CRNCY_CONV. To extend the expiration date to 7 days after the CRNCY_CONV. DT_CRNCY_CONV.
FAT_MASTERDM_0010.0001 | Validate Migrated Person Group Data into Maximo. | ✔
FAT_MASTERDM_0011.0001 | Validate Migrated Labor Data into Maximo. | ✔ |  |  |  |  | 2024-10-02
FAT_MASTERDM_0012.0001 | Validate Migrated Crews Data into Maximo. | ✔ |  |  |  |  | 2024-10-02 |  |  | 1. SBST requested for all RES_SUPV records to be created as a Crew. 2. STE to clarify the creation of Crew. Currently, each Person record is creating a Crew record in the Crew Application.
FAT_MASTERDM_0013.0001 | Validate Migrated Unit Of Measure Data into Maximo. | ✔ |  |  |  |  | 2024-09-25 |  |  | 1. The count of Coswin Units is 156. Maximo Unit of Measure is showing 167. Observed that there is additional units in the Maximo UOM table. “?C”, “MIN”, “SEC”, “%”, “A”, “BTU/H”, “DEG”, “KW”, “PF”, “V”. To check if the additional units are required in Maximo. 2. Coswin Unit Conversions are not covered in the Test Case. It is observed that the Unit Conversions are not migrated to Maximo.
FAT_MASTERDM_0014.0001 | Validate Migrated Chart of Accounts Data into Maximo. | ✔ |  |  |  |  | 2024-10-02 |  |  | 1. SBST highlighted that for WIP_WO table, it is not necessary to reference the WO_REQUEST_AUTH as the Entity for Department Lookup. For EQP_JR, it is not necessary to reference the JR_REQUEST_AUTH as the Entity for Department Lookup. 2. SBST asked that how to set an existing GL Account to be inactive and do not allow Normal Users to view and use in Maximo. 3. SBST highlighted that the Description for the GL Account in Chart of Accounts is currently blank.
FAT_MASTERDM_0015.0001 | Validate Migrated Qualifications Data into Maximo. | ✔ |  |  |  |  | 2024-10-02 |  |  | The migrated Associated Labor Code is displaying the LANID of the employee. This is incorrect. It should be associated to the employee no of the Employee as the Labor Code is created using the Coswin Employee Number.
FAT_MASTERDM_0016.0001 | Validate Migrated Companies/Company Master Data into Maximo. |  | ✔ |  |  |  | 24/09/2024 25/09/2024 |  |  | 1) SUPPLIER_.SUPL_TYPE is created as Vendor in Maximo. Possible values from Coswin are N, Y, A, n, S. Records. Currently all records are mapped to “V”. 2) COMPMASTER.PAYMENTTERMS is stored as ALN without domain. To create a Payment Terms Domain to hold all possible values. 3) Company Remarks not displayed in the Long Description. To check why it is not shown on screen. 4) COMPMASTER.STE_CSWNSAPVNDCODE is shown as blank on Maximo. Corresponding Coswin Record has values recorded. To check mapping in SSIS. 5) Company Field in Company Master is not showing the full code. User needs to scroll right in order to view the Company Code fully. 6) Coswin Supplier History not mapped to Maximo. 7) Company Master Contacts Tab Phone and Fax Number not able to display the full content of the field on screen. 8) Coswin HO Addr and Mail Address not visible on Companies Application. It is only showing in Company Master Application. Company Master HO Addr and Mail Address to be shifted downwards after ZIP / Postal Code field. 9) DIR_MANF records are missing from Company Master Table. To check if the lookup for existing company includes Vendor (Company Type = “V”). 10) Currently Vendor and Manufacturer Dropdown selector is showing all companies. To check if the dropdown should only show Vendor or Manufacturer. 11) Currently Maximo is creating the Company records as Vendor (V) and Manufacturer (M). Is it possible to consolidate the two types into one. To check for possible implications to report generation if the company types are merged, for data migration which information should take precedence, (Supplier / Manufacturer Information). 12) Remarks Long Description is not displayed correctly in the Long Description field for Company Master. STE to check whether the data is populated correctly. SBST requested for the Remarks Field to be shown in the Company Master Main Tab as a separate Section that can be collapsed and expanded. 13) STE to clarify the difference between Company Master and Companies as the records are duplicated between these 2 tables. The Coswin HO Address and Mail Address is only loaded for Company Master. 14) Coswin HO Address and Mail Address to be loaded as per Vendor Manufacturers information from BA’s Excel. The original Coswin data for Coswin HO Address and Mail Address is to be loaded as-is to the Maximo DB. STE to provide the Coswin HO Address and Mail Address to SBST for data verification.
FAT_MASTERDM_0017.0001 | Validate Migrated Craft Data into Maximo. | ✔ |  |  |  |  | 2024-10-02 |  |  | 1) The Labor showing under the Associated Labor for a Craft is still displaying the LAN ID or Barcode for a Labor. This is incorrect. It should be storing the Employee Number of an Employee.
FAT_MASTERDM_0018.0001 | Validate Migrated Work Zone Data into Maximo. | ✔ |  |  |  |  | 2024-09-27 |  |  | SBST requested to migrate the DIR_ZONE table as is to the Maximo Database. The Coswin Zone records are not required to be created as Maximo Work Zones. There is also no migration to the Maximo Asset Work Zone tables
FAT_MASTERDM_0019.0001 | Validate Migrated Service Item Data into Maximo. | ✔ |  |  |  |  | 2024-10-01 |  |  | Currently, STE is using the Auto Reserve Tag (GRP_RES_TAG) of the Item Group to determine whether an Item is a Service or not. SBST pointed out that this is incorrect. To identify if a Service Item from the Coswin NSITEM table: If the UOM = “JOB”, create as Service Item. (UOM != “JOB”) If the Type = “Service”, create as Service Item. (UOM !=”JOB” and Type != “Service”) If the Item Group Description contains “SERVICES”, create as Service Item. 1) SBST feedback that the Coswin Item Group Details is not mapped over to Maximo. The Item Group value K31is currently mapped to a customized field ITEM.STE_ITEMGROUP. In this case, only Item Groups that are referenced by a Service Item will appear in the STE_ITEMGROUP column. Item Groups that are not referenced by any items will be lost. This results in a loss of information. The Description of the Item Group is also not mapped to any fields currently. 2) Long Description / Remarks not appearing in Maximo Service Item Application. STE to check and verify the data. 3) SBST enquired that if a Service Item is being created as an Item in Maximo or vice versa, is there a way to clean up the data in Maximo?
FAT_MASTERDM_0020.0001 | Validate Migrated Failure Code Data into Maximo. | ✔ |  |  |  |  | 2025-01-09 |  |  | Not Tested due to changes not implemented.
FAT_MASTERDM_0021.0001 | Validate AS-IS Coswin tables Migrated to Maximo Database | ✔ |  |  |  |  | 2025-01-09 |  |  | Not Tested
FAT_MASTERDM_0022.0001 | Validate Fields Not Displayed on Maximo UI Migrated to Maximo Database. | ✔ |  |  |  |  | 24/09/2024 25/09/2024
Test Statistic
Total Test Cases(✔) |  | 22
Total Test Cases Passes |  | 16
Total Test Cases Fail Minor |  | 6
Total Test Cases Fail Major |  | 0
Total Test Cases Fail Critical |  | 0
Total Test Cases Not tested |  | 0
Total % Test Cases Passed |  | 72.7273
Total % Test Cases Failed |  | 27.2727
Total % Test Cases Not Tested |  | 0

## PR Summary
Affected Test Case | Title | Internal Status | Type | Nature | Occurrence | Severity | Affected Test Case | Problem Description | Reported By | Reported Date | Problem Analysis | Analysed By | Analysed Date | SBST Validation | Validation Comment | Validated By | Validated Date | Close Comment | Closed By | Closed Date | BA Remarks
FAT_MASTERDM_0001.0001 | 1. The Coswin Equipment Topographical Count is different from Maximo Asset Count. | [12 empty] | Pass | SBST has taken a snapshot of count in coswin. To be verified with SBST against the snapshot taken. | Sidharth | 2024-10-22 | The count 241564 is validated successfully with SBST. | Peng keong | 2024-10-29
FAT_MASTERDM_0001.0001 | 2.Meter Start Date when mapped to Asset Meter does not match. It is displaying 1/1/1970 12:00 AM. | Pass | [11 empty] | Pass | 29/10/2024: The Meter Start Date for Asset: A100000031098 is 24/06/2002 in Coswin, In maximo it shows as 1/1/03 12:00 AM for meter TRAIN /208D/4DCN. The Meter Start Date still appears to be 1/1/1970 12:00 AM. Ex: Asset: A100000031098 | Sidharth | 2024-10-22 | The PR is validated successfully. | Peng keong | 2025-01-09
FAT_MASTERDM_0001.0001 | 3. How to view the Asset Meter Total Reading if the Meter Type is changed to Delta instead of Actual. | [12 empty] | Pass | It is not an issue but a query. The "Reading" column in Manage meter Reading History will show the total reading. | Sidharth | 2024-10-22 | Clarified and confirmed with SBST on their query. | Peng keong | 2024-10-29
FAT_MASTERDM_0001.0001 | Unable to view the Meter Reading History from Asset Meter. | Pass | [11 empty] | Pass | 29/10/2024: STE needs to rectify. ………………………………………………………………... It is not an issue but a query. The "Reading" column in Manage meter Reading History will show the total reading. | Sidharth | 2024-10-22 | The PR is validated successfully. | Peng keong | 2025-01-09
FAT_MASTERDM_0001.0001 | The field "Reading" in manage meter reading history is showing ambiguous value. The original meter reading value from coswin are stored in a custom field "STE_CSWNMREADING". STE to verify how the Reading is populated. Example:Asset "A100000042309", meter:"TRAIN /141D/MDKM". | [12 empty] | Fail | 09/01/2025: New observation by SBST. | Peng Keong | 2025-01-09 |  |  |  | Change the calculated value of READING and DELTA for readingtype="DELTA" For readingtype="ACTUAL", no changes. Keep the decimal value in READING and DELTA from original coswin value. | Need to get SBST to confirm the value for the big number reading
FAT_MASTERDM_0001.0001 | 4.1) Found the value 1899-12-31 in Maximo Asset Table. INSTALLDATE, ESTENDOFLIFE. It is incorrect. | Pass | [11 empty] | Pass | No more record with INSTALLDATE, ESTENDOFLIFE as 1899-12-31. | Sidharth | 2024-10-22 | Validated successfully with SBST. | Peng keong | 2024-10-29
FAT_MASTERDM_0001.0001 | 2) Asset Move History is different from Coswin | Pass | [11 empty] | Fail | For asset:A100000006018 , coswin eq code: AFCCQYB2/GTNK68 the asset move history is incorrect. The move to parent is AFCCQYB2/T02 is incorrect for dates 19/06/2002 and 28/09/2016, 15/4/2019. | Peng Keong | 2025-01-09 |  |  |  | To check
FAT_MASTERDM_0001.0001 | 3) Maximo Maintenance Entity not displayed in Asset Main Tab. The Maintenance Entity is showing in Associate Users and Custodians under Associate Group. | Fail | [11 empty] | Pass | To make TLOAMASSETGRP.ISPRIMARY=1 where there is one TLOAMASSETGRP record. Note: Verified in the current data that there are no dual Maintenance entity record for assets. | Sidharth | 2024-10-22 | Validated successfully with SBST. | Peng keong | 2024-10-29
FAT_MASTERDM_0001.0001 | 4) The GL Account is incorrect. The Dept Component of the GL Account for 3711100 is “SYS”. It should be “POW” | Pass | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0001.0001 | 5) Coswin Equipment with EQ_LEVL = 0 should not be created as Assets as they are Assets Group. These Equipment should only be created as Maximo Route. | Pass | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0002.0001 | 1. SBST requested the Facility Codes to be migrated to Maximo as Location running number instead of migrating the Coswin FM_FACILITY.FM_CODE to Maximo LOCATIONS.LOCATION. | Pass | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0002.0001 | The FM_CODE is to be migrated to LOCATIONS.STE_LOCCODE. | Pass | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0002.0001 | All Facility Tracks with East and West to migrate only one single Track Location. For example S10E and S10W, to only create one S10 Location in Maximo. | Pass | [11 empty] | Fail | Seems, instead of one S10 location, just the suffix E and W are removed to create two location records.STE to rectify. | Peng Keong | 2025-01-09 |  |  |  |  | Done
FAT_MASTERDM_0002.0001 | The “East” and “West” text within the description to be removed. | Pass | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0002.0001 | The Location Type for Coswin Facility is to be created as DEPOTTRK. | Pass | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0002.0001 | .The EQP_TOPO.EQ_LOCT should not be migrated to Maximo as an operating Location. The EQP_TOPO.EQ_LOCT is to be stored in a new field STE_CSWNEQLOCT in the Maximo Asset table. | Pass | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0002.0001 | The Facility Rate, Sharable and Time Unit to be migrated to new fields in Maximo Locations, STE_CSWNxx fields. | Pass | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0002.0001 | There is no mapping for the above mentioned values in the mapping table. These fields are currently not migrated. Coswin displays the Opening, Receipts, Issues, Adjusted, Transfer and Closed Values by periods (Monthly, Quarterly, Half-Yearly, Yearly and Up to Date). How is this represented in Maximo? | Pass | [11 empty] | Pass | 29/10/2024: STE to check and propose on mapping.Reference directory: Store Details. .............................................................................................. There is no equivalent function in maximo as maximo doesn't take any such snapshot. As discussed, Gareth to check in which table this data is being captured. We may need to create a separate table to store thes values against an item group. | Sidharth | 2024-10-22 |  | Peng Keong | 2025-01-09
FAT_MASTERDM_0002.0001 | There is no mapping for the above mentioned values in the mapping table. These fields are currently not migrated. Coswin displays the Opening, Receipts, Issues, Adjusted, Transfer and Closed Values by periods (Monthly, Quarterly, Half-Yearly, Yearly and Up to Date). How is this represented in Maximo? | [12 empty] | NA | 09/01/2025: SBST enquired on how this requirement is being achieved of getting the snapshot of the store accounting (Opening, Receipts, Issues, Adjusted, Transfer and Closed Values by periods (Monthly, Quarterly, Half-Yearly, Yearly and Up to Date)). BA to clarify
FAT_MASTERDM_0002.0001 | Checked for Storeroom ML_SIG and found 2 additional items not found in Coswin Store Item List. SIGNAL/CBI/03/58 SIGNAL/CBI/03/59 | [12 empty] | Pass | As inventory transaction data is not loaded yet, it cannot be tested now. | Peng Keong | 2025-01-09 |  | Peng Keong | 2025-01-09
FAT_MASTERDM_0003.0001 | The Coswin Entity is not mapped to the Maximo Maintenance Entity. STE to check the mapping. | Pass | [11 empty] | Pass | Tested in maximo routes. Maintenance Entities are migrated. | Sidharth | 2024-10-22 | Validated successfully with SBST. | Peng keong | 2024-10-29
FAT_MASTERDM_0003.0001 | There is no mapping for Coswin Zone, Category, Function, WP Type, Cost Centre. The fields are to be mapped to new customized fields in the Maximo Route Table. | Pass | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0003.0001 | SBST requested for the Behaviour of the Route Stops to be entries in the Work Order Multi Asset, Location and CI Table when the Route is applied to a Work Order. | Pass | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0003.0001 | WO ID : 657661, 849834, multiassetlocii should be populated as they have a route associated to it.But it is not present. | [12 empty] | Fail |  | Peng Keong | 2025-01-09 |  |  |  | 1. Copy ASSET/ROUTE from PM to WO 2. If there is ROUTE in WO, create all corresponding ROUTE_STOP in table MULTIASSETLOCCI | Done
FAT_MASTERDM_0004.0001 | 1. Coswin Employee Details Supervisor not migrated to Maximo Person. STE to rectify. | Fail | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0004.0001 | 2. In Maximo, there are about 1400 person records beginning with “USR######”. These records are not from the Coswin Employee or User Table. STE to check and verify the source of these person and to check if these persons can be associated to existing Employee or Users. | Pass | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0004.0001 | 3. Current SSIS Migration creates Person Records from the Supervisor (RES_SUPV) table. SBST confirms that the records within this table do not need to be created as a Person record in Maximo. | Pass | [11 empty] | Pass | These are created as Crew as confirmed with SBST. | Sidharth | 2024-10-22 | Validated successfully with SBST. | Peng keong | 2024-10-29
FAT_MASTERDM_0005.0001 | 1. Unable to verify Coswin Item Group. Value not shown in screen or in downloaded excel. According to mapping table, the Coswin Item Group is mapped over to Maximo.STE_ITEMGROUP. If the field is not shown on UI, how is the Coswin functionality replicated in Maximo. The item group is used to identify items belonging to the same group. | Pass | [11 empty] | Pass | Item Group from coswin is mapped to Item.STE_ITEMGROUP.The field can be brought over to UI and added as a column in List tab to filter out the items belonging to a particular item group. | Sidharth | 2024-10-22 | Validated successfully with SBST. | Peng keong | 2024-10-29
FAT_MASTERDM_0005.0001 | 2. STE to clarify on how the Coswin Item Type 0, 1 and 2 is represented in Maximo. | Pass | [11 empty] | Fail | 09/01/2025: The STE_ITEMTYPE field doesn't have any value.STE to verify. 29/10/2024: STE to migrate the value in ITEM.STE_TYPE field. NSITEM.NSITEM_TYPE -> ITEM.STE_TYPE ITEM_.ITEM_TYPE - >ITEM.STE_TYPE Spare/Tools Details (Spare/Tool Type) ->ITEM.STE_TYPE ……………………………………………………………………. These are mapped to ITEM.STE_TYPE field in maximo. | Peng Keong | 2025-01-09 |  |  |  | To update | Done
FAT_MASTERDM_0005.0001 | 3. Coswin Last Modified on Date Time is stored incorrectly in Maximo. Maximo is only displaying the date of Last Modifed On, time 12:00AM. | Pass | [11 empty] | Pass | 30/10/2024: The time value is found in Coswin. Updating the status to Pass. .......................................................................................... 29/10/2024: Item PO000000000000034499 has only date in coswin but migrated data displays time as well.STE to check from where time is populated for the non-stock items from coswin. For stocked items it is displaying correctly. ………………………………………….................................... ITEM.STATUSDATE is populated with both date and time. | Sidharth | 2024-10-23 | Validated successfully with SBST. | Peng keong | 2024-10-29
FAT_MASTERDM_0005.0001 | 4. Coswin Item Main Store is mapped to a new field STE_CSWNMAINSTORE. This field is not displayed on screen | Fail | [11 empty] | Pass | This is UI related. Software team needs to display it on screen. | Sidharth | 2024-10-23 | Validated successfully with SBST. | Peng keong | 2024-10-29
FAT_MASTERDM_0005.0001 | 5. Coswin Item Decimal is not available for Verification. The field is not mapped to Maximo. | [12 empty] | Pass | 29/10/2024: SBST confirmed qty Digit field is not required to be migrated over. …………………………………………………………………….. Did not understand which field it is referring to.Need to check with Esther or Gareth. | Sidharth | 2024-10-23 | Not required to migrate as per confirmation from SBST. | Peng keong | 2024-10-29
FAT_MASTERDM_0005.0001 | 6. To clarify how Coswin Shelf Life Type is mapped to Maximo Item Lot Type. | Pass | [11 empty] | Fail | 09/01/2025: The PR has failed valiation. There are 41729 with lot type as "LOT". ,........................................................................................ 29/10/2024: Shell life type is clarified to SBST. STE to make all the items to be of NOLOT type. …………………………………………………………………….. Need further details. To check with Gareth on how we have mapped lottype initiailly. | Peng Keong | 2025-01-09 |  |  |  | Change lottype="NOLOT" | Done
FAT_MASTERDM_0005.0001 | 7. Coswin Criticality not mapped correctly to Maximo Critical. Item COMMS/ELC/CT/03A is a critical item in Coswin but non-critical item in Maximo. | Pass | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0005.0001 | Non-Stock Items to be populated as Non-Stock and stocked as stock items in item/organization details. STE to check if there is any identifier which differentiates stocked from non-stock. | Fail | [11 empty] | Pass | ITEMORGINFO.CATEGORY to be populated with "STK" for stocked item and "NS" for Non-stocked item | Sidharth | 2024-10-23 | Validated successfully with SBST. | Peng keong | 2024-10-29
FAT_MASTERDM_0006.0001 | 1) The Maximo METER.STE_CSWNDEFAULTVALUE is displaying 3.14159. The value is incorrect. | Pass | [11 empty] | Fail | 09/01/2025: The PR has failed validation.STE to rectify. ……………………………………………………………………….. 30/10/2024: To nullify all the METER.STE_CSWNDEFAULTVALUE values. The value is still the same.Need to verify on what is the correct value. | Peng Keong | 2025-01-09 |  |  |  | Remove the mapping | Done
FAT_MASTERDM_0006.0001 | The MT_CU_RUNT field is 0 / 1 / 2. There should be Cumulative Total, Cumulative Increment. Meters ending with “MDKM” are Cumulative Increment, which is Maximo Delta. Not all meters are ACTUAL Reading. | Pass | [11 empty] | Pass | Meters ending with “MDKM” are changed as Delta. | Sidharth | 2024-10-23 | Validated successfully with SBST. | Peng keong | 2024-10-30
FAT_MASTERDM_0006.0001 | Frequency of Measurement not displayed on screen. Need to verify whether data is stored correctly. | Pass | [11 empty] | Fail | 09/01/2025: This will be availble in next db version V1.12 .......................................................................................... 30/10/2024: The data is migrated to ASSETMETER.STE_CSWNFREQUENCY and ASSETMETER.STE_CSWNFREQUENCYUNIT. It needs to be migrated to METER.STE_CSWNFREQUENCY and METER.STE_CSWNFREQUENCYUNIT instead. The frequency and frequency unit needs to be displayed on UI under "Unit of Measure" field in asset meter. To be pulled over from METER.STE_CSWNFREQUENCY and METER.STE_CSWNFREQUENCYUNIT via relationship and displayed. …………………………………………………………………….. The frequency of measurement is stored in ASSETMETER.STE_CSWNFREQUENCY | Peng Keong | 2025-01-09 |  |  |  |  | Done
FAT_MASTERDM_0007.0001 | Tools and Tools Inventory data is migrated as Items and Inventory data in Item Master and Inventory applications in Maximo. It is covered as part of FAT_MASTERDM_0005.0001 - To Validate Item Master Data. | [12 empty] | NA | 30/10/2024: To display ITEM.STE_ITEMGROUP on UI above "Item Part No." field in Item master application. Refer Transaction PR summary for Service Group related issue(Highlighted in yellow). …………………………………………………………………….. The inventory data is not verified as the transaction data is not yet loaded. | Sidharth | 2024-10-23
FAT_MASTERDM_0008.0001 | 1. Mas Manage comes with a default set of currencies in the system. Hence the count of the currency record in Maximo does not tally with the count of currency in Coswin. | Pass | [11 empty] | Pass | 30/10/2024: SBST requested to de-activate the standard currency codes in maximo. Only the coswin migrated currency codes should be made active. | Sidharth | 2024-10-23 | Validated successfully with SBST. | Peng keong | 2024-10-30
FAT_MASTERDM_0008.0001 | 2. Only currencies that are not present in Maximo are migrated over from Coswin. SBST requested that STE_CSWNCTRYCD, STE_CSWNCTRYNAME, STE_CSWNDPT to be patched for existing currencies. | Pass | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0008.0001 | 3. Exchange Rates from SBST Finance do not have an expiry date. The Conversion Rates will be downloaded from Finance every Monday. STE to check how to enter the conversion rates for Currencies moving forward. | NA | [11 empty] | NA | To check and verify with Wei Teng if there is any such requirement. | Sidharth | 2024-10-23 | Not related to data Migration. | Peng keong | 2024-10-30
FAT_MASTERDM_0009.0001 | 1. Coswin Buy and Sell Rate for the Exchange Rate is all 0s. Coswin is using the Average Rate as the conversion rate from 1 currency to another currency. The current mapping of CRNCY_CONV.CONV_BUY_RATE to EXCHANGE. EXCHANGERATE is incorrect. To re-map the CRNCY_CONV. CONV_AVG_RATE to EXCHANGE.EXCHANGERATE. | Pass | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0009.0001 | 2. EXCHANGE.CHANGEDATE is not shown in the downloaded data. To include the EXCHANGE.CHANGEDATE in the downloaded data. | NA | [11 empty] | NA | 30/10/2024: The data is migrated successfully. SBST requested to have a audit log trail for the updated exchange records. .............................................................................................. The Data is migrated. It doesn't seems to be included on screen in exhange rates app. If SBST is downloading the data using the download function. It should be added as another column on UI. BA to confirm? | Sidharth | 2024-10-23 | Not related to data Migration. |  | 2024-10-30
FAT_MASTERDM_0009.0001 | 3.Expiration Date is mapped to the CRNCY_CONV. DT_CRNCY_CONV. To extend the expiration date to 7 days after the CRNCY_CONV. DT_CRNCY_CONV. | Pass | [11 empty] | Pass | 30/10/2024: The activity to upload the exchange rates after data migration is part of the pre-commision(Data loading) planned task. ............................................................................................. Observed, active date in maximo is mapped to CRNCY_CONV. DT_CRNCY_CONV from coswin and expiration date in maximo is mapped to CRNCY_CONV. DT_CRNCY_CONV + 7. While the above mapping is confirmed with SBST. The data seems to be ambigous as active date is in the past (2003) which contradicts SBST's statement that finance is updating it every week. To discuss with SBST on the future course of action. | Sidharth | 2024-10-23 | Validated successfully with SBST. | Peng keong | 2024-10-30
FAT_MASTERDM_0012.0001 | 1. SBST requested for all RES_SUPV records to be created as a Crew. | Pass | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0012.0001 | 2. STE to clarify the creation of Crew. Currently, each Person record is creating a Crew record in the Crew Application. | Fail | [11 empty] | Pass | Observed crew type as EMPL for crews records. However, there is no crew type as EMPL defined in the Crew type domain. This should be all changed to Craft .As crew type domain only have a value of Craft. | Sidharth | 2024-10-23 | Validated successfully with SBST. | Peng keong | 2024-10-30
FAT_MASTERDM_0013.0001 | The count of Coswin Units is 156. Maximo Unit of Measure is showing 167. | Pass | [11 empty] | Pass | 09/01/2025: As of date, the total count of UOM is 169. .............................................................................................. 15/11/2024: The total count of UOM in maximo is 169 (160 + 9 extra non-migrated values), the total of migrated UOM is coming same as 160 of coswin. Hence, passing the item. ............................................................................................ 30/10/2024: The total count of coswin UOM + Meter UOM is coming to be 160 in coswin. The migrated data in maximo is 156. STE to investigate on the missing values. There are 9 extra values which are not from migrated data.To clarify with BA. ............................................................................................... SBST has taken a snapshot of count in coswin. To be verified with SBST against the snapshot take or with the current production on the day of next testing with SBST. | Peng Keong | 2025-01-09 |  | Peng Keong | 2025-01-09 | The extra 9 values are created internally by STE, inclusive of OOTB values as clarified with BA.
FAT_MASTERDM_0013.0001 | Observed that there is additional units in the Maximo UOM table. “?C”, “MIN”, “SEC”, “%”, “A”, “BTU/H”, “DEG”, “KW”, “PF”, “V”. To check if the additional units are required in Maximo. | Pass | [11 empty] | Pass | 30/10/2024: Similar to issue 46. …………………………………………………………………….. The data is migrated. The source is from coswin meters. | Sidharth | 2024-10-23 | Validated successfully with SBST. | Peng keong | 2024-10-30
FAT_MASTERDM_0013.0001 | Coswin Unit Conversions are not covered in the Test Case. It is observed that the Unit Conversions are not migrated to Maximo. | Pass | [11 empty] | Pass |  | Sidharth | 2024-10-23 | Validated successfully with SBST. | Peng keong | 2024-10-30
FAT_MASTERDM_0014.0001 | 1. SBST highlighted that for WIP_WO table, it is not necessary to reference the WO_REQUEST_AUTH as the Entity for Department Lookup. For EQP_JR, it is not necessary to reference the JR_REQUEST_AUTH as the Entity for Department Lookup. | Pass | [11 empty] | Pass | 30/10/2024: This should be verified as part of work order transaction data validation. | Peng Keong | 2025-01-09
FAT_MASTERDM_0014.0001 | 2. SBST asked that how to set an existing GL Account to be inactive and do not allow Normal Users to view and use in Maximo. | NA | [11 empty] | NA | 30/10/2024: Explained SBST as per below: GL Account can be made inactive by entering expiration date which follows the below conditions: Expiration date > Active Date and Expiration date < Current date & Time GL Account can be made Active again by removing the expiration date. | Sidharth | 2024-10-23 | Not related to data Migration. | Peng keong | 2024-10-30 | This is a query from SBST. Discussed with Wei Teng, The explanation is in the Validation comment column.
FAT_MASTERDM_0014.0001 | 3. SBST highlighted that the Description for the GL Account in Chart of Accounts is currently blank. | Pass | [11 empty] | Pass | As per SBST cost center and department mapping sheet, the descirptions are loaded for the gl accounts in maximo wherever it was provided. The description are blank for the GL acounts whose description were not provided by SBST and they are migrated from transaction records. | Sidharth | 2024-10-23 | Validated successfully with SBST. | Peng keong | 2024-10-30
FAT_MASTERDM_0015.0001 | The migrated Associated Labor Code is displaying the LANID of the employee. This is incorrect. It should be associated to the employee no of the Employee as the Labor Code is created using the Coswin Employee Number. | Pass | [11 empty] | Pass |  | Sidharth | 2024-10-23 | Validated successfully with SBST. | Peng keong | 2024-10-30
FAT_MASTERDM_0016.0001 | 1) SUPPLIER_.SUPL_TYPE is created as Vendor in Maximo. Possible values from Coswin are N, Y, A, n, S. Records. Currently all records are mapped to “V”. | Fail | [11 empty] | Pass | 30/10/2024: The data in manufacturer directory in coswin is move to company master in maximo as company record with company type as "M". Rest all are moved with company type as "V". Create a custom field STE_CSWNSUPLTYPE in maximo to map it from SUPPLIER_.SUPL_TYPE in coswin. | Sidharth | 2024-10-23
FAT_MASTERDM_0016.0001 | COMPMASTER.PAYMENTTERMS is stored as ALN without domain. To create a Payment Terms Domain to hold all possible values. | NA | [11 empty] | NA | 30/10/2024: The data is migrated. Software team needs to add a domain with the list of payment terms values. BA to check and confirm. | Sidharth | 2024-10-23 | Not related to data Migration. | Peng keong | 2024-10-30 | Wei Teng to check and confirm with Software Team to add the domain and share all the values received from SBST.
FAT_MASTERDM_0016.0001 | Company Remarks not displayed in the Long Description. To check why it is not shown on screen. | Pass | [11 empty] | Pass | 09/01/2025: The company remarks are migrated to "Company Master" main tab under "Remarks" Section in Company Master application. ............................................................................................. 15/11/2024: Verified remarks, populated for the following company master records: GOLDBELLLEASI65GESGD,GBCASIAPTELTD65OESGD,GOLDBELLLEASI65GESGD,GOLDENWHEELHA65MISGD ............................................................................................ 30/10/2024: This will be done as part of long description package deployment. Gareth to check. | Peng Keong | 2025-01-09 | Validated successfully. | Peng Keong | 2025-01-09
FAT_MASTERDM_0016.0001 | COMPMASTER.STE_CSWNSAPVNDCODE is shown as blank on Maximo. Corresponding Coswin Record has values recorded. To check mapping in SSIS. | Pass | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0016.0001 | Company Field in Company Master is not showing the full code. User needs to scroll right in order to view the Company Code fully. | NA | [11 empty] | NA | Did not observed any issue here. BA to suggest and clarify with software team.To ignore, if fixed. | Sidharth | 2024-10-23 | Not related to data Migration. | Peng keong | 2024-10-30 | As discussed with Wei Teng, The company Master Main tab company field needs to be scrolled to view the entire name of the company.He needs to check and confirm with software team and highlight any limitations.
FAT_MASTERDM_0016.0001 | 6) Coswin Supplier History not mapped to Maximo. | Pass | [11 empty] | Fail | 09/01/2025: Early by Days, late by days values are not populated. 30/10/2024: Gareth to look into migrated STE_TOTALPOVAL from Total PO Value. It is 41240.59 in migrated data and 41240.60 in coswin. Early by Days and Late by Days need to be entered as per the logic below: 1- 15 2 - 30 3- 45 4 - 60 ........................................................................................... Create a custom table STE_SUPPLHISTORY in database and map the coswin fields as below: Supplier: STE_SUPPL Supplier Description : STE_SUPPL_DESC Last PO Reference : STE_LASTPOREF Last PO date : STE_LASTPODATE Total PO Value : STE_TOTALPOVAL No of times Ordered: STE_NOOFTO No of times Delivered: STE_NOOFTD No of times Rejected: STE_NOOFTR Early by - Days: STE_ERLYD Early by - Times: STE_ERLYT Late by - Days: STE_LATEBYD Late by - Times: STE_LATEBYT | Peng Keong | 2025-01-09
FAT_MASTERDM_0016.0001 | 7) Company Master Contacts Tab Phone and Fax Number not able to display the full content of the field on screen. | NA | [11 empty] | NA | BA to suggest. | Sidharth | 2024-10-23 | Not related to data Migration. | Peng keong | 2024-10-30 | As discussed and observed with Wei Teng,The maximum length migrated for Homephone and Faxphone is 20. This requires the Home Phone and Fax field on screen to be scrolled in order to see the entire value. Wei Teng to check and confirm with software team and highlight any limitations.
FAT_MASTERDM_0016.0001 | 8) Coswin HO Addr and Mail Address not visible on Companies Application. It is only showing in Company Master Application. Company Master HO Addr and Mail Address to be shifted downwards after ZIP / Postal Code field. | NA | NA | [10 empty] | NA | BA to suggest. | Sidharth | 2024-10-23 | Not related to data Migration. | Peng keong | 2024-10-30 | Wei Teng to check with software team to bring these fields on screen. COMPMASTER.STE_HO_ADDR_LONGDESCRIPTION COMPMASTER.STE_MAIL_ADDR_LONGDESCRIPTION
FAT_MASTERDM_0016.0001 | 9) DIR_MANF records are missing from Company Master Table. To check if the lookup for existing company includes Vendor (Company Type = “V”). | Pass | [11 empty] | Pass | 30/10/2024: The DIR_MANF records are migrated as company type = V. ……………………………………………………………………... Coswin Manufacturers are moved to company master wth type as M. | Sidharth | 2024-10-23 | Validated successfully with SBST. | Peng keong | 2024-10-30
FAT_MASTERDM_0016.0001 | 10) Currently Vendor and Manufacturer Dropdown selector is showing all companies. To check if the dropdown should only show Vendor or Manufacturer. | NA | [11 empty] | NA | 30/10/2024: The vendor lookup is showing around 220 lesser companies (type = "V') than manufacturer field's lookup. Software team to analyze what is restricting the vendor field's lookup values to display all companies. …………………………………………………………………….. BA to suggest. | Sidharth | 2024-10-23 | Not related to data Migration. | Peng keong | 2024-10-30
FAT_MASTERDM_0016.0001 | 11) Currently Maximo is creating the Company records as Vendor (V) and Manufacturer (M). Is it possible to consolidate the two types into one. To check for possible implications to report generation if the company types are merged, for data migration which information should take precedence, (Supplier / Manufacturer Information). | Pass | [11 empty] | Pass | 30/10/2024: All the companies are consolidated as type V and migrated. ……………………………………………………………………... BA to suggest. | Sidharth | 2024-10-23 | Validated successfully with SBST. | Peng keong | 2024-10-30 | Wei teng to analyse and check.
FAT_MASTERDM_0016.0001 | 12) Remarks Long Description is not displayed correctly in the Long Description field for Company Master. STE to check whether the data is populated correctly. SBST requested for the Remarks Field to be shown in the Company Master Main Tab as a separate Section that can be collapsed and expanded. | NA | [11 empty] | Pass | 09/01/2025: Same as row number 57.To create one single PR form for both. 30/10/2024: It will be migrated as part of long description deployment package. ............................................................................................ Remarks from coswin's company master to be migrated to a separate long description field STE_REMARKS. BA and software to suggest on the visibility of this field in application. | Peng Keong | 2025-01-09 | Validated successfully. | Peng Keong | 2025-01-09 | Wei Teng to check with Software team to create a field COMPMASTER.STE_RMK.LONGDESCRIPTION.
FAT_MASTERDM_0016.0001 | 13) STE to clarify the difference between Company Master and Companies as the records are duplicated between these 2 tables. The Coswin HO Address and Mail Address is only loaded for Company Master. | NA | [11 empty] | Pass | 15/11/2024: HO Add and Mail Add seems to be added in company master. .......................................................................................... 30/10/2024: SBST clarified about the Company Master and Companies fucntionality in maximo. Ho Add and Mail add to be migrated as part of long description. ........................................................................................... | Peng Keong | 2025-01-09 | Validated successfully. | Peng Keong | 2025-01-09
FAT_MASTERDM_0016.0001 | 14) Coswin HO Address and Mail Address to be loaded as per Vendor Manufacturers information from BA’s Excel. The original Coswin data for Coswin HO Address and Mail Address is to be loaded as-is to the Maximo DB. STE to provide the Coswin HO Address and Mail Address to SBST for data verification. | Pass | [11 empty] | Pass | 30/10/2024: Same as above.To create one single PR form. ……………………………………………………………………. Gareth to check. | Peng Keong | 2025-01-09 | Validated successfully. | Peng Keong | 2025-01-09
FAT_MASTERDM_0017.0001 | 1) The Labor showing under the Associated Labor for a Craft is still displaying the LAN ID or Barcode for a Labor. This is incorrect. It should be storing the Employee Number of an Employee. | Fail | [11 empty] | Pass | No data seems to be populated for LABORCRAFTRATE table (Associated Labor).Kindly check. | Sidharth | 2024-10-23 | Validated successfully with SBST. | Peng keong | 2024-10-30
FAT_MASTERDM_0018.0001 | SBST requested to migrate the DIR_ZONE table as is to the Maximo Database. | Pass | [11 empty] | Pass | 09/01/2025: The scope (section 1.3 , serial 2) in STD needs to be updated with the updated list of AS-IS migrated tables (count : 172). 30/10/2024: All the AS-IS tables are yet to be migrated. …………………………………………………………………….. Gareth to Migrate it AS-IS similar to other AS-IS tables with CSWN_ prefix. CSWN_DIR_ZONE. | Sidharth | 2024-10-23
FAT_MASTERDM_0018.0001 | The Coswin Zone records are not required to be created as Maximo Work Zones. There is also no migration to the Maximo Asset Work Zone tables | Fail | [11 empty] | Pass | The custom field created to store Asset's work zone is not migrated.Gareth to look into it. | Sidharth | 2024-10-23 | Validated successfully with SBST. | Peng keong | 2024-10-30
FAT_MASTERDM_0019.0001 | Currently, STE is using the Auto Reserve Tag (GRP_RES_TAG) of the Item Group to determine whether an Item is a Service or not. SBST pointed out that this is incorrect. To identify if a Service Item from the Coswin NSITEM table: If the UOM = “JOB”, create as Service Item. (UOM != “JOB”) If the Type = “Service”, create as Service Item. (UOM !=”JOB” and Type != “Service”) If the Item Group Description contains “SERVICES”, create as Service Item. | Pass | [11 empty] | Pass | 30/10/2024: Not able to access Service Items application due to sql error :4460.Gareth to check the structure of the view.If any additional column is erroneously appearing. ..................................................................................................... Not able to access Service Items application due to sql error :4460.Gareth to check the structure of the view.If any additional column is erroneously appearing. | Sidharth | 2024-10-23
FAT_MASTERDM_0019.0001 | SBST feedback that the Coswin Item Group Details is not mapped over to Maximo. The Item Group value K31is currently mapped to a customized field ITEM.STE_ITEMGROUP. In this case, only Item Groups that are referenced by a Service Item will appear in the STE_ITEMGROUP column. Item Groups that are not referenced by any items will be lost. This results in a loss of information. The Description of the Item Group is also not mapped to any fields currently. | [12 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
FAT_MASTERDM_0019.0001 | Long Description / Remarks not appearing in Maximo Service Item Application. STE to check and verify the data. | Pass | [11 empty] | Pass | 09/01/2025: The data is migrated. Remarks to be displayed on screen. 30/10/2024: This will be done as part of Long description package deployment. …………………………………………………………………….. Gareth to check. | Peng Keong | 2025-01-09 | Validated successfully. | Peng Keong | 2025-01-09
FAT_MASTERDM_0019.0001 | SBST enquired that if a Service Item is being created as an Item in Maximo or vice versa, is there a way to clean up the data in Maximo? | NA | [11 empty] | NA | 30/10/2024: STE explained that there is no straight answer to this and requires analysis. As in case if there are active or open transactions associated to Service Items. The system may not allow the type to be changed from UI.If it is still needed to be done it has to be carefully analyzed and done Via Data patch. …………………………………………………………………….. This is an enquiry from SBST.BA to suggest. | Sidharth | 2024-10-23 |  |  |  | As discussed with Wei Teng.If an item is associated with a transaction, it cannot be deleted through UI. If there is a claenup required it has to be done through data patches via backend.
FAT_MASTERDM_0020.0001 | Failure code to be consolidated into one CSWNFL_CLS. | Pass | [11 empty] | Pass |  | Peng Keong | 2025-01-09 | Successfully validated. | Peng Keong | 2025-01-09
| If the status of work order is APPR and beyond, the originating SR should be populated with status of "CLOSED".To clarify with Sam. | [12 empty] | Fail | DAR Number:3027, SDS for work management module.Section 5.3.1 | Peng Keong | 2025-01-09 |  |  |  |  | Done
| Failure Report for migrated work orders is unable to open on UI having the consolidated failure class: CSWNFL_CLS | [12 empty] | Fail |  | Peng Keong | 2025-01-09 |  |  |  | To check

## Drop down list (hidden)
Event Type | Nature | Occurrence | Severity | Status
Error | Document | Constant Defect | Critical | Pending Analysis
Fault | Software | Random Defect | Major | Pending Validation
Evolution | Hardware | Defect due to change | Minor | Pending Closure
Improvement |  |  |  | Closed