## Test Summary
NEL1902 FAT Test Status
DM-Transaction
|  | Test Status |  |  |  | Defects |  |  |  | Updated Date: 18/09/2024
Test ID | Test Description | Pass | Fail Minor | Fail Major | Fail Critical | Test Specifications Version | Date of Test | PR ID | PR Status | Remarks
FAT_TRANSACTDM_0001.0001 | Validate Migrated Contracts (Price) Data into Maximo |  | ✔ |  |  |  | 2024-10-08
FAT_TRANSACTDM_0002.0001 | Validate Migrated Blanket Contracts Data into Maximo |  | ✔ |  |  |  | 2024-10-08
FAT_TRANSACTDM_0003.0001 | Validate Migrated Purchase Requisition(PR) Data into Maximo |  | ✔ |  |  |  | 2024-10-08
FAT_TRANSACTDM_0004.0001 | Validate Migrated Request For Quotation(RFQ) Data into Maximo |  | ✔ |  |  |  | 2024-10-08
FAT_TRANSACTDM_0005.0001 | Validate Migrated RFQ Vendor Data into Maximo |  | ✔ |  |  |  | 2024-10-08
FAT_TRANSACTDM_0006.0001 | Validate Migrated Purchase Orders(PO) Data into Maximo |  | ✔ |  |  |  | 09-Oct-24
FAT_TRANSACTDM_0007.0001 | Validate Migrated Invoices Data into Maximo |  | ✔ |  |  |  | 27-Sep-24 09-Oct-24 |  |  | 1.STE to check the purpose of G/L Posting Date in invoice Table. STE to check the value for totaltax1. Value is rounded to 0 decimal places. For Eg, Coswin 16.90, Maximo 17.00. The Coswin Remarks for Invoice is currently migrated to Terms and Condition Long Description. As the information within this field is entered by the end users, STE proposed for the remarks to be added onto the Invoice Application. 1) INV_DT and INV_RCT_DT is not mapped correctly. INV_DT should be mapped to INVOICE.CHANGEDATE and INV_RCT_DT should be mapped to INVOICE.INVOICEDATE. 2) Coswin Invoice SAP GL Code should be displayed on Maximo Invoice Main Tab. Currently it is mapped to INVOICECOST. STE_CSWNSAPGL.
FAT_TRANSACTDM_0008.0001 | Validate Migrated Receipts Data into Maximo |  | ✔ |  |  |  | 2024-10-10
FAT_TRANSACTDM_0009.0001 | Validate Migrated Work Order Data into Maximo | [5 empty] | 02-Oct-24 10-Oct-24 |  |  | 1. Coswin stores the Track Access Number in WIP_WO. WO_EQ_PHON. Currently in Maximo, it is mapped to a customized field in the Work Order table, STE_EQPPHONE. To amend the field label on screen to TAR No. The Maximo Labor in the Actuals Tab is still displaying the LAN ID or Barcode of the Employee. This is incorrect. It should display the Employee Number of the Employee. 2. SBST highlighted that the Maximo Work Order for migrated Work Orders should be having a “WO” prefix with running numbers. STE to check and verify if the migrated work orders is to be created in the above format.
FAT_TRANSACTDM_0010.0001 | Validate Migrated Service Requests Data into Maximo
FAT_TRANSACTDM_0011.0001 | Validate Inventory Data into Maximo |  | ✔ |  |  |  | 2024-09-25 |  |  | Min Qty, Max Qty, Reorder Point, Safety Stock showing 0 on screen. It is having values in Coswin. Population field is present in Coswin but is not mapped to Maximo. Currently Coswin Stockout Risk %, Cyclic Re-order and No. of days in Cycle is not mapped to any Maximo fields. To clarify if this field should be populated to a new field within Inventory. These fields are currently not available for verification. Coswin ORG_SUPL_CD is currently mapped to Inventory Manufacturer. The mapping is incorrect as the Suppliers are Vendors. SBST proposed that the original Supplier Code to be mapped to a new separate field instead of Manufacturer.
FAT_TRANSACTDM_0012.0001 | Validate Inventory Vendor Data into Maximo |  | ✔ |  |  |  | 2024-09-25 |  |  | 1) Coswin GST not mapped correctly to Maximo Inventory Vendor Tax Code. It should display GST in Inventory Vendor for all Items that are associated with GST. 2) The Coswin Max Lead Time is mapped to Inventory Delivery Time. SBST feedback that the Max Lead Time should also be within the same Section as the Min, Average Lead Time in the Inventory Vendor Section. 3) Coswin First Procured Date is mapped to the Inventory Vendor Last Order Date. However, the Last Order Date is not showing the correct information. SBST proposed to store the First Procured Date. 4) Remarks Column is advised by SBST to be stored in the STK_ITEM. STE to check if the Remarks field can be retrieved and stored in Maximo Item Application. 5) 1899-12-31 is visible for Last PO Date. To amend the mapping of the date value if it is NULL or 0. 6) Last Price is showing 0 for all records. User feedback that it should not show 0, but instead, the Unit Price of the Item should be displayed. 7) STE_CSWNLASTPO is not displayed correctly. TO check mapping of the field.
FAT_TRANSACTDM_0013.0001 | Validate Inventory Balances Data into Maximo | [5 empty] | 2024-09-25 |  |  | SBST feedback that Coswin Bins are created from a Bin Selector. Maximo Bins are mapped over to Inventory Balances Table BINNUM field. There is no application to create Bin in Maximo. It is currently stored as a ALN field.
FAT_TRANSACTDM_0014.0001 | Validate Material Requisitions Data into Maximo
FAT_TRANSACTDM_0015.0001 | Validate Preventive Maintenance Data into Maximo | [5 empty] | 30-Sep-24 10-Oct-24
FAT_TRANSACTDM_0016.0001 | Validate Migrated Job Plans Data into Maximo |  | ✔ |  |  |  | 2024-09-30 |  |  | SBST highlighted that the Maximo Jobplans are created incorrectly. The Jobplans should be created as per the Job Directory. Currently there are multiple instances of the same Job ID but having different Equipment Code.
FAT_TRANSACTDM_0017.0001 | Validate Fields Not Displayed on Maximo UI Migrated to Maximo Database
Test Statistic
Total Test Cases(✔) |  | 17
Total Test Cases Passes |  | 0
Total Test Cases Fail Minor |  | 11
Total Test Cases Fail Major |  | 0
Total Test Cases Fail Critical |  | 0
Total Test Cases Not tested |  | 6
Total % Test Cases Passed |  | 0
Total % Test Cases Failed |  | 64.7059
Total % Test Cases Not Tested |  | 35.2941
17 | 3
21 | 10
38 | 13
34.21%

## PR Summary
PR No | Title | Status | Type | Nature | Occurrence | Severity | Affected Test Case | Problem Description | Reported By | Reported Date | Problem Analysis | Problem Analysis (Notes) |  | Pkg | Fix Status | Data Loading | Analysed By | Analysed Date | Validation Comment | Validated By | Validated Date | Close Comment | Closed By | Closed Date
[7 empty] | FAT_TRANSACTDM_0001.0001 | Coswin's Purchase order details "Date" and "Del Due Date" needs to be captured in a separate custom field. | Peng Keong |  | Create two new custom fields. CONTRACT.STE_CSWNDATE and CONTRACT.STE_CSWNDELDUEDATE. | Create two new custom fields. PO.STE_CSWNDATE and PO.STE_CSWNDEDUEDATE. | In CONTRACT (PRICE), there is no Purchase Order reference. No mapping. In CONTRACT (BLANKET), it is mapped. New mapping: coswin PO Date => PORDER_.PO_DT coswin PO Del Due Date => PO_ITEMS.PO_ITEM_DEL_DT Need to create custom column | 0302 | Done | Done
[7 empty] | FAT_TRANSACTDM_0001.0001 | SAP GL Code 435666 for blanket contract OS0156/000 doesn’t seems to be mapped to any field in Maximo. Need to check the mapping. | Peng Keong |  | Create a new custom field in maximo. CONTRACT.STE_CSWNSAPGL | Create a new custom field in maximo. | New mapping: PORDER_.PO_STRING1 >> CONTRACT.STE_CSWNSAPGL |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0001.0001 | Unit Cost in contract lines is rounded up. For example: unit cost 13.80 is displayed as 14. | Peng Keong |  | Remove the rounding up of cost values. | Remove the rounding up of cost values. | Backend data is not rounded up. Mapping has no transformation: SUPL_AGREE_ITEM.SUPL_ITEMS.S_LAT_UNIT_RATE >> CONTRACTLINE.UNITCOST |  | No Action | Done
[7 empty] | FAT_TRANSACTDM_0001.0001 | Maximum Amount is blank for contract OS0156/000. | Peng Keong |  | Need to check with Gareth if it was removed as part of cost exercise. | NO | Applicable to CONTRACT (BLANKET) PORDER_.PO_VALUE >> CONTRACTPURCH.MAXVOL | 309 | Done | Done |  |  | Need to check the script
[7 empty] | FAT_TRANSACTDM_0001.0001 | Amount received and amount remaining in costinput table needs to be verified. | Peng Keong |  | Need to check with Gareth if it was removed as part of cost exercise. | NO | Applicable to CONTRACT (BLANKET) PORDER_.PO_DELVD_VALUE -> CONTRACT.STE_COMMITTEDCOST PORDER_.PO_PENDG_VALUE -> CONTRACT.STE_AMOUNTREMAINING |  | Done | Done |  |  | Need to check the script
[7 empty] | FAT_TRANSACTDM_0002.0001 | For the blanket contract buyer is not mapped. PURCHVIEW.PURCHASEAGENT, but the subsequent release POs have buyers. | Peng Keong |  | Coswin Blanket PO Buyer to be mapped with PURCHVIEW.PURCHASEAGENT | Coswin Blanket PO Buyer to be mapped with PURCHVIEW.PURCHASEAGENT | New mapping: PORDER_.PO_REQ_BY >> CONTRACT.PURCHASEAGENT | 0302 | Done | Done
[7 empty] | FAT_TRANSACTDM_0002.0001 | Changeby is maxadmin in for blanket contract. It should be same as amend by in coswim contracts. | Peng Keong |  | Correct value from Coswin's "Amend By" to be populated instead of MAXADMIN. | Correct value from Coswin's "Amend By" to be populated instead of MAXADMIN. | New mapping: PORDER_.PO_AMD_WHO >> CONTRACT.CHANGEBY Default value is still set to MAXADMIN New custom column | 0302 | Done | Done
[7 empty] | FAT_TRANSACTDM_0002.0001 | Payment terms is not mapped for blanket contract OS0156/000. | Peng Keong |  | Payment term mapping to be done. | Payment term mapping to be done. | Currently not mapped yet. To confirm mapping: PORDER_.PO_PAY_DET >> CONTRACT.PAYMENTTERM | 0302 | Done | Done
[7 empty] | FAT_TRANSACTDM_0007.0001 | The count of invoices(credit note + Invoice) is 67 records less in maximo after comparing with coswin's invoices + credit notes. | Peng Keong |  | Need to analyze. | Need to analyze. | Need to check migrated data. Pkg still has error! |  | Not Checked Yet | NA
[7 empty] | FAT_TRANSACTDM_0002.0001 | Make all the WAPPR blanket contracts status as APPR. | Peng Keong |  | Mapping change for blanket contracts: 48 (COSWIN screen = 0) - APPR 54 (COSWIN screen = 6) - WAPPR | Mapping change for blanket contracts: 48 (COSWIN screen = 0) - APPR 54 (COSWIN screen = 6) - WAPPR | Update transformation | 0302 | Done | Done
[7 empty] | FAT_TRANSACTDM_0002.0001 | PO Not authorized (54) (6 on coswin screen) is similar to WAPPR in contract and hence needs to be changed as needed. 0 is approved. | Peng Keong |  | Mapping Change for PO: 48 - just created - APPR 54 - not authorized - WAPPR | Mapping Change for PO: 48 - just created - APPR 54 - not authorized - WAPPR | Update transformation | 0302 | Done | Done
[7 empty] | FAT_TRANSACTDM_0002.0001 | Default the properties as standard values based on when contract type is selected as “BLANKET”,”PRICE” using scripts. For example: If Type is BLANKET: 1. Requires PO? - Y 2. Create Release? – Y 3. Can Exceed amount – Y 4. Add Lines on use? – Y 5. Acceptance Loss? – Y 6. Vendor termination Allowed – Y 7. Customer Termination Allowed? – Y. For Type = 'PRICE': 1. Requires PO? - Y 2. Create Release? – N 3. Can Exceed amount – N 4. Add Lines on use? – N 5. Acceptance Loss? – Y 6. Vendor termination Allowed – Y 7. Customer Termination Allowed? – Y. | Peng Keong |  | Population of default values based on system defaults for Contract Type as "BLANKET", "PRICE". | Population of default values based on system defaults for Contract Type as "BLANKET", "PRICE". | The following need to be updated In Contract Level: 6. Vendor termination Allowed – Y 7. Customer Termination Allowed? – Y. The rest is in 0309-ContractPurch. No change for ContractPurch for Contract (PRICE) | 0301 - Contract (PRICE) 0302 - Contract (BLANKET) 0309 - ContractPurch | Done | Done
[7 empty] | FAT_TRANSACTDM_0003.0001 | For Cost centers part of the GL account (cost center) list should use the Department mapping as provided by SBST for GL account string in PRLINE. | Peng Keong |  | Value migrated in separate columns as cost center needs to be re-mapped to GL account field as a concatenation of Department-cost center - SAP GL Code(optional, only if available). The department should be defaulted as NEL for the cost centers that are not part of the list provided by SBST. Rest should be mapped as per the department-cost center mapping provided by SBST. | Value migrated in separate columns as cost center needs to be re-mapped to GL account field as a concatenation of Department-cost center - SAP GL Code(optional, only if available). The department should be defaulted as NEL for the cost centers that are not part of the list provided by SBST. Rest should be mapped as per the department-cost center mapping provided by SBST. | New mapping |  | Done | Done |  |  | Where is this GL mapping?
[7 empty] | FAT_TRANSACTDM_0003.0001 | For Cost centers that are not part of the list provided by SBST, Department should be defaulted to NEL. | Peng Keong |  | Value migrated in separate columns as cost center needs to be re-mapped to GL account field as a concatenation of Department-cost center - SAP GL Code(optional, only if available). The department should be defaulted as NEL for the cost centers that are not part of the list provided by SBST. Rest should be mapped as per the department-cost center mapping provided by SBST. | Value migrated in separate columns as cost center needs to be re-mapped to GL account field as a concatenation of Department-cost center - SAP GL Code(optional, only if available). The department should be defaulted as NEL for the cost centers that are not part of the list provided by SBST. Rest should be mapped as per the department-cost center mapping provided by SBST. | New calculated field |  | Done | Done |  |  | Where is this GL mapping?
[7 empty] | FAT_TRANSACTDM_0002.0001 | Blanket contract remarks are not captured anywhere. | Peng Keong |  | A new field to be created. CONTRACT.STE_REMARKS | A new field to be created. | To confirm mapping PORDER_.PO_RMK.PO_TXT >> CONTRACT.STE_REMARKS Create new pkg: 0603B_CONTRACT_BLANKET. Pkg 0607-LD PO add filter: WHERE po.PO_TYPE != 49 |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0004.0001 | Coswin RFQ has no description. The RFQ description migrated in Maximo seems to be migrated from coswin’s By Fax/Box/Mail field which is incorrect. As per mapping sheet, it is mapped to RFQVENDOR. STE_CSWNNOTES field. | Peng Keong |  | RFQ Description to be removed. | RFQ Description to be removed. | Remove mapping: RFQ.Description |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0004.0001 | Coswin RFQ’s PR number needs to be mapped to RFQ.STE_PRNUM. | Peng Keong |  | Create a new custom field to migrate PRNUM. | Create a new custom field to migrate PRNUM. | New mapping: DEVIS.DV_PREQ_REF >> RFQ.STE_PRNUM Need to create custom column |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0004.0001 | SAP GL CODE from cownin quotation details is migrated to RFQVENDOR.Need to re-map as part of GL Debit account. | Peng Keong |  | Value migrated in separate columns as cost center needs to be re-mapped to GL account field as a concatenation of Department-cost center - SAP GL Code(optional, only if available). The department should be defaulted as NEL for the cost centers that are not part of the list provided by SBST. Rest should be mapped as per the department-cost center mapping provided by SBST. | Value migrated in separate columns as cost center needs to be re-mapped to GL account field as a concatenation of Department-cost center - SAP GL Code(optional, only if available). The department should be defaulted as NEL for the cost centers that are not part of the list provided by SBST. Rest should be mapped as per the department-cost center mapping provided by SBST. | Create new custom columns: STE_CSWNSAPGL STE_CSWNCC | 0304 | Done | Done |  |  | Where is this GL mapping?
[7 empty] | FAT_TRANSACTDM_0004.0001 | Quotationline is not populated for RFQ CJ01951512003. | Peng Keong |  | Need to verify in case of any script issues. | Need to verify in case of any script issues. | Backend data for RFQ CJ01951512003 has 4 quotation line |  | No action | Done |  |  | Need to see the data
[7 empty] | FAT_TRANSACTDM_0003.0001 | Coswin PR remarks should be populated as PR work log in maximo. | Peng Keong |  | Re-mapping of coswin PR remarks from PR Terms and Conditions to PR work log. | Re-mapping of coswin PR remarks from PR Terms and Conditions to PR work log. | WORKLOG. Update pkg 0604 LD PR |  | Done | Not Done
[7 empty] | FAT_TRANSACTDM_0004.0001 | Maximo computes the value of the quotation at item level but not at vendor level. Rule Related - Document to be updated. | Peng Keong |  | Just a remark. No action required. | Just a remark. No action required. |  |  | No action | Done
[7 empty] | FAT_TRANSACTDM_0004.0001 | RFQ count in maximo is 162306 and coswin is 162129. Total count of quotations mismatch. | Peng Keong |  | To analyse the reason for count mismatch. This can be verified with the latest copy of coswin db. | To analyse the reason for count mismatch. This can be verified with the latest copy of coswin db. | Backend data has consistent count |  | No action | Done
[7 empty] | FAT_TRANSACTDM_0006.0001 | PR number in coswin is not migrated to PO : Sample PO AA10007683. | Peng Keong |  | PR number in coswin to be mapped to PO.STE_PRNUM | PR number in coswin to be mapped to POLINE.PONUM and POLINE.POLINENUM | New mapping: PORDER_.PO_PREQ_REF >> PO.STE_PRNUM Need to create custom column |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0006.0001 | PO AA10007683 has 1 line item in coswin but not in maximo. | Peng Keong |  | To analyse the reason and if there is any issue with the scripts. | To analyse the reason and if there is any issue with the scripts. | Backend data for PO AA10007683 has 1 PO line item! |  | No action | Done |  |  | Need to see the data
[7 empty] | FAT_TRANSACTDM_0006.0001 | Delivery due date under the section "Purchase/Purchase Order/Purchase Order Details/Details" should be migrated to POLINE.REQDELIVERYDATE. The other Deliver due date at top level should be migrated to header level PO. Required date. | Peng Keong |  | Re-mapping of fields. | Re-mapping of fields. | Current mapping: PO_ITEMS.PO_ITEM_DEL_DT -> POLINE.REQDELIVERYDATE New mapping: In POLine: PORDER_.DR_TEXT2 >> POLINE.REQDELIVERYDATE (TRANFORMED) PORDER_.DR_TEXT2 >> POLINE.STE_CSWNREQDELIVERYDATE (AS-IS) In top PO Level: PO_ITEMS.PO_ITEM_DEL_DT -> PO.REQUIREDDATE |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0006.0001 | PO AA10013181 have a contract reference (WAGT21-110)in maximo but no reference in coswin. | Peng Keong |  | To analyse the mismatch in data. | To analyse the mismatch in data. | Remove mapping: PORDER_.SUPPLIER_.SUPPL_AGREE.SAGREE_CODE >> PO.CONTRACTREFNUM Keep mapping: PORDER_.PO_BLKT_REF >> PO.CONTRACTREFNUM (PO_BLKT_REF -> PO.PO_TYPE=49) |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0006.0001 | For coswin number of amendments 1, it seems to be 0 in maximo. Should it be 1 instead? STE to verify. | Peng Keong |  | To analyse the current mapping and why the revision is 0 instead of 1. | To analyse the current mapping and why the revision is 0 instead of 1. | Current mapping: PORDER_.PO_AMD_NO >> PO.REVISIONNUM For PO OS0124/032 (PO_AMD_NO=1), backend migrated data is correct (REVISIONNUM=1) |  | No Action | Done |  |  | Need to see the data
[7 empty] | FAT_TRANSACTDM_0004.0001 | Move RFQ terms and conditions to RFQ.STE_Remarks column in RFQ main tab. | Peng Keong |  | Create a new custom field RFQ.STE_REMARKS and move Coswin RFQ remarks. | Create a new custom field RFQ.STE_REMARKS and move Coswin RFQ remarks. | DV_RMK.DEV_TEXT >> RFQ.STE_REMARK Update in pkg 0608 LD_RFQ_RFQLine |  | Done | Not Done
[7 empty] | FAT_TRANSACTDM_0006.0001 | Total cost value in PO is blank.STE to verify whether it was nullified as part of removing cost value exercise. | Peng Keong |  | Need to check with Gareth if it was removed as part of cost exercise. | NO | Current mapping: PORDER_.PO_VALUE >> PO.TOTALCOST Backend data show correct result. |  | No action | Done
[7 empty] | FAT_TRANSACTDM_0006.0001 | Coswin PO remarks which are migrated to maximo's term n condition to be changed and migrated as part PO worklog. | Peng Keong |  | Re-mapping. | Re-mapping. | PORDER_.PO_RMK >> WORKLOG Update pkg 0607_LD_PO |  | Done | Not Done
[7 empty] | FAT_TRANSACTDM_0007.0001 | INV_DT and INV_RCT_DT is not mapped correctly. INV_DT should be mapped to INVOICE.CHANGEDATE and INV_RCT_DT should be mapped to INVOICE.INVOICEDATE. | Peng Keong |  | Re-mapping. | Re-mapping. | Change the mapping for INVOICEDATE: INVOICE_.INV_RCT_DT >> INVOICE.INVOICEDATE Mapping for CHANGEDATE is already correct: INVOICE_.INV_DT >> INVOICE.CHANGEDATE |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0007.0001 | Coswin Invoice SAP GL Code should be displayed on Maximo Invoice Main Tab. Currently it is mapped to INVOICECOST. STE_CSWNSAPGL. | Peng Keong |  | Re-mapping. INVOICECOST.STE_CSWNSAPGL INVOICE.STE_CSWNSAPGL | Re-mapping. | New mapping: INVOICE_.INV_STRING1 >> INVOICE.STE_CSWNSAPGL New custom column: INVOICE.STE_CSWNSAPGL |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0007.0001 | For Credit note status mapping: 48 - Created - APPR 49 - Validated - APPR 50 - Partially used - APPR 51 - Used - PAID 52 - Cancelled - CANCEL 53 - Closed - PAID | Peng Keong |  | Re-mapping. | Re-mapping. | Change transformation for INVOICE.STATUS. To confirm: This is also for NEG_INV? YES. |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0007.0001 | STE to check from where uninvoiced total is coming in invoice application in maximo.For example : NI-C753M017 | Peng Keong |  | Need to analyze. | Need to analyze. | Calculated columns. Nothing to do |  | No Action | Done
[7 empty] | FAT_TRANSACTDM_0007.0001 | Remaining value for credit notes in coswin needs to be migrated to Invoice.STE_CSWNREMVALUE. | Peng Keong |  | Re-map. | Re-map. | Calculated columns. Nothing to do |  | No Action | Done
[7 empty] | FAT_TRANSACTDM_0007.0001 | GLDebit account needs to be populated for Invoice line, PO line and PR line as per the agreed logic with SBST. | Peng Keong |  | Re-map. | Re-map. | Dept-CC-SAPGL in INVOICECOST |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0008.0001 | 1. POREVISIONUM is missing from matrectrans records which is preventing material receipt to be displayed on screen. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | Add new mapping: RCT_ITEMS.PORDERS_.PO_AMD_NO >> MATRECTRANS.POREVISIONNUM |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0008.0001 | 2. GRN Ref num and GRN date to be displayed on screen? TBD by SBST. | Peng Keong |  | To be decided by SBST. | To be decided by SBST. |  |  | No Action | Done
[7 empty] | FAT_TRANSACTDM_0008.0001 | 3. PO Lines items in maximo is not migrated for PONUM: AA10009897. STE to verify the issue and rectify if it is happening for other POs as well. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | Need to check the migrated data. Similar to row 25. Executing the query manually produce 144 po line items |  | No Action | Done |  |  | Need to see the data
[7 empty] | FAT_TRANSACTDM_0008.0001 | 4. Quantity is showing as -ve for transaction type of Return in material receipts. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | Remove transformation for MATRECTRANS.QUANTITY |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0008.0001 | 5. The migration of DO remarks to MATRECTRANS.STE_CSWNRECEIPTREMARK is missing in maximo.The field is not created in database. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | New mapping: RCT_ITEMS.RCT_RMK.RCT_TXT >> MATRECTRANS.STE_CSWNRECEIPTREMARK Need to create new custom column (LD) Need to create new LD package |  | Done | Not Done
[7 empty] | FAT_TRANSACTDM_0008.0001 | 7. Service receipts needs to be created for service items.For example : PONUM: BB60015612, DO number: 00000015. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | How to create service receipts? SERVRECTRANS Notes: The transformation to get service items is quite messy! Should probably just do a lookup to migrated item table |  | Done | Partial |  |  | Need to see the data
[7 empty] | FAT_TRANSACTDM_0008.0001 | 8. STE to check the treatment for non-PO receipts. For example: miscellaneous type DOs in coswin. | Peng Keong |  | Create a dummy PO (CSWN_NONPO) and tag against it all the miscellaneous receipts. | Create a dummy PO (CSWN_NONPO) and tag against it all the miscellaneous receipts. | Add default value to MATRECTRANS.PONUM mapping: coalesce(RCT_PO_REF, 'CSWN_NONPO') Create a new master pkg to create the dummy PO |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0009.0001 | 1. There is a discrepancy between the count of work orders by 700k in maximo.STE needs to verify for the extra work orders. | Peng Keong |  | Need to analyze. | Need to analyze. |  |  | NA (Gareth) | NA
[7 empty] | FAT_TRANSACTDM_0009.0001 | 2. Gl account needs to be populated as agreed with SBST.STE_CSWNACTIONAUTH field can be used as maintenance entity.The mapping from main entity to department can be found in the sheet shared by SBST. | Peng Keong |  | re-map | re-map |  |  | NA (Gareth) | NA |  |  | Need clarification
[7 empty] | FAT_TRANSACTDM_0009.0001 | Currently no tax-code mapping ITEMS_.I_VAT_CD >> INVVENDOR.STE_TAX1CODE Need to confirm 46:53 | Peng Keong |  | re-map | re-map |  |  | NA (Gareth) | NA |  |  | Need clarification
[7 empty] | FAT_TRANSACTDM_0009.0001 | 4. Work order main tab duration field needs to be populated.STE to verify the logic for the duration field in work order. | Peng Keong |  | This should be based on Actual Finish - Actual Start. | This should be based on Actual Finish - Actual Start. |  |  | NA (Gareth) | NA
[7 empty] | FAT_TRANSACTDM_0009.0001 | 5. STE to migrate work permit WIP_WO.WO_WORK_PERMIT from work order to maximo workorder.STEWP. | Peng Keong |  | Re-map. | Re-map. |  |  | NA (Gareth) | NA |  |  | Need clarification
[7 empty] | FAT_TRANSACTDM_0009.0001 | 6. coswin wo type values are : U Unplanned - 80 P Planned - 79 O Others - 85 it seems to be wrongly migrated: for example wo number :1202559. it is unplanned in coswin and hence STE_CSWNWOTYPE value should be 80 instead of 85. | Peng Keong |  | Re-map | Re-map |  |  | NA (Gareth) | NA |  |  | What is the new mapping?
[7 empty] | FAT_TRANSACTDM_0009.0001 | 7.Coswin Cost Type field is not migrated to any field in maximo. | Peng Keong |  | To create a new field STE_CSWNCOSTTYPE. | To create a new field STE_CSWNCOSTTYPE. |  |  | NA (Gareth) | NA
[7 empty] | FAT_TRANSACTDM_0009.0001 | 8. Labor 132794 should be migrated to labtrans (laborcode) instead of it's LAN ID: NEISTO03 | Peng Keong |  | Re-map. | Re-map. |  |  | NA (Gareth) | NA |  |  | Need clarification?
[7 empty] | FAT_TRANSACTDM_0009.0001 | Chainage number from and to fields in coswin are: WIP_WO.FREE2 and WIP_WO.FREE3.It was not migrated early due to these two technical fields. | Peng Keong |  | Re-map. | Re-map. |  |  | NA (Gareth) | NA
[7 empty] | FAT_TRANSACTDM_0009.0001 | Need to check where Job Activ remarks and Spec. Text are migrated to in maximo. | Peng Keong |  | Re-map. | Re-map. |  |  | NA (Gareth) | NA |  |  | Need to see the data
[7 empty] | FAT_TRANSACTDM_0010.0001 | 1. The count in maximo is 6 times more than coswin.STE to verify from where this is coming. | Peng Keong |  | Need to analyze. | Need to analyze. |  |  | NA (Gareth) | NA |  |  | Which table? SR?
[7 empty] | FAT_TRANSACTDM_0010.0001 | 2. The time for sanction from and sanction to is not migrated to target start and target finish in SR in maximo. | Peng Keong |  | Map to new fields. | Map to new fields. |  |  | NA (Gareth) | NA |  |  | What is the mapping?
[7 empty] | FAT_TRANSACTDM_0010.0001 | 3. Coswin Job Request supervisor to be migrated to SR.STE_CSWNSUP field. | Peng Keong |  | Map as required. | Map as required. |  |  | NA (Gareth) | NA
[7 empty] | FAT_TRANSACTDM_0010.0001 | 4. Failure reporting in coswin SR does not exist, but migrated sr record in maximo is having failure class and problem code populated. STE to verify on how the failure class and problem code is getting populated in maximo. Sample SR: 15JR133755 | Peng Keong |  | Need to analyze. | Need to analyze. |  |  | NA (Gareth) | NA
[7 empty] | FAT_TRANSACTDM_0011.0001 | Min Qty, Max Qty, Reorder Point, Safety Stock showing 0 on screen. It is having values in Coswin. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | Map ITEM_INFO via ITEM_ instead of directly from STOREITEM. Please verify the following fields as well (similar to MinQty, originally from ITEM_ but now from STOREITEM): MAXLEVEL MINLEVEL SSTOCK DELIVERYTIME ISSUE1YRAGO ISSUE2YRAGO CURBALTOTAL AVBLBALANCE RESERVEDQTY ORDERQTY |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0011.0001 | Population field is present in Coswin but is not mapped to Maximo. | Peng Keong |  | Need to create a new field STE_CSWNPOPULATION. | Need to create a new field STE_CSWNPOPULATION. | New mapping: ITEM_.ITEM_NUMBER1 >> INVENTORY.STE_CSWNPOPULATION Need to create custom mapping |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0011.0001 | Currently Coswin Stockout Risk %, Cyclic Re-order and No. of days in Cycle is not mapped to any Maximo fields. To clarify if this field should be populated to a new field within Inventory. These fields are currently not available for verification. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | ITEM.STKOUT_RISKP -> STE_CSWNSTKRISK ITEM_INFO.I_CYCLIC_REORDER -> STE_CYCLICREORDER ITEM_INFO.I_CYCLE -> STE_NODAYSCYCL |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0011.0001 | Coswin ORG_SUPL_CD is currently mapped to Inventory Manufacturer. The mapping is incorrect as the Suppliers are Vendors. SBST proposed that the original Supplier Code to be mapped to a new separate field instead of Manufacturer. | Peng Keong |  | Map to new fields: STE_CSWNSUPPLIER | Need to re-visit scripts. | Remove mapping on INVENTORY.MANUFACTURER Update mapping to custom column. STORES_ITEMS.ITEM_.ORG_SUPL_CD >> INVENTORY.STE_CSWNSUPPLIER Need to create custom column |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0012.0001 | Coswin GST not mapped correctly to Maximo Inventory Vendor Tax Code. It should display GST in Inventory Vendor for all Items that are associated with GST. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | Map to default value: "GST" >> INVVENDOR.TAX1CODE |  | Done | Done |  |  | What is the mapping?
[7 empty] | FAT_TRANSACTDM_0012.0001 | The Coswin Max Lead Time is mapped to Inventory Delivery Time. SBST feedback that the Max Lead Time should also be within the same Section as the Min, Average Lead Time in the Inventory Vendor Section. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | Keep mapping in INVENTORY: STORES_ITEMS. ITEM_. ITEM_INFO.MAX_LEAD_TIME >> INVENTORY.DELIVERYTIME Mapping INVVENDOR: STORES_ITEMS. ITEM_. ITEM_INFO.MAX_LEAD_TIME >>INVVENDOR.PROMDELIVERYTIME |  | Done | Done |  |  | What is the mapping? Any example?
[7 empty] | FAT_TRANSACTDM_0012.0001 | Coswin First Procured Date is mapped to the Inventory Vendor Last Order Date. However, the Last Order Date is not showing the correct information. SBST proposed to store the First Procured Date. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | Currently INVVENDOR.LASTDATE is mapped to SUPL_ITEMS.S_L_DT_PO. New mapping: ITEM_.DT_FIRST_PROC >> INVENTORY.STE_FIRSTPROCDATE |  | Done | Done |  |  | What is the mapping?
[7 empty] | FAT_TRANSACTDM_0012.0001 | Remarks Column is advised by SBST to be stored in the STK_ITEM. STE to check if the Remarks field can be retrieved and stored in Maximo Item Application. | Peng Keong |  | Map to new fields: STE_REMARKS | Need to re-visit scripts. | New mapping: SUPL_RMK.SUPL_TXT >> INVVENDOR.STE_REMARKS Need to create new custom column (LD) Need to create new LD package |  | Done | Not Done |  |  | What is the mapping?
[7 empty] | FAT_TRANSACTDM_0012.0001 | 1899-12-31 is visible for Last PO Date. To amend the mapping of the date value if it is NULL or 0. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | Set to NULL if value = 1899-12-31. Set default value to NULL |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0012.0001 | Last Price is showing 0 for all records. User feedback that it should not show 0, but instead, the Unit Price of the Item should be displayed. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | Update mapping: SUPL_ITEMS.S_LAT_UNIT_RATE >> INVVENDOR.LASTCOST If SUPL_ITEMS.S_LAT_UNIT_RATE=0 then: SUPL_ITEMS.ITEM_.BUY_PRICE >> INVVENDOR.LASTCOST |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0012.0001 | STE_CSWNLASTPO is not displayed correctly. TO check mapping of the field. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | Missing mapping: SUPL_ITEMS.S_L_PO >> INVVENDOR.STE_CSWNLASTPO |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0014.0001 | 1. Coswin Demand "From" date should be migrated to MR.REQUIREDDATE and "To" date should be migrated to "STE_CSWNDEMTODATE". | Peng Keong |  | New custom column: STE_CSWNDEMTODATE | Need to re-visit scripts. | New mapping. New custom column |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0014.0001 | 2. Entered date needs to be displayed on screen. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | Currently MR.ENTERDATE is mapped to DEM_ISS.DEM_DT |  | No Action | Done
[7 empty] | FAT_TRANSACTDM_0014.0001 | 3. Demand remarks should be migrated to STE_DEMREMARKS. | Peng Keong |  | New custom column: MR.STE_DEMREMARKS | Need to re-visit scripts. | New mapping: DEM_ISS.ISS_RMK >> MR.STE_DEMREMARKS. New custom column |  | Done | Not Done
[7 empty] | FAT_TRANSACTDM_0014.0001 | 4. Material Requisions status mapping: 48 - 0 - No Issued - APPR 49 - 1 - Part Issued - APPR 50 - 2 - Issue Completed - CLOSE 51 - 3 - Cancelled - CAN 52 - 4 - Not Validated - WAPPR 57 - 9- Directly Issued - CLOSE | Peng Keong | WHEN DEM_STATUS=48 THEN 'APPR' WHEN DEM_STATUS=49 THEN 'APPR' WHEN DEM_STATUS=50 THEN 'CLOSE' WHEN DEM_STATUS=51 THEN 'CAN' WHEN DEM_STATUS=52 THEN 'WAPPR' WHEN DEM_STATUS=57 THEN 'APPR' | Need to re-visit scripts. | Need to re-visit scripts. | Update transformation |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0014.0001 | 5. MATUSETRANS.STORELOC is "Transit" for all the items.It should be populated with the correct item location. For example: item TRAIN /GEN/AR/01. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | Get actual store loc: SELECT ii.PK_ISS_ITEMS, ii.ISS_REF, dli.PK_DEM_LOC_INT, l.PK_LOCATION_, si.IS_STOR_CD FROM coswin.ISS_ITEMS ii LEFT JOIN coswin.DEM_LOC_INT dli ON dli.S_ISS_LOC_INT = ii.PK_ISS_ITEMS LEFT JOIN coswin.LOCATION_ l ON l.PK_LOCATION_ = dli.S_LOC_DEM_INT LEFT JOIN coswin.STORES_ITEMS si ON si.PK_STORES_ITEMS = l.S_STORES_ITEM_LOC WHERE ii.S_ITEM_ISS=27322 |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0014.0001 | 6. Transfer transactions are not migrated to maximo. For example: Item number: TRAIN /GEN/AR/01. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | TR_ITEMS >> cswn_tr_items H_TRANSFER >> cswn_h_transfer H_TR_ITEMS >> NO DATA H_TRANSFER is parent of H_TR_ITEMS. Since H_TR_ITEMS is empty, no need to migrate H_TRANSFER (ie. no detail data such as quantity, etc) Create record: MATRECTRANS (IssueType= 'SHIPTRANSFER') |  | WIP | Not Done
[7 empty] | FAT_TRANSACTDM_0014.0001 | 7. Issue number from coswin is not migrated in maximo. Issues number exammple: ISS12577. This needs to be migrated to matusetrans.STE_ISSUENUM. | Peng Keong |  | New custom column: MATUSETRANS.STE_ISSUENUM | Need to re-visit scripts. | New mapping: ISS_ITEMS.ISS_REF >> MATUSETRANS.STE_ISSUENUM New custom column |  | Done | Done
[7 empty] | FAT_TRANSACTDM_0014.0001 | 8. Need to populate coswin adjustments to invtrans in maximo.Coswin STK_ADJ table needs to be migrated to INVTRANS. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | Need to create new pkg! TransType='PCOUNTADJ' | 206 | Done | Not Done
Note on M2: Wahyu Yoga Pratama: Maximo table is CONTRACT, not PO
Note on M24: Wahyu Yoga Pratama: PR should be in PO level? Also, POLINE.PONUM refer to parent PO. Can not be used to store PRNUM.

## Custom Column
0303 | PO_PR_PRCost | DF-PR | Need to extend PRLine.Description to 104 char
|  |  | New custom column: PR.STE_CSWNSAPGL | VARCHAR | 20
0304 | PO_RFQ |  | Need to extend RFQLine.Description to 104 char |  |  | di.PK_DV_ITEMS = 553226
|  |  | Need to extend Item related description to 104 char |  |  | Item with STE_MIGRATIONID=84190 has description truncated
|  |  | New custom column: RFQ.STE_CSWNSAPGL | VARCHAR | 20
|  |  | New custom column: RFQLINE.STE_CSWNSAPGL | VARCHAR | 20
|  |  | New custom column: RFQLINE.STE_CSWNCC | VARCHAR | 16
|  |  | New custom column: RFQ.STE_PRNUM | VARCHAR | 12
|  |  | New custom column: RFQ.STE_REMARKS | VARCHAR | With long description
0202 | InvVendor |  | Need to extend InvVendor.Description to 104 char
|  |  | New custom column: INVVENDOR.STE_REMARKS | VARCHAR | With long description
0205 | MR_MRLine |  | Need to extend MR.WONUM to 25 char (consistent with WORKORDER.WONUM)
|  |  | New custom column: MR.STE_CSWNDEMTODATE | DATE
|  |  | New custom column: MR.STE_REMARKS | VARCHAR | With long description
|  |  | New custom column: MR.STE_CSWNCC | VARCHAR | 16
0302 | PO_Contract (Blanket) |  | New custom column: CONTRACT.STE_CSWNDATE | DATE
|  |  | New custom column: CONTRACT.STE_CSWNDELDUEDATE | DATE
Custom column: ste_actualstartdate (date) mapped from PO_VALID_FM
|  |  | New custom column: CONTRACT.STE_REMARKS | VARCHAR | With long description
|  |  | New custom column: CONTRACT.STE_GLACCOUNT | VARCHAR | 110
0306 | PO_PO |  | New custom column: STE_PRNUM | VARCHAR | 12
0206 | INVTRANS |  | New custom column: INVTRANS.STE_CSWNCC | VARCHAR | 16
|  |  | New custom column: INVTRANS.STE_SCCODE | VARCHAR | 10
|  |  | New custom column: INVTRANS.STE_ADJVAL | DECIMAL | 22,10
|  |  | New custom column: INVTRANS.STE_ADJUNITCOST | DECIMAL | 22,10
0308A | SERVRECTRANS |  | New custom column: SERVRECTRANS.STE_CSWNCC | VARCHAR | 16
|  |  | New custom column: SERVRECTRANS.STE_CSWNSAPGL | VARCHAR | 20
|  |  | New custom column: SERVRECTRANS.STE_CSWNDNDATE | DATETIME | 10
|  |  | New custom column: SERVRECTRANS.STE_CSWNFWDR | VARCHAR | 15
|  |  | New custom column: SERVRECTRANS.STE_CSWNGRNDATE | DATETIME | 10
|  |  | New custom column: SERVRECTRANS.STE_CSWNGRNNUM | VARCHAR | 10
|  |  | New custom column: SERVRECTRANS.STE_CSWNGRNREF | VARCHAR | 10
|  |  | New custom column: SERVRECTRANS.STE_CSWNINSPSTATUS | VARCHAR | 20
|  |  | New custom column: SERVRECTRANS.STE_CSWNINSPDATE | DATETIME | 10
|  |  | New custom column: SERVRECTRANS.STE_CSWNINSPREF | VARCHAR | 10
|  |  | New custom column: SERVRECTRANS.STE_CSWNINSPSTAT | NUMBER | 3
|  |  | New custom column: SERVRECTRANS.STE_CSWNRCTSTATUS | SMALLINT | 3
|  |  | New custom column: SERVRECTRANS.STE_CSWNRECEIPTCHANGEDATE | DATETIME | 10
|  |  | New custom column: SERVRECTRANS.STE_CSWNRECEIPTFORWARDER | VARCHAR | 15
|  |  | New custom column: SERVRECTRANS.STE_CSWNRECEIPTTYPE | SMALLINT | 3
|  |  | New custom column: SERVRECTRANS.STE_CSWNRECEIPTREMARK | VARCHAR | With long description
| INVOICE |  | New custom column: INVOICE.STE_CSWNSAPGL | VARCHAR | 20
| INVENTORY |  | New custom column: INVENTORY.STE_CSWNSTKRISK | DECIMAL | 22,10
|  |  | New custom column: INVENTORY.STE_CYCLICREORDER | DECIMAL | 5,0
|  |  | New custom column: INVENTORY.STE_NODAYSCYCL | DECIMAL | 5,0
|  |  | New custom column: INVENTORY.STE_CSWNSUPPLIER | VARCHAR | 20
|  |  | New custom column: INVENTORY.STE_CSWNPOPULATION | DECIMAL | 22,10
| MATUSETRANS |  | New custom column: MATUSETRANS.STE_ISSUENUM | varchar | 8
| MATRECTRANS |  | New custom column: MATRECTRANS.STE_CSWNRECEIPTREMARK | VARCHAR | With long description
| CONTRACTTERM |  | New custom column: CONTRACTTERM.STE_MIGRATIONSOURCE | VARCHAR | 50
| CHARTOFACCOUNTS |  | New custom column: CHARTOFACCOUNTS.STE_MIGRATIONSOURCE | VARCHAR | 50
| SERVRECTRANS |  | New custom column: SERVRECTRANS.STE_CSWNRECEIPTREMARK | VARCHAR | With long description
| MATRECTRANS |  | New custom column: MATRECTRANS.STE_MIGRATIONSOURCE | VARCHAR | 50
| POLINE |  | New custom column: POLINE.STE_CSWNSAPGL | VARCHAR | 20
Need to extend POLINE.GLDEBITACCT to 110 char
| PERSON |  | PERSON.BARCODE extend to 16
| TLOAMASSETGRP |  | New custom column: TLOAMASSETGRP.STE_CSWNAUTHORITY | VARCHAR | 16
| invlot |  | New custom column: INVLOT.STE_MIGRATIONID | BIGINT
|  |  | New custom column: INVLOT.STE_MIGRATIONDATE | TIMESTAMP
| invoicecost |  | invoicecost.gldebitacct extend to 110
| invtrans |  | New custom column: INVTRANS.STE_MIGRATIONTS | integer
| GLCOMPONENTS |  | New custom column: GLCOMPONENTS.STE_MIGRATIONID | BIGINT
|  |  | New custom column: GLCOMPONENTS.STE_MIGRATIONDATE | TIMESTAMP
|  |  | New custom column: GLCOMPONENTS.STE_MIGRATIONSOURCE | VARCHAR | 50
|  |  | New custom column: GLCOMPONENTS.STE_COSTCENTREDEPT | VARCHAR | 50
| ITEM |  | New custom column: ITEM.STE_CSWNITEMNO | VARCHAR | 30
|  |  | New custom column: ITEM.STE_SPARECRITICAL | VARCHAR | 2
| PERSONANCESTOR |  | New custom column: PERSONANCESTOR.STE_MIGRATIONID | BIGINT
|  |  | New custom column: PERSONANCESTOR.STE_MIGRATIONDATE | TIMESTAMP
| ITEM |  | extend ste_itempartno to 60 char
extend itemnum to 40 char
| STE_CSWNASSETSLHIST |  | extend STE_CSWNSNO to 30 char
| INVENTORY |  | New custom column: INVENTORY.STE_FIRSTPROCDATE | TIMESTAMP
| INVLOT |  | New custom column: INVLOT.STE_MIGRATIONTS | INTEGER
| Need to recreate |  | PO.STE_MIGRATIONTS | INTEGER
|  |  | RFQ.STE_MIGRATIONTS | INTEGER
-- PLUSTMTRCHNG
ALTER TABLE MAXIMO.PLUSTMTRCHNG ADD "STE_MIGRATIONID" BIGINT;
ALTER TABLE MAXIMO.PLUSTMTRCHNG ADD "STE_MIGRATIONDATE" TIMESTAMP;
ALTER TABLE MAXIMO.PLUSTMTRCHNG ADD "STE_MIGRATIONTS" INTEGER;
-- PLUSTMTRCHNG
ALTER TABLE MAXIMO.PLUSTASSETSTHIST ADD "STE_MIGRATIONID" BIGINT;
ALTER TABLE MAXIMO.PLUSTASSETSTHIST ADD "STE_MIGRATIONDATE" TIMESTAMP;
ALTER TABLE MAXIMO.PLUSTASSETSTHIST ADD "STE_MIGRATIONTS" INTEGER;
ALTER TABLE MAXIMO.AMCREW ADD "STE_MIGRATIONSOURCE" VARCHAR(50);
ALTER TABLE MAXIMO.MATRECTRANS ADD "STE_CSWNACPQTY" DECIMAL(15,2);
ALTER TABLE MAXIMO.MATRECTRANS ADD "STE_CSWNRTNTOSUPL" DECIMAL(15,2);
ALTER TABLE MAXIMO.SERVRECTRANS ADD "STE_CSWNACPQTY" DECIMAL(15,2);
ALTER TABLE MAXIMO.SERVRECTRANS ADD "STE_CSWNRTNTOSUPL" DECIMAL(15,2);
ALTER TABLE MAXIMO.MATRECTRANS ADD "STE_CSWNRCTQTY" DECIMAL(15,2);
ALTER TABLE MAXIMO.MATRECTRANS ADD "STE_CSWNRCTVAL" DECIMAL(13,5);
ALTER TABLE MAXIMO.SERVRECTRANS ADD "STE_CSWNRCTQTY" DECIMAL(15,2);
ALTER TABLE MAXIMO.SERVRECTRANS ADD "STE_CSWNRCTVAL" DECIMAL(13,5);
ALTER TABLE MAXIMO.ALNDOMAIN ADD "STE_MIGRATIONID" BIGINT;
ALTER TABLE MAXIMO.ALNDOMAIN ADD "STE_MIGRATIONDATE" TIMESTAMP;
ALTER TABLE MAXIMO.ALNDOMAIN ADD "STE_MIGRATIONSOURCE" VARCHAR(50);
ALTER TABLE MAXIMO.ALNDOMAIN ADD "STE_MIGRATIONTS" INTEGER;
ALTER TABLE MAXIMO.MR ADD "STE_CSWNDEMTYPE" INTEGER;
ALTER TABLE MAXIMO.ITEM ADD "STE_NONSTOCKFLAG" VARCHAR(1);
ALTER TABLE MAXIMO.INVOICELINE ADD "STE_CSWNITEMBASEVAL" DECIMAL(18,2);
ALTER TABLE MAXIMO.COMPMASTER ADD "STE_CSWNSUPLTYPE" VARCHAR(1);
ALTER TABLE MAXIMO.COMPANIES ADD "STE_CSWNSUPLTYPE" VARCHAR(1);
ALTER TABLE MAXIMO.INVOICE ADD "STE_CSWNSTRING3" VARCHAR(20);
ALTER TABLE MAXIMO.CALENDAR ADD "STE_MIGRATIONID" BIGINT;
ALTER TABLE MAXIMO.CALENDAR ADD "STE_MIGRATIONDATE" TIMESTAMP;
ALTER TABLE MAXIMO.WORKPERIOD ADD "STE_MIGRATIONID" BIGINT;
ALTER TABLE MAXIMO.WORKPERIOD ADD "STE_MIGRATIONDATE" TIMESTAMP;
ALTER TABLE MAXIMO.PERSONCAL ADD "STE_MIGRATIONID" BIGINT;
ALTER TABLE MAXIMO.PERSONCAL ADD "STE_MIGRATIONDATE" TIMESTAMP;
ALTER TABLE MAXIMO.INVOICE ADD "STE_CSWNISSUEDATE" DATE;
ALTER TABLE MAXIMO.PERSONGROUP ADD "STE_DEPARTMENT" VARCHAR(16);
RESIZE LOCATIONS.STE_TUNNEL TO 8 CHAR
RESIZE LOCATIONS.STE_TRAINAREA TO 4 CHAR

## Sheet1
10981 | 9381 | 2621101 | 4 | 50 | 50 | 0 | 1
10981 | 9382 | 2621102 | 3 | 50 | 50 | 0 | 2
10981 | 9383 | 2621103 | 3 | 50 | 50 | 0 | 3
10981 | 9384 | 2621104 | 3 | 50 | 50 | 0 | 4
10981 | 9385 | 2621105 | 3 | 50 | 50 | 0 | 5
10981 | 9386 | 2621106 | 3 | 50 | 50 | 0 | 6
10981 | 9387 | 2621107 | 3 | 50 | 50 | 0 | 7
10981 | 9388 | 2621108 | 3 | 50 | 50 | 0 | 8
10981 | 9389 | 2621109 | 3 | 50 | 50 | 0 | 9
10981 | 9390 | 2621110 | 3 | 50 | 50 | 0 | 10
10981 | 9391 | 2621111 | 3 | 50 | 50 | 0 | 11
10981 | 9392 | 2621112 | 3 | 50 | 50 | 0 | 12
10981 | 9393 | 2621113 | 3 | 50 | 50 | 0 | 13
10981 | 9394 | 2621114 | 3 | 50 | 50 | 0 | 14
10981 | 9395 | 2621115 | 3 | 50 | 50 | 0 | 15
10981 | 9396 | 2621116 | 4 | 50 | 50 | 0 | 16

## Drop down list (hidden)
Event Type | Nature | Occurrence | Severity | Status
Error | Document | Constant Defect | Critical | Pending Analysis
Fault | Software | Random Defect | Major | Pending Validation
Evolution | Hardware | Defect due to change | Minor | Pending Closure
Improvement |  |  |  | Closed