## Migration Plan
# | Activity |  | Duration | Coswin Running | MAS Running
1 | Get Dec Dump File | First Iteration | 3 Days | X
2 | Restore Dec Dump to Local Oracle DB | First Iteration |  | X
3 | Do Migration to MAS 8.7 DB2 | First Iteration |  | X
4 | Maximo configuration | First Iteration |  | X | X
5 | User Testing/Data Validation | First Iteration | 1-2 Days | X | X
6 | Backup Iteration1 MAS DB | Parallel Run |  | X | X
7 | Parallel Run (>= 1 week) | Parallel Run |  | X | X
8 | Restore Iteration1 MAS DB Backup (Make sure configuration changes during Parallel Run ARE carried over) | Parallel Run |  | X | X
9 | Get Dec2 Dump File | Second Iteration (Delta) | <= 2 days |  | X
10 | Restore Dec2 Dump to Local Oracle DB | Second Iteration (Delta) |  |  | X
11 | Delta Migration | Second Iteration (Delta) |  |  | X
12 | Cut-off | Cut-off |  |  | X
# | Delta Migration Strategy | Est. Duration
1 | Get Oracle Dump File | 16 hours
2 | Restore December Dump to Local Oracle DB
3 | Do Full Migration (Dec Data) to DB2 Staging: | 32 hours | 24 hours
4 | Check for Delta Data between DB2 Staging (Delta) and MAS 8.7 (Base) |  | 8 hours
5 | Run Update SQL from DB2 Staging schema (Delta) to MAXIMO schema (Base)

## Delta Migration Strategy
SSIS Package Name | Delta? | Delta Strategy | Notes | MAX Tables | Coswin Tables
0003_Master_Locations.dtsx | N
0004_Master_Person.dtsx | N
0005_Master_Meter.dtsx | N
0006_Master_Classification_ClassStructure.dtsx | N
0007_Master_AssetAttribute_ClassSpec_ClassSpecUseWith.dtsx | N
0008A_Master_FailureCode.dtsx | N
0008B_Master_FailureList.dtsx | N
0009_Master_Routes.dtsx | N
0010_Master_Item_ItemOrgInfo.dtsx | N
0011_Master_CompMaster_CompContactMstr.dtsx | N
0012_Master_Companies_CompContact.dtsx | N
0013_Master_Craft_CraftSkill.dtsx | N
0014_Master_PersonGroup.dtsx | N
0015_Master_PersonGroupTeam.dtsx | N
0016_Master_Labor.dtsx | N
0017_Master_AMCrewType_AMCrew_AMCrewLabor.dtsx | N
0018_Master_MeasureUnit.dtsx | N
0019A_Master_GL_CC.dtsx | N
0019B_Master_ChartOfAsscounts.dtsx | N
0020_Master_Workzone.dtsx | N
0021_Master_ItemStruct.dtsx | N
0022_Master_Commodities.dtsx | N
0023_Master_AltItem.dtsx | N
0101_Asset_Asset.dtsx | ? | Add-Update-Delete |  | ASSET | EQP_TOPO
0102_Asset_AssetLocUserCust.dtsx | ? | Add-Update-Delete |  | ASSETLOCUSERCUST | EQP_TOPO
0103_Asset_AssetMeter.dtsx | ? | Add-Update-Delete | Ref to ASSET | ASSETMETER | EQP_METER
0104_Asset_STE_CSWNASSETSLHIST.dtsx | ? | Add-Update-Delete |  | STE_CSWNASSETSLHIST | EQP_SRL
0105_Asset_AssetTrans.dtsx | ? | Add-Update-Delete | Ref to ASSET | ASSETTRANS | EQP_MOVE
0106_Asset_AssetSpec.dtsx | ? | Add-Update-Delete | Ref to assetspec | ASSETSPEC | EQP_TECH
0107_Asset_SpareParts.dtsx | ? | Add-Update-Delete |  | SPAREPART | EQP_SPARE
0108_Asset_RouteStop.dtsx | ? | Add-Update-Delete |  | ROUTESTOP | EQP_GROUP
0109_Asset_AssetAncestor.dtsx | ? | Add-Update-Delete |  | ASSETANCESTOR | EQP_TOPO
0110_Asset_AssetWorkzone.dtsx | ? | Add-Update-Delete |  | ASSETWORKZONE | EQP_TOPO
0111_Asset_TLOAMASSETGRP.dtsx | ? | Add-Update-Delete |  | TLOAMASSETGRP | EQP_TOPO
0201_Inventory_Inventory.dtsx | Y | Add-Update-Delete |  | INVENTORY | STORES_ITEMS
0202_Inventory_InvVendor.dtsx | Y | Add-Update-Delete |  | INVVENDOR | SUPL_ITEMS
0203_Inventory_InvBalances.dtsx | Y | Add-Update-Delete |  | INVBALANCES | LOCATION_
0204_Inventory_InvCost.dtsx | Y | Add-Update-Delete |  | INVCOST | STORES_ITEMS
0205_Inventory_MR_MRLine.dtsx | Y | Add-Update-Delete |  | MR, MRLINE | DEM_ISS, DEM_ITEMS | No package for Inventory_MATUSETRANS?
0301_PO_Contract_ContractLine.dtsx | Y | Add-Update-Delete |  | CONTRACT CONTRACTLINE | SUPP_AGREE, SUPL_AGREE_ITEM
0302_PO_Contract_ContractLine_Blanket.dtsx | Y | Add-Update-Delete |  | CONTRACT CONTRACTLINE | PORDER_ , PO_ITEMS
0303_PO_PR_PRLine_PRCost.dtsx | Y | Add-Update-Delete Truncate-Insert (PRCOST) |  | PR, PRLINE, PRCOST (SQL) | PREQUEST, PR_ITEMS
0304_PO_RFQ_RFQLine.dtsx | Y | Add-Update-Delete |  | RFQ, RFQLINE | DEVIS, DV_ITEMS
0305_PO_RFQVendor_QuotationLine.dtsx | Y | Add-Update-Delete |  | RFQVENDOR, QUOTATIONLINE | DEVIS, DV_ITEMS
0306_PO_PO_POLine_POCost.dtsx | Y | Add-Update-Delete Truncate-Insert (POCOST) |  | PO, POLINE, POCOST (SQL) | PORDER_, PO_ITEMS
0307_PO_Invoice_InvoiceLine_InvoiceCost.dtsx | Y | Add-Update-Delete |  | INVOICE, INVOICELINE, INVOICECOST | INVOICE_, NEG_INV, INV_ITEMS | Why DF for INVOICE_ is disabled? Can we use SQL for INVOICECOST?
0308_PO_MATRECTRANS.dtsx | Y | Add-Update-Delete |  | MATRECTRANS | RCT_ITEMS
0309_PO_ContractPurch.dtsx | Y | Add-Update-Delete |  | CONTRACTPURCH | SUPP_AGREE, PORDER_
0401_WO_Workorder.dtsx | Y | Add-Update-Delete |  | WORKORDER | WIP_WO, WIP_WA
0402_WO_WOActivity.dtsx | Y | Add-Update-Delete | Ref to Workorder | WORKORDER | WIP_WA
0403_WO_LabTrans.dtsx | Y | Add-Update-Delete | Ref to Workorder | LABTRANS | WIP_WE
0405_WO_SR.dtsx | Y | Add-Update-Delete |  | TICKET | EQP_JOBR
0406_WO_FailureReport.dtsx | Y | Add-Update-Delete |  | FAILUREREPORT | EQP_DEFR
0407_WO_RelatedRecord.dtsx | Y | Truncate-Insert | Ref to Workorder. Ref to Ticket | RELATEDRECORD (SQL) | WIP_WO, EQP_JOBR
0408_WO_WPLabor_WPMaterial.dtsx | Y | Add-Update-Delete |  | WPLABOR, WPMATERIAL | WIP_WT, ISS_ITEMS
0409_WO_MATUSETRANS.dtsx | Y | Add-Update-Delete |  | MATUSETRANS | ISS_ITEMS
0501_Misc_Currency.dtsx | O | Truncate-Insert
0502_Misc_Exchange.dtsx | Y | Truncate-Insert
0503_Misc_Qualification.dtsx | Y | Truncate-Insert
0504_Misc_PPCraftRate.dtsx | Y | Truncate-Insert
0505_Misc_LaborQual.dtsx | Y | Truncate-Insert
0506_Misc_Attendance.dtsx | Y | Truncate-Insert
0507_Misc_Address.dtsx | O | Truncate-Insert
0508_Misc_MeterReading.dtsx | Y | Truncate-Insert
0509_Misc_WorkType.dtsx | O | Truncate-Insert
0510_Misc_ServiceItems.dtsx | O | Truncate-Insert
0511_Misc_JobPlan_JPAssetsPLink_JobTask.dtsx | Y | Truncate-Insert
0512_Misc_JobLabor.dtsx | Y | Truncate-Insert
0513_Misc_JobMaterial.dtsx | Y | Truncate-Insert
0514_Misc_PM_PMMeter_PMSeasons.dtsx | Y | Truncate-Insert
0515_Misc_Shift_ShiftPatternDay.dtsx | Y | Truncate-Insert
0601_LD_CompMaster.dtsx | N
0602_LD_Asset.dtsx | N
0603_LD_Contract.dtsx | N
0604_LD_PR.dtsx | N
0605A_LD_Workorder_Worklog.dtsx | N
0605_LD_Workorder.dtsx | N
0606_LD_SR.dtsx | N
0607_LD_PO.dtsx | N
0608_LD_RFQ_RFQLine.dtsx | N
0609_LD_Item.dtsx | N
0610_LD_Invoice.dtsx | N
0611_LD_PO_BILLTO.dtsx | N
0701_Others_AuditTables1.dtsx | Y | Truncate-Insert
0702_Others_AuditTables2.dtsx | Y | Truncate-Insert
0703_Others_AuditTables3.dtsx | Y | Truncate-Insert
0704_Others_AuditTables4.dtsx | Y | Truncate-Insert
0705_Others_AuditTables5.dtsx | Y | Truncate-Insert
0706_Others_TransactionTables1.dtsx | Y | Truncate-Insert
0707_Others_TransactionTables2.dtsx | Y | Truncate-Insert
0708_Others_TransactionTables3.dtsx | Y | Truncate-Insert
0709_Others_TransactionTables4.dtsx | Y | Truncate-Insert
0710_Others_TransactionTables5.dtsx | Y | Truncate-Insert
0711_Others_TransactionTables6.dtsx | Y | Truncate-Insert
0712_Others_TransactionTables7.dtsx | Y | Truncate-Insert
0713_Others_TransactionTables8.dtsx | Y | Truncate-Insert
0714_Others_MasterTables1.dtsx | Y | Truncate-Insert
0715_Others_MasterTables2.dtsx | Y | Truncate-Insert
0716_Others_Supplier.dtsx | Y | Truncate-Insert