## Overview
Legend | Description
NA | Related to general Query or UI changes.
Pass | Pass
Fail | Fail
Pending | Not fixed and deployed from STE
Pending LD Load | Pending Long Description from STE
Pending Verification with SBST | Fixed and deployed by STE but was not verified with SBST at the day of validation due to time constraint
Testing Date: | 2024-11-27 | Affected Test Case | (All)
Column Labels
|  |  | Fail | NA | Pass | Pending Verification With SBST | Grand Total
|  | Count of SBST Validation | 8 | 7 | 24 | 28 | 67

## Test Summary
NEL1902 FAT Test Status
DM-Transaction
|  | Test Status |  |  |  | Defects |  |  |  | Updated Date: 18/09/2024
Test ID | Test Description | Pass | Fail Minor | Fail Major | Fail Critical | Test Specifications Version | Date of Test | PR ID | PR Status | Remarks
FAT_TRANSACTDM_0001.0001 | Validate Migrated Contracts (Price) Data into Maximo |  | ✔ |  |  |  | 2024-10-08
FAT_TRANSACTDM_0002.0001 | Validate Migrated Blanket Contracts Data into Maximo |  | ✔ |  |  |  | 2024-10-08
FAT_TRANSACTDM_0003.0001 | Validate Migrated Purchase Requisition(PR) Data into Maximo |  | ✔ |  |  |  | 2024-10-08
FAT_TRANSACTDM_0004.0001 | Validate Migrated Request For Quotation(RFQ) Data into Maximo |  | ✔ |  |  |  | 2024-10-08
FAT_TRANSACTDM_0005.0001 | Validate Migrated RFQ Vendor Data into Maximo |  | ✔ |  |  |  | 2024-10-08
FAT_TRANSACTDM_0006.0001 | Validate Migrated Purchase Orders(PO) Data into Maximo |  | ✔ |  |  |  | 09-Oct-24
FAT_TRANSACTDM_0007.0001 | Validate Migrated Invoices Data into Maximo |  | ✔ |  |  |  | 27-Sep-24 09-Oct-24 |  |  | 1.STE to check the purpose of G/L Posting Date in invoice Table. STE to check the value for totaltax1. Value is rounded to 0 decimal places. For Eg, Coswin 16.90, Maximo 17.00. The Coswin Remarks for Invoice is currently migrated to Terms and Condition Long Description. As the information within this field is entered by the end users, STE proposed for the remarks to be added onto the Invoice Application. 1) INV_DT and INV_RCT_DT is not mapped correctly. INV_DT should be mapped to INVOICE.CHANGEDATE and INV_RCT_DT should be mapped to INVOICE.INVOICEDATE. 2) Coswin Invoice SAP GL Code should be displayed on Maximo Invoice Main Tab. Currently it is mapped to INVOICECOST. STE_CSWNSAPGL.
FAT_TRANSACTDM_0008.0001 | Validate Migrated Receipts Data into Maximo |  | ✔ |  |  |  | 2024-10-10
FAT_TRANSACTDM_0009.0001 | Validate Migrated Work Order Data into Maximo | [5 empty] | 02-Oct-24 10-Oct-24 |  |  | 1. Coswin stores the Track Access Number in WIP_WO. WO_EQ_PHON. Currently in Maximo, it is mapped to a customized field in the Work Order table, STE_EQPPHONE. To amend the field label on screen to TAR No. The Maximo Labor in the Actuals Tab is still displaying the LAN ID or Barcode of the Employee. This is incorrect. It should display the Employee Number of the Employee. 2. SBST highlighted that the Maximo Work Order for migrated Work Orders should be having a “WO” prefix with running numbers. STE to check and verify if the migrated work orders is to be created in the above format.
FAT_TRANSACTDM_0010.0001 | Validate Migrated Service Requests Data into Maximo
FAT_TRANSACTDM_0011.0001 | Validate Inventory Data into Maximo |  | ✔ |  |  |  | 2024-09-25 |  |  | Min Qty, Max Qty, Reorder Point, Safety Stock showing 0 on screen. It is having values in Coswin. Population field is present in Coswin but is not mapped to Maximo. Currently Coswin Stockout Risk %, Cyclic Re-order and No. of days in Cycle is not mapped to any Maximo fields. To clarify if this field should be populated to a new field within Inventory. These fields are currently not available for verification. Coswin ORG_SUPL_CD is currently mapped to Inventory Manufacturer. The mapping is incorrect as the Suppliers are Vendors. SBST proposed that the original Supplier Code to be mapped to a new separate field instead of Manufacturer.
FAT_TRANSACTDM_0012.0001 | Validate Inventory Vendor Data into Maximo |  | ✔ |  |  |  | 2024-09-25 |  |  | 1) Coswin GST not mapped correctly to Maximo Inventory Vendor Tax Code. It should display GST in Inventory Vendor for all Items that are associated with GST. 2) The Coswin Max Lead Time is mapped to Inventory Delivery Time. SBST feedback that the Max Lead Time should also be within the same Section as the Min, Average Lead Time in the Inventory Vendor Section. 3) Coswin First Procured Date is mapped to the Inventory Vendor Last Order Date. However, the Last Order Date is not showing the correct information. SBST proposed to store the First Procured Date. 4) Remarks Column is advised by SBST to be stored in the STK_ITEM. STE to check if the Remarks field can be retrieved and stored in Maximo Item Application. 5) 1899-12-31 is visible for Last PO Date. To amend the mapping of the date value if it is NULL or 0. 6) Last Price is showing 0 for all records. User feedback that it should not show 0, but instead, the Unit Price of the Item should be displayed. 7) STE_CSWNLASTPO is not displayed correctly. TO check mapping of the field.
FAT_TRANSACTDM_0013.0001 | Validate Inventory Balances Data into Maximo | [5 empty] | 2024-09-25 |  |  | SBST feedback that Coswin Bins are created from a Bin Selector. Maximo Bins are mapped over to Inventory Balances Table BINNUM field. There is no application to create Bin in Maximo. It is currently stored as a ALN field.
FAT_TRANSACTDM_0014.0001 | Validate Material Requisitions Data into Maximo
FAT_TRANSACTDM_0015.0001 | Validate Preventive Maintenance Data into Maximo | [5 empty] | 30-Sep-24 10-Oct-24
FAT_TRANSACTDM_0016.0001 | Validate Migrated Job Plans Data into Maximo |  | ✔ |  |  |  | 2024-09-30 |  |  | SBST highlighted that the Maximo Jobplans are created incorrectly. The Jobplans should be created as per the Job Directory. Currently there are multiple instances of the same Job ID but having different Equipment Code.
FAT_TRANSACTDM_0017.0001 | Validate Fields Not Displayed on Maximo UI Migrated to Maximo Database
Test Statistic
Total Test Cases(✔) |  | 17
Total Test Cases Passes |  | 0
Total Test Cases Fail Minor |  | 11
Total Test Cases Fail Major |  | 0
Total Test Cases Fail Critical |  | 0
Total Test Cases Not tested |  | 6
Total % Test Cases Passed |  | 0
Total % Test Cases Failed |  | 64.7059
Total % Test Cases Not Tested |  | 35.2941
17 | 3
21 | 10
38 | 13
34.21%

## PR Summary
PR No | Title | Status | Type | Nature | Occurrence | Severity | Affected Test Case | Problem Description | SBST Validation | SBST Validation Remarks | Reported By | Reported Date | Problem Analysis | Problem Analysis (Notes) | Pkg | Fix Status | Data Loading | Analysed By | Analysed Date | Validation Comment | Validated By | Validated Date | Close Comment | Closed By | Closed Date
[7 empty] | FAT_TRANSACTDM_0001.0001 | Coswin's Purchase order details "Date" and "Del Due Date" needs to be captured in a separate custom field. | Pending Verification With SBST | Could not be tested because of 4460 sql error in contract application. | Peng Keong |  | Create two new custom fields. CONTRACT.STE_CSWNDATE and CONTRACT.STE_CSWNDELDUEDATE. | Create two new custom fields. PO.STE_CSWNDATE and PO.STE_CSWNDEDUEDATE. | 0302 | Done | Done | [8 empty] | In CONTRACT (PRICE), there is no Purchase Order reference. No mapping. In CONTRACT (BLANKET), it is mapped. New mapping: coswin PO Date => PORDER_.PO_DT coswin PO Del Due Date => PO_ITEMS.PO_ITEM_DEL_DT Need to create custom column
[7 empty] | FAT_TRANSACTDM_0001.0001 | SAP GL Code 435666 for blanket contract OS0156/000 doesn’t seems to be mapped to any field in Maximo. Need to check the mapping. | Pending Verification With SBST | Could not be tested because of 4460 sql error in contract application. | Peng Keong |  | Create a new custom field in maximo. CONTRACT.STE_CSWNSAPGL | Create a new custom field in maximo. |  | Done | Done | [8 empty] | New mapping: PORDER_.PO_STRING1 >> CONTRACT.STE_CSWNSAPGL
[7 empty] | FAT_TRANSACTDM_0001.0001 | Unit Cost in contract lines is rounded up. For example: unit cost 13.80 is displayed as 14. | Pending Verification With SBST | Could not be tested because of 4460 sql error in contract application. | Peng Keong |  | Remove the rounding up of cost values. | Remove the rounding up of cost values. |  | No Action | Done | [8 empty] | Backend data is not rounded up. Mapping has no transformation: SUPL_AGREE_ITEM.SUPL_ITEMS.S_LAT_UNIT_RATE >> CONTRACTLINE.UNITCOST
[7 empty] | FAT_TRANSACTDM_0001.0001 | Maximum Amount is blank for contract OS0156/000. | Pending Verification With SBST | Could not be tested because of 4460 sql error in contract application. | Peng Keong |  | Need to check with Gareth if it was removed as part of cost exercise. | NO | 309 | Done | Done |  |  | Need to check the script | [5 empty] | Applicable to CONTRACT (BLANKET) PORDER_.PO_VALUE >> CONTRACTPURCH.MAXVOL
[7 empty] | FAT_TRANSACTDM_0001.0001 | Amount received and amount remaining in costinput table needs to be verified. | Pending Verification With SBST | Could not be tested because of 4460 sql error in contract application. | Peng Keong |  | Need to check with Gareth if it was removed as part of cost exercise. | NO |  | Done | Done |  |  | Need to check the script | [5 empty] | Applicable to CONTRACT (BLANKET) PORDER_.PO_DELVD_VALUE -> CONTRACT.STE_COMMITTEDCOST PORDER_.PO_PENDG_VALUE -> CONTRACT.STE_AMOUNTREMAINING
[7 empty] | FAT_TRANSACTDM_0002.0001 | For the blanket contract buyer is not mapped. PURCHVIEW.PURCHASEAGENT, but the subsequent release POs have buyers. | Pending Verification With SBST | Could not be tested because of 4460 sql error in contract application. | Peng Keong |  | Coswin Blanket PO Buyer to be mapped with PURCHVIEW.PURCHASEAGENT | Coswin Blanket PO Buyer to be mapped with PURCHVIEW.PURCHASEAGENT | 0302 | Done | Done | [8 empty] | New mapping: PORDER_.PO_REQ_BY >> CONTRACT.PURCHASEAGENT
[7 empty] | FAT_TRANSACTDM_0002.0001 | Changeby is maxadmin in for blanket contract. It should be same as amend by in coswim contracts. | Pending Verification With SBST | Could not be tested because of 4460 sql error in contract application. | Peng Keong |  | Correct value from Coswin's "Amend By" to be populated instead of MAXADMIN. | Correct value from Coswin's "Amend By" to be populated instead of MAXADMIN. | 0302 | Done | Done | [8 empty] | New mapping: PORDER_.PO_AMD_WHO >> CONTRACT.CHANGEBY Default value is still set to MAXADMIN New custom column
[7 empty] | FAT_TRANSACTDM_0002.0001 | Payment terms is not mapped for blanket contract OS0156/000. | Pending Verification With SBST | Could not be tested because of 4460 sql error in contract application. | Peng Keong |  | Payment term mapping to be done. | Payment term mapping to be done. | 0302 | Done | Done | [8 empty] | Currently not mapped yet. To confirm mapping: PORDER_.PO_PAY_DET >> CONTRACT.PAYMENTTERM
[7 empty] | FAT_TRANSACTDM_0007.0001 | The count of invoices(credit note + Invoice) is 67 records less in maximo after comparing with coswin's invoices + credit notes. | Pass |  | Peng Keong |  | Need to analyze. | Need to analyze. |  | Not Checked Yet | NA | [8 empty] | Need to check migrated data. Pkg still has error!
[7 empty] | FAT_TRANSACTDM_0002.0001 | Make all the WAPPR blanket contracts status as APPR. | Pending Verification With SBST | Could not be tested because of 4460 sql error in contract application. | Peng Keong |  | Mapping change for blanket contracts: 48 (COSWIN screen = 0) - APPR 54 (COSWIN screen = 6) - WAPPR | Mapping change for blanket contracts: 48 (COSWIN screen = 0) - APPR 54 (COSWIN screen = 6) - WAPPR | 0302 | Done | Done | [8 empty] | Update transformation
[7 empty] | FAT_TRANSACTDM_0002.0001 | PO Not authorized (54) (6 on coswin screen) is similar to WAPPR in contract and hence needs to be changed as needed. 0 is approved. | Pending Verification With SBST | Could not be tested because of 4460 sql error in contract application. | Peng Keong |  | Mapping Change for PO: 48 - just created - APPR 54 - not authorized - WAPPR | Mapping Change for PO: 48 - just created - APPR 54 - not authorized - WAPPR | 0302 | Done | Done | [8 empty] | Update transformation
[7 empty] | FAT_TRANSACTDM_0002.0001 | Default the properties as standard values based on when contract type is selected as “BLANKET”,”PRICE” using scripts. For example: If Type is BLANKET: 1. Requires PO? - Y 2. Create Release? – Y 3. Can Exceed amount – Y 4. Add Lines on use? – Y 5. Acceptance Loss? – Y 6. Vendor termination Allowed – Y 7. Customer Termination Allowed? – Y. For Type = 'PRICE': 1. Requires PO? - Y 2. Create Release? – N 3. Can Exceed amount – N 4. Add Lines on use? – N 5. Acceptance Loss? – Y 6. Vendor termination Allowed – Y 7. Customer Termination Allowed? – Y. | Pending Verification With SBST | Could not be tested because of 4460 sql error in contract application. | Peng Keong |  | Population of default values based on system defaults for Contract Type as "BLANKET", "PRICE". | Population of default values based on system defaults for Contract Type as "BLANKET", "PRICE". | 0301 - Contract (PRICE) 0302 - Contract (BLANKET) 0309 - ContractPurch | Done | Done | [8 empty] | The following need to be updated In Contract Level: 6. Vendor termination Allowed – Y 7. Customer Termination Allowed? – Y. The rest is in 0309-ContractPurch. No change for ContractPurch for Contract (PRICE)
[7 empty] | FAT_TRANSACTDM_0003.0001 | For Cost centers part of the GL account (cost center) list should use the Department mapping as provided by SBST for GL account string in PRLINE. | Fail | 26/11/2024: No PR data is found. ........................................................... For PR: RSW0008550, Coswin Cost Center: 2712220, SAP GL Code: 432150 is present. But the GLDebit Account field is blank.It should have the value as : NEL-2712220-432150. Similarly for PRs PL06/0223,RSW0008550,PL06/0215 As there is no corresponding mapping of cost center in mapping sheet. NOTE: The GL Debit Account for the ones that have a mapping in excel is populated correctly. | Peng Keong |  | Value migrated in separate columns as cost center needs to be re-mapped to GL account field as a concatenation of Department-cost center - SAP GL Code(optional, only if available). The department should be defaulted as NEL for the cost centers that are not part of the list provided by SBST. Rest should be mapped as per the department-cost center mapping provided by SBST. | Value migrated in separate columns as cost center needs to be re-mapped to GL account field as a concatenation of Department-cost center - SAP GL Code(optional, only if available). The department should be defaulted as NEL for the cost centers that are not part of the list provided by SBST. Rest should be mapped as per the department-cost center mapping provided by SBST. |  | Done | Done |  |  | Where is this GL mapping? | [5 empty] | New mapping
[7 empty] | FAT_TRANSACTDM_0003.0001 | For Cost centers that are not part of the list provided by SBST, Department should be defaulted to NEL. | Fail | 26/11/2024: No PR data is found. .......................................................... Similar to above. | Peng Keong |  | Value migrated in separate columns as cost center needs to be re-mapped to GL account field as a concatenation of Department-cost center - SAP GL Code(optional, only if available). The department should be defaulted as NEL for the cost centers that are not part of the list provided by SBST. Rest should be mapped as per the department-cost center mapping provided by SBST. | Value migrated in separate columns as cost center needs to be re-mapped to GL account field as a concatenation of Department-cost center - SAP GL Code(optional, only if available). The department should be defaulted as NEL for the cost centers that are not part of the list provided by SBST. Rest should be mapped as per the department-cost center mapping provided by SBST. |  | Done | Done |  |  | Where is this GL mapping? | [5 empty] | New calculated field
[7 empty] | FAT_TRANSACTDM_0002.0001 | Blanket contract remarks are not captured anywhere. | Pass |  | Peng Keong |  | A new field to be created. CONTRACT.STE_REMARKS | A new field to be created. |  | Done | Done | [8 empty] | To confirm mapping PORDER_.PO_RMK.PO_TXT >> CONTRACT.STE_REMARKS Create new pkg: 0603B_CONTRACT_BLANKET. Pkg 0607-LD PO add filter: WHERE po.PO_TYPE != 49
[7 empty] | FAT_TRANSACTDM_0004.0001 | Coswin RFQ has no description. The RFQ description migrated in Maximo seems to be migrated from coswin’s By Fax/Box/Mail field which is incorrect. As per mapping sheet, it is mapped to RFQVENDOR. STE_CSWNNOTES field. | Pass |  | Peng Keong |  | RFQ Description to be removed. | RFQ Description to be removed. |  | Done | Done | [8 empty] | Remove mapping: RFQ.Description
[7 empty] | FAT_TRANSACTDM_0004.0001 | Coswin RFQ’s PR number needs to be mapped to RFQ.STE_PRNUM. | Pass | Migration is done successfully. Note: Peng Keong mentioned that he requested to have a PR linkage field from RFQ. The field doesn't seems to be avaiable on UI in Data Validation platform. | Peng Keong |  | Create a new custom field to migrate PRNUM. | Create a new custom field to migrate PRNUM. |  | Done | Done | [8 empty] | New mapping: DEVIS.DV_PREQ_REF >> RFQ.STE_PRNUM Need to create custom column
[7 empty] | FAT_TRANSACTDM_0004.0001 | SAP GL CODE from cownin quotation details is migrated to RFQVENDOR.Need to re-map as part of GL Debit account. | Pass | 27/11/2024: As observed by Peng Keong, the description of the SAP GL Code component's description is incomplete and cut short possibly due to field length restriction. SAP GL Code is loaded successfully. Note: There is an extra 435800 SAP GL Code in coswin. ........................................................... 26/11/2024: Migrated data is verified successfully. However, the item is failed as the SAP GL Code list is not populated in GL Components. This is already fixed by STE in Db V1.05 and will be available as part of that.To be verified with db V1.05. ………………………............................. For RFQ: AB04380222000 The GL Debit account is not mapped even though the mapping is present in the GL mapping sheet. Similarly for AB04380222002. | Peng Keong |  | Value migrated in separate columns as cost center needs to be re-mapped to GL account field as a concatenation of Department-cost center - SAP GL Code(optional, only if available). The department should be defaulted as NEL for the cost centers that are not part of the list provided by SBST. Rest should be mapped as per the department-cost center mapping provided by SBST. | Value migrated in separate columns as cost center needs to be re-mapped to GL account field as a concatenation of Department-cost center - SAP GL Code(optional, only if available). The department should be defaulted as NEL for the cost centers that are not part of the list provided by SBST. Rest should be mapped as per the department-cost center mapping provided by SBST. | 0304 | Done | Done |  |  | Where is this GL mapping? | [5 empty] | Create new custom columns: STE_CSWNSAPGL STE_CSWNCC
[7 empty] | FAT_TRANSACTDM_0004.0001 | Quotationline is not populated for RFQ CJ01951512003. | Pass |  | Peng Keong |  | Need to verify in case of any script issues. | Need to verify in case of any script issues. |  | No action | Done |  |  | Need to see the data | [5 empty] | Backend data for RFQ CJ01951512003 has 4 quotation line
[7 empty] | FAT_TRANSACTDM_0003.0001 | Coswin PR remarks should be populated as PR work log in maximo. | Pass |  | Peng Keong |  | Re-mapping of coswin PR remarks from PR Terms and Conditions to PR work log. | Re-mapping of coswin PR remarks from PR Terms and Conditions to PR work log. |  | Done | Not Done | [8 empty] | WORKLOG. Update pkg 0604 LD PR
[7 empty] | FAT_TRANSACTDM_0004.0001 | Maximo computes the value of the quotation at item level but not at vendor level. Rule Related - Document to be updated. | NA |  | Peng Keong |  | Just a remark. No action required. | Just a remark. No action required. |  | No action | Done
[7 empty] | FAT_TRANSACTDM_0004.0001 | RFQ count in maximo is 162306 and coswin is 162129. Total count of quotations mismatch. | Pass |  | Peng Keong |  | To analyse the reason for count mismatch. This can be verified with the latest copy of coswin db. | To analyse the reason for count mismatch. This can be verified with the latest copy of coswin db. |  | No action | Done | [8 empty] | Backend data has consistent count
[7 empty] | FAT_TRANSACTDM_0006.0001 | PR number in coswin is not migrated to PO : Sample PO AA10007683. | Fail | 26/11/2024: PO.STE_PRNUM field is not availble in V1.04 db and hence the item is failed. ……………………………………………... PO.STE_PRNUM is blank for all the Pos.STE to re-check. | Peng Keong |  | PR number in coswin to be mapped to PO.STE_PRNUM | PR number in coswin to be mapped to POLINE.PONUM and POLINE.POLINENUM |  | Done | Done | [8 empty] | New mapping: PORDER_.PO_PREQ_REF >> PO.STE_PRNUM Need to create custom column
[7 empty] | FAT_TRANSACTDM_0006.0001 | PO AA10007683 has 1 line item in coswin but not in maximo. | Pass |  | Peng Keong |  | To analyse the reason and if there is any issue with the scripts. | To analyse the reason and if there is any issue with the scripts. |  | No action | Done |  |  | Need to see the data | [5 empty] | Backend data for PO AA10007683 has 1 PO line item!
[7 empty] | FAT_TRANSACTDM_0006.0001 | For Cost centers part of the GL account (cost center) list should use the Department mapping as provided by SBST for GL account string in POLINE. | Pass | 27/11/2024: As observed by Peng Keong, the description of the SAP GL Code component's description is incomplete and cut short possibly due to field length restriction. SAP GL Code is loaded successfully. Note: There is an extra 435800 SAP GL Code in coswin. ........................................................... 26/11/2024: Migrated data is verified successfully. However, the item is failed as the SAP GL Code list is not populated in GL Components. This is already fixed by STE in Db V1.05 and will be available as part of that.To be verified with db V1.05. ………………………............................ New Problem created. The GL Debit accounts are not mapped to POLINE.GLDEBITACCT. This should follow the same approach as PRLINE or RFQLINE. | Peng Keong
[7 empty] | FAT_TRANSACTDM_0006.0001 | Delivery due date under the section "Purchase/Purchase Order/Purchase Order Details/Details" should be migrated to POLINE.REQDELIVERYDATE. The other Deliver due date at top level should be migrated to header level PO. Required date. | Pass |  | Peng Keong |  | Re-mapping of fields. | Re-mapping of fields. |  | Done | Done | [8 empty] | Current mapping: PO_ITEMS.PO_ITEM_DEL_DT -> POLINE.REQDELIVERYDATE New mapping: In POLine: PORDER_.DR_TEXT2 >> POLINE.REQDELIVERYDATE (TRANFORMED) PORDER_.DR_TEXT2 >> POLINE.STE_CSWNREQDELIVERYDATE (AS-IS) In top PO Level: PO_ITEMS.PO_ITEM_DEL_DT -> PO.REQUIREDDATE
[7 empty] | FAT_TRANSACTDM_0006.0001 | PO AA10013181 have a contract reference (WAGT21-110)in maximo but no reference in coswin. | Pass |  | Peng Keong |  | To analyse the mismatch in data. | To analyse the mismatch in data. |  | Done | Done | [8 empty] | Remove mapping: PORDER_.SUPPLIER_.SUPPL_AGREE.SAGREE_CODE >> PO.CONTRACTREFNUM Keep mapping: PORDER_.PO_BLKT_REF >> PO.CONTRACTREFNUM (PO_BLKT_REF -> PO.PO_TYPE=49)
[7 empty] | FAT_TRANSACTDM_0006.0001 | For coswin number of amendments 1, it seems to be 0 in maximo. Should it be 1 instead? STE to verify. | Fail | 27/11/2024: Still failed as per V1.05. ........................................................... 26/11/2024: To be verified as part of V1.05. ………………………………................... Coswin PO Number: OS0123/000 has No. Of amendments = 4 in coswin, this is migrated to Maximo as a blanket contract with revisionnum = 0. The contract revision number needs to be re-verified. | Peng Keong |  | To analyse the current mapping and why the revision is 0 instead of 1. | To analyse the current mapping and why the revision is 0 instead of 1. |  | No Action | Done |  |  | Need to see the data | [5 empty] | Current mapping: PORDER_.PO_AMD_NO >> PO.REVISIONNUM For PO OS0124/032 (PO_AMD_NO=1), backend migrated data is correct (REVISIONNUM=1)
[7 empty] | FAT_TRANSACTDM_0004.0001 | Move RFQ terms and conditions to RFQ.STE_Remarks column in RFQ main tab. | Pass | 26/11/2024: Data is migrated and verified successfully. | Peng Keong |  | Create a new custom field RFQ.STE_REMARKS and move Coswin RFQ remarks. | Create a new custom field RFQ.STE_REMARKS and move Coswin RFQ remarks. |  | Done | Not Done | [8 empty] | DV_RMK.DEV_TEXT >> RFQ.STE_REMARK Update in pkg 0608 LD_RFQ_RFQLine
[7 empty] | FAT_TRANSACTDM_0006.0001 | Total cost value in PO is blank.STE to verify whether it was nullified as part of removing cost value exercise. | Fail | 27/11/2024: This is a known issue. STE is still looking into it. ........................................................... 26/11/2024: This is a known issue. STE is looking into it. ......................................................... Data is migrated.However, there are few records which are off by 1 cent.There could be more such records. Need to re-check the rounding off or the logic in SSIS. STE to verify. Maximo: PO: 02905, TC: 55,612.69 Coswin: PO: 02905, TC: 55,612.70 Maximo: PO:BB60001536 , TC: 37.25 Coswin: PO:BB60001536 , TC: 37.26 | Peng Keong |  | Need to check with Gareth if it was removed as part of cost exercise. | NO |  | No action | Done | [8 empty] | Current mapping: PORDER_.PO_VALUE >> PO.TOTALCOST Backend data show correct result.
[7 empty] | FAT_TRANSACTDM_0004.0001 | RFQ.STE_REMARKS longdescription needs to be displayed on screen under Details section > Type Field. | NA | 26/11/2024: The changes are related to UI.
[7 empty] | FAT_TRANSACTDM_0006.0001 | Coswin PO remarks which are migrated to maximo's term n condition to be changed and migrated as part PO worklog. | Pass |  | Peng Keong |  | Re-mapping. | Re-mapping. |  | Done | Not Done | [8 empty] | PORDER_.PO_RMK >> WORKLOG Update pkg 0607_LD_PO
[7 empty] | FAT_TRANSACTDM_0007.0001 | INV_DT and INV_RCT_DT is not mapped correctly. INV_DT should be mapped to INVOICE.CHANGEDATE and INV_RCT_DT should be mapped to INVOICE.INVOICEDATE. | Fail | 27/11/2024: This change was raised on 26/11/2024 and hence it is not fixed as part of V1.05. ........................................................... 26/11/2024: 1. INVOICE.INV_DT >> INVOICE.INVOICEDATE Note: Currently INVOICE.INV_DT is mapped to INVOICE.CHANGEDDATE which is incorrect. New Requirement: To display the MATRECTRANS.ACTUALDATE in view related records INV_RCT_DT >> This is equivalent of MATRECTRANS.ACTUALDATE ............................................................ Dates Logic: Coswin Posting Date is Invoice record creation date in the system. The posting Date shall be mapped to the below two fields. 1. INVOICE_.DT_INVOICE(Posting Date) >> INVOICE.ENTERDATE. 2. INVOICE_.DT_INVOICE(Posting Date) >> INVOICE.INVOICE.GLPOSTDATE. System No. Date is the supplier date INV_RCT_DT >> INVOICE.INVOICEDATE Received Date is the DO/Receiver date. Invoice: 706971, Invoice date in coswin is 2016-06-17, but maximo is displaying 2016-06-16. This is regarding: "INV_RCT_DT should be mapped to INVOICE.INVOICEDATE". Note: Change Date is mapped correctly to IN_DT. | Peng Keong |  | Re-mapping. | Re-mapping. |  | Done | Done | [8 empty] | Change the mapping for INVOICEDATE: INVOICE_.INV_RCT_DT >> INVOICE.INVOICEDATE Mapping for CHANGEDATE is already correct: INVOICE_.INV_DT >> INVOICE.CHANGEDATE
[7 empty] | FAT_TRANSACTDM_0007.0001 | Coswin Invoice SAP GL Code should be displayed on Maximo Invoice Main Tab. Currently it is mapped to INVOICECOST. STE_CSWNSAPGL. | NA | This is to be displayed on Invoice application main tab. | Peng Keong |  | Re-mapping. INVOICECOST.STE_CSWNSAPGL INVOICE.STE_CSWNSAPGL | Re-mapping. |  | Done | Done | [8 empty] | New mapping: INVOICE_.INV_STRING1 >> INVOICE.STE_CSWNSAPGL New custom column: INVOICE.STE_CSWNSAPGL
[7 empty] | FAT_TRANSACTDM_0007.0001 | For Credit note status mapping: 48 - Created - APPR 49 - Validated - APPR 50 - Partially used - APPR 51 - Used - PAID 52 - Cancelled - CANCEL 53 - Closed - PAID | Pass | NI-SBSNEL1503 credit note status is cancelled in coswin but appr in maximo. It should be cancelled. The mapping provided in the description to be followed for all credit notes. Additional Comments: Credit code numbers are not found or created as invoice numbers. STE to verify . For example: Invoice number SBSNEL1601 has an associated credit note number : LD/NEL1601. Example: LD/NEL1601 needs to be created as a invoice number with a "Credit" invoice type with original Invoice number as SBSNEL1601. Currently, Credit notes are created as NI-<Invoicenume>. | Peng Keong |  | Re-mapping. | Re-mapping. |  | Done | Done | [8 empty] | Change transformation for INVOICE.STATUS. To confirm: This is also for NEG_INV? YES.
[7 empty] | FAT_TRANSACTDM_0007.0001 | STE to check from where uninvoiced total is coming in invoice application in maximo.For example : NI-C753M017 | NA | Uninvoiced total seems to be appearing even after the PO is totally invoiced. | Peng Keong |  | Need to analyze. | Need to analyze. |  | No Action | Done | [8 empty] | Calculated columns. Nothing to do
[7 empty] | FAT_TRANSACTDM_0007.0001 | Remaining value for credit notes in coswin needs to be migrated to Invoice.STE_CSWNREMVALUE. | NA |  | Peng Keong |  | Re-map. | Re-map. |  | No Action | Done | [8 empty] | Calculated columns. Nothing to do
[7 empty] | FAT_TRANSACTDM_0007.0001 | GLDebit account needs to be populated for Invoice line, PO line and PR line as per the agreed logic with SBST. | Fail | 27/11/2024: Data verification has failed for PO Line's GL Debit account, It was passed in V1.04 db version on 26/11/2024, but failed in V1.05. Example PO: BB60023280 Invoice: 48731 PR :OPS0000503 ........................................................... As observed by Peng Keong, the description of the SAP GL Code component's description is incomplete and cut short possibly due to field length restriction. SAP GL Code is loaded successfully. Note: There is an extra 435800 SAP GL Code in coswin. ........................................................... 26/11/2024: Migrated data is verified successfully. However, the item is failed as the SAP GL Code list is not populated in GL Components. This is already fixed by STE in Db V1.05 and will be available as part of that.To be verified with db V1.05. ………………………............................. The GL Debit accounts are not mapped to POLINE.GLDEBITACCT for the some Invoices which are not part of the GL mapping sheet provided by SBST. This should follow the same approach as PRLINE or RFQLINE.If the department mapping is provided.It should be defaulted as NEL. | Peng Keong |  | Re-map. | Re-map. |  | Done | Done | [8 empty] | Dept-CC-SAPGL in INVOICECOST
[7 empty] | FAT_TRANSACTDM_0008.0001 | 1. POREVISIONUM is missing from matrectrans records which is preventing material receipt to be displayed on screen. | Pass |  | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. |  | Done | Done | [8 empty] | Add new mapping: RCT_ITEMS.PORDERS_.PO_AMD_NO >> MATRECTRANS.POREVISIONNUM
[7 empty] | FAT_TRANSACTDM_0008.0001 | The "quantity received" field in "Material Receipts" Table column is displaying all the quantiies ordered for a particular POLINE. STE to check whether it should display only the received quantity for that particular line item. | NA | 26/11/2024: Captured as part of Process flow.
[7 empty] | FAT_TRANSACTDM_0008.0001 | 2. GRN Ref num and GRN date to be displayed on screen? TBD by SBST. | NA | SBST confirmed to be included under Material Reciept/Service Receipt sub section. Under GRN Ref Type field. | Peng Keong |  | To be decided by SBST. | To be decided by SBST. |  | No Action | Done
[7 empty] | FAT_TRANSACTDM_0008.0001 | 3. PO Lines items in maximo is not migrated for PONUM: AA10009897. STE to verify the issue and rectify if it is happening for other POs as well. | Pass |  | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. |  | No Action | Done |  |  | Need to see the data | [5 empty] | Need to check the migrated data. Similar to row 25. Executing the query manually produce 144 po line items
[7 empty] | FAT_TRANSACTDM_0008.0001 | 4. Quantity is showing as -ve for transaction type of Return in material receipts. | Pass | PONUM: 02336, Coswin has Quantity Received as 107.60 and maximo is showing 107.59 (MATRECTRANS.RECEIPTQUANTITY).STE to Verify. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. |  | Done | Done | [8 empty] | Remove transformation for MATRECTRANS.QUANTITY
[7 empty] | FAT_TRANSACTDM_0008.0001 | 5. The migration of DO remarks to MATRECTRANS.STE_CSWNRECEIPTREMARK is missing in maximo.The field is not created in database. | Pass |  | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. |  | Done | Not Done | [8 empty] | New mapping: RCT_ITEMS.RCT_RMK.RCT_TXT >> MATRECTRANS.STE_CSWNRECEIPTREMARK Need to create new custom column (LD) Need to create new LD package
[7 empty] | FAT_TRANSACTDM_0008.0001 | 7. Service receipts needs to be created for service items.For example : PONUM: BB60015612, DO number: 00000015. | Pass | 27/11/2024: Service Receipts are populated. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. |  | Done | Partial |  |  | Need to see the data | [5 empty] | How to create service receipts? SERVRECTRANS Notes: The transformation to get service items is quite messy! Should probably just do a lookup to migrated item table
[7 empty] | FAT_TRANSACTDM_0008.0001 | 8. STE to check the treatment for non-PO receipts. For example: miscellaneous type DOs in coswin. | Pass |  | Peng Keong |  | Create a dummy PO (CSWN_NONPO) and tag against it all the miscellaneous receipts. | Create a dummy PO (CSWN_NONPO) and tag against it all the miscellaneous receipts. |  | Done | Done | [8 empty] | Add default value to MATRECTRANS.PONUM mapping: coalesce(RCT_PO_REF, 'CSWN_NONPO') Create a new master pkg to create the dummy PO
[7 empty] | FAT_TRANSACTDM_0011.0001 | Min Qty, Max Qty, Reorder Point, Safety Stock showing 0 on screen. It is having values in Coswin. | Pass |  | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. |  | Done | Done | [8 empty] | Map ITEM_INFO via ITEM_ instead of directly from STOREITEM. Please verify the following fields as well (similar to MinQty, originally from ITEM_ but now from STOREITEM): MAXLEVEL MINLEVEL SSTOCK DELIVERYTIME ISSUE1YRAGO ISSUE2YRAGO CURBALTOTAL AVBLBALANCE RESERVEDQTY ORDERQTY
[7 empty] | FAT_TRANSACTDM_0011.0001 | ITEM_INFO.REORD_LEVEL to be re-mapped to INVENTORY.MINLEVEL (Reorder Point) from INVENTORY.SSTOCK. | Pass | 27/11/2024: Note: Safety stock is obsereved to be blank and Coswin minimum and max qty For an item is migrated to their custom columns respectively in maximo. | Peng Keong
[7 empty] | FAT_TRANSACTDM_0011.0001 | Population field is present in Coswin but is not mapped to Maximo. | Pending Verification With SBST |  | Peng Keong |  | Need to create a new field STE_CSWNPOPULATION. | Need to create a new field STE_CSWNPOPULATION. |  | Done | Done | [8 empty] | New mapping: ITEM_.ITEM_NUMBER1 >> INVENTORY.STE_CSWNPOPULATION Need to create custom mapping
[7 empty] | FAT_TRANSACTDM_0011.0001 | Currently Coswin Stockout Risk %, Cyclic Re-order and No. of days in Cycle is not mapped to any Maximo fields. To clarify if this field should be populated to a new field within Inventory. These fields are currently not available for verification. | Pending Verification With SBST |  | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. |  | Done | Done | [8 empty] | ITEM.STKOUT_RISKP -> STE_CSWNSTKRISK ITEM_INFO.I_CYCLIC_REORDER -> STE_CYCLICREORDER ITEM_INFO.I_CYCLE -> STE_NODAYSCYCL
[7 empty] | FAT_TRANSACTDM_0011.0001 | Coswin ORG_SUPL_CD is currently mapped to Inventory Manufacturer. The mapping is incorrect as the Suppliers are Vendors. SBST proposed that the original Supplier Code to be mapped to a new separate field instead of Manufacturer. | Pending Verification With SBST |  | Peng Keong |  | Map to new fields: STE_CSWNSUPPLIER | Need to re-visit scripts. |  | Done | Done | [8 empty] | Remove mapping on INVENTORY.MANUFACTURER Update mapping to custom column. STORES_ITEMS.ITEM_.ORG_SUPL_CD >> INVENTORY.STE_CSWNSUPPLIER Need to create custom column
[7 empty] | FAT_TRANSACTDM_0012.0001 | Coswin GST not mapped correctly to Maximo Inventory Vendor Tax Code. It should display GST in Inventory Vendor for all Items that are associated with GST. | Pending Verification With SBST |  | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. |  | Done | Done |  |  | What is the mapping? | [5 empty] | Map to default value: "GST" >> INVVENDOR.TAX1CODE
[7 empty] | FAT_TRANSACTDM_0012.0001 | The Coswin Max Lead Time is mapped to Inventory Delivery Time. SBST feedback that the Max Lead Time should also be within the same Section as the Min, Average Lead Time in the Inventory Vendor Section. | Pending Verification With SBST |  | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. |  | Done | Done |  |  | What is the mapping? Any example? | [5 empty] | Keep mapping in INVENTORY: STORES_ITEMS. ITEM_. ITEM_INFO.MAX_LEAD_TIME >> INVENTORY.DELIVERYTIME Mapping INVVENDOR: STORES_ITEMS. ITEM_. ITEM_INFO.MAX_LEAD_TIME >>INVVENDOR.PROMDELIVERYTIME
[7 empty] | FAT_TRANSACTDM_0012.0001 | Coswin First Procured Date is mapped to the Inventory Vendor Last Order Date. However, the Last Order Date is not showing the correct information. SBST proposed to store the First Procured Date. | Pending Verification With SBST |  | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. |  | Done | Done |  |  | What is the mapping? | [5 empty] | Currently INVVENDOR.LASTDATE is mapped to SUPL_ITEMS.S_L_DT_PO. New mapping: ITEM_.DT_FIRST_PROC >> INVENTORY.STE_FIRSTPROCDATE
[7 empty] | FAT_TRANSACTDM_0012.0001 | Remarks Column is advised by SBST to be stored in the STK_ITEM. STE to check if the Remarks field can be retrieved and stored in Maximo Item Application. | Pending Verification With SBST |  | Peng Keong |  | Map to new fields: STE_REMARKS | Need to re-visit scripts. |  | Done | Not Done |  |  | What is the mapping? | [5 empty] | New mapping: SUPL_RMK.SUPL_TXT >> INVVENDOR.STE_REMARKS Need to create new custom column (LD) Need to create new LD package
[7 empty] | FAT_TRANSACTDM_0012.0001 | 1899-12-31 is visible for Last PO Date. To amend the mapping of the date value if it is NULL or 0. | Pending Verification With SBST |  | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. |  | Done | Done | [8 empty] | Set to NULL if value = 1899-12-31. Set default value to NULL
[7 empty] | FAT_TRANSACTDM_0012.0001 | Last Price is showing 0 for all records. User feedback that it should not show 0, but instead, the Unit Price of the Item should be displayed. | Pending Verification With SBST |  | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. |  | Done | Done | [8 empty] | Update mapping: SUPL_ITEMS.S_LAT_UNIT_RATE >> INVVENDOR.LASTCOST If SUPL_ITEMS.S_LAT_UNIT_RATE=0 then: SUPL_ITEMS.ITEM_.BUY_PRICE >> INVVENDOR.LASTCOST
[7 empty] | FAT_TRANSACTDM_0012.0001 | STE_CSWNLASTPO is not displayed correctly. TO check mapping of the field. | Pending Verification With SBST |  | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. |  | Done | Done | [8 empty] | Missing mapping: SUPL_ITEMS.S_L_PO >> INVVENDOR.STE_CSWNLASTPO
[7 empty] | FAT_TRANSACTDM_0014.0001 | 1. Coswin Demand "From" date should be migrated to MR.REQUIREDDATE and "To" date should be migrated to "STE_CSWNDEMTODATE". | Pending Verification With SBST |  | Peng Keong |  | New custom column: STE_CSWNDEMTODATE | Need to re-visit scripts. |  | Done | Done | [8 empty] | New mapping. New custom column
[7 empty] | FAT_TRANSACTDM_0014.0001 | 2. Entered date needs to be displayed on screen. | Pending Verification With SBST |  | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. |  | No Action | Done | [8 empty] | Currently MR.ENTERDATE is mapped to DEM_ISS.DEM_DT
[7 empty] | FAT_TRANSACTDM_0014.0001 | 3. Demand remarks should be migrated to STE_DEMREMARKS. | Pending Verification With SBST |  | Peng Keong |  | New custom column: MR.STE_DEMREMARKS | Need to re-visit scripts. |  | Done | Not Done | [8 empty] | New mapping: DEM_ISS.ISS_RMK >> MR.STE_DEMREMARKS. New custom column
[7 empty] | FAT_TRANSACTDM_0014.0001 | 4. Material Requisions status mapping: 48 - 0 - No Issued - APPR 49 - 1 - Part Issued - APPR 50 - 2 - Issue Completed - CLOSE 51 - 3 - Cancelled - CAN 52 - 4 - Not Validated - WAPPR 57 - 9- Directly Issued - CLOSE | Pending Verification With SBST |  | Peng Keong | WHEN DEM_STATUS=48 THEN 'APPR' WHEN DEM_STATUS=49 THEN 'APPR' WHEN DEM_STATUS=50 THEN 'CLOSE' WHEN DEM_STATUS=51 THEN 'CAN' WHEN DEM_STATUS=52 THEN 'WAPPR' WHEN DEM_STATUS=57 THEN 'APPR' | Need to re-visit scripts. | Need to re-visit scripts. |  | Done | Done | [8 empty] | Update transformation
[7 empty] | FAT_TRANSACTDM_0014.0001 | 5. MATUSETRANS.STORELOC is "Transit" for all the items.It should be populated with the correct item location. For example: item TRAIN /GEN/AR/01. | Pending Verification With SBST |  | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. |  | Done | Done | [8 empty] | Get actual store loc: SELECT ii.PK_ISS_ITEMS, ii.ISS_REF, dli.PK_DEM_LOC_INT, l.PK_LOCATION_, si.IS_STOR_CD FROM coswin.ISS_ITEMS ii LEFT JOIN coswin.DEM_LOC_INT dli ON dli.S_ISS_LOC_INT = ii.PK_ISS_ITEMS LEFT JOIN coswin.LOCATION_ l ON l.PK_LOCATION_ = dli.S_LOC_DEM_INT LEFT JOIN coswin.STORES_ITEMS si ON si.PK_STORES_ITEMS = l.S_STORES_ITEM_LOC WHERE ii.S_ITEM_ISS=27322
[7 empty] | FAT_TRANSACTDM_0014.0001 | 6. Transfer transactions are not migrated to maximo. For example: Item number: TRAIN /GEN/AR/01. | Fail | 27/11/2024: Transfer transactions needs to be migrated. | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. |  | WIP | Not Done | [8 empty] | TR_ITEMS >> cswn_tr_items H_TRANSFER >> cswn_h_transfer H_TR_ITEMS >> NO DATA Create record: MATRECTRANS (IssueType= 'SHIPTRANSFER')
[7 empty] | FAT_TRANSACTDM_0014.0001 | 7. Issue number from coswin is not migrated in maximo. Issues number exammple: ISS12577. This needs to be migrated to matusetrans.STE_ISSUENUM. | Pending Verification With SBST |  | Peng Keong |  | New custom column: MATUSETRANS.STE_ISSUENUM | Need to re-visit scripts. |  | Done | Done | [8 empty] | New mapping: ISS_ITEMS.ISS_REF >> MATUSETRANS.STE_ISSUENUM New custom column
[7 empty] | FAT_TRANSACTDM_0014.0001 | 8. Need to populate coswin adjustments to invtrans in maximo.Coswin STK_ADJ table needs to be migrated to INVTRANS. | Pending Verification With SBST |  | Peng Keong |  | Need to re-visit scripts. | Need to re-visit scripts. | 206 | Done | Not Done | [8 empty] | Need to create new pkg! TransType='PCOUNTADJ'
[7 empty] | FAT_TRANSACTDM_0009.0001 | WIP_WO.WO_ACT_HRS to be migrated to WORKORDER.ACTINTLABHRS. | Pass |  | Peng Keong
[7 empty] | FAT_TRANSACTDM_0008.0001 | Line Type for Service receipts should be "SERVICE" and not "ITEM" as observed in Receiving record for example : PONUM: BB60015612, DO number: 00000015. Line Cost is not populated. | Pending | New item. | Peng Keong
[7 empty] | FAT_TRANSACTDM_0002.0001 | CONTRACT.STE_REMARKS field needs to be displayed on Contract application screen under screen. | NA | 2024-11-27
Note on O2: Wahyu Yoga Pratama: Maximo table is CONTRACT, not PO
Note on O24: Wahyu Yoga Pratama: PR should be in PO level? Also, POLINE.PONUM refer to parent PO. Can not be used to store PRNUM.

## Custom Column
0303 | PO_PR_PRCost | DF-PR | Need to extend PRLine.Description to 104 char
|  |  | New custom column: PR.STE_CSWNSAPGL | VARCHAR | 20
0304 | PO_RFQ |  | Need to extend RFQLine.Description to 104 char |  |  | di.PK_DV_ITEMS = 553226
|  |  | Need to extend Item related description to 104 char |  |  | Item with STE_MIGRATIONID=84190 has description truncated
|  |  | New custom column: RFQ.STE_CSWNSAPGL | VARCHAR | 20
|  |  | New custom column: RFQLINE.STE_CSWNSAPGL | VARCHAR | 20
|  |  | New custom column: RFQLINE.STE_CSWNCC | VARCHAR | 16
|  |  | New custom column: RFQ.STE_PRNUM | VARCHAR | 12
|  |  | New custom column: RFQ.STE_REMARKS | VARCHAR | 32000 | With long description
0202 | InvVendor |  | Need to extend InvVendor.Description to 104 char
|  |  | New custom column: INVVENDOR.STE_REMARKS | VARCHAR | 32000 | With long description
0205 | MR_MRLine |  | Need to extend MR.WONUM to 25 char (consistent with WORKORDER.WONUM)
|  |  | New custom column: MR.STE_CSWNDEMTODATE | DATE
|  |  | New custom column: MR.STE_REMARKS | VARCHAR | 32000 | With long description
|  |  | New custom column: MR.STE_CSWNCC | VARCHAR | 16
0302 | PO_Contract (Blanket) |  | New custom column: CONTRACT.STE_CSWNDATE | DATE
|  |  | New custom column: CONTRACT.STE_CSWNDELDUEDATE | DATE
|  |  | Custom column: ste_actualstartdate (date) mapped from PO_VALID_FM |  |  | Not mapped yet but derived column exist. Check with gareth!
|  |  | New custom column: CONTRACT.STE_REMARKS | VARCHAR | 32000 | With long description
|  |  | New custom column: CONTRACT.STE_GLACCOUNT | VARCHAR | 110
0306 | PO_PO |  | New custom column: STE_PRNUM | VARCHAR | 12
0206 | INVTRANS |  | New custom column: INVTRANS.STE_CSWNCC | VARCHAR | 16
|  |  | New custom column: INVTRANS.STE_SCCODE | VARCHAR | 10
|  |  | New custom column: INVTRANS.STE_ADJVAL | DECIMAL | 22,10
|  |  | New custom column: INVTRANS.STE_ADJUNITCOST | DECIMAL | 22,10
0308A | SERVRECTRANS |  | New custom column: SERVRECTRANS.STE_CSWNCC | VARCHAR | 16
|  |  | New custom column: SERVRECTRANS.STE_CSWNSAPGL | VARCHAR | 20
|  |  | New custom column: SERVRECTRANS.STE_CSWNDNDATE | DATETIME | 10
|  |  | New custom column: SERVRECTRANS.STE_CSWNFWDR | VARCHAR | 15
|  |  | New custom column: SERVRECTRANS.STE_CSWNGRNDATE | DATETIME | 10
|  |  | New custom column: SERVRECTRANS.STE_CSWNGRNNUM | VARCHAR | 10
|  |  | New custom column: SERVRECTRANS.STE_CSWNGRNREF | VARCHAR | 10
|  |  | New custom column: SERVRECTRANS.STE_CSWNINSPSTATUS | VARCHAR | 20
|  |  | New custom column: SERVRECTRANS.STE_CSWNINSPDATE | DATETIME | 10
|  |  | New custom column: SERVRECTRANS.STE_CSWNINSPREF | VARCHAR | 10
|  |  | New custom column: SERVRECTRANS.STE_CSWNINSPSTAT | NUMBER | 3
|  |  | New custom column: SERVRECTRANS.STE_CSWNRCTSTATUS | SMALLINT | 3
|  |  | New custom column: SERVRECTRANS.STE_CSWNRECEIPTCHANGEDATE | DATETIME | 10
|  |  | New custom column: SERVRECTRANS.STE_CSWNRECEIPTFORWARDER | VARCHAR | 15
|  |  | New custom column: SERVRECTRANS.STE_CSWNRECEIPTTYPE | SMALLINT | 3
|  |  | New custom column: SERVRECTRANS.STE_CSWNRECEIPTREMARK | VARCHAR | 32000
| INVOICE |  | New custom column: INVOICE.STE_CSWNSAPGL | VARCHAR | 20
| INVENTORY |  | New custom column: INVENTORY.STE_CSWNSTKRISK | DECIMAL | 22,10
|  |  | New custom column: INVENTORY.STE_CYCLICREORDER | DECIMAL | 5,0
|  |  | New custom column: INVENTORY.STE_NODAYSCYCL | DECIMAL | 5,0
|  |  | New custom column: INVENTORY.STE_CSWNSUPPLIER | VARCHAR | 20
|  |  | New custom column: INVENTORY.STE_CSWNPOPULATION | DECIMAL | 22,10
| MATUSETRANS |  | New custom column: MATUSETRANS.STE_ISSUENUM | varchar | 8
| MATRECTRANS |  | New custom column: MATRECTRANS.STE_CSWNRECEIPTREMARK | VARCHAR | 32000
| CONTRACTTERM |  | New custom column: CONTRACTTERM.STE_MIGRATIONSOURCE | VARCHAR | 50

## Drop down list (hidden)
Event Type | Nature | Occurrence | Severity | Status
Error | Document | Constant Defect | Critical | Pending Analysis
Fault | Software | Random Defect | Major | Pending Validation
Evolution | Hardware | Defect due to change | Minor | Pending Closure
Improvement |  |  |  | Closed