## Conversion Status
SSIS Package Name | Converted to DB2? | Planned Conversion Start Date | Planned Conversion End Date | Executed? | Executed on | Tested with Maximo 7.6.1.3 (Pass/Fail?) | Tested With MAS 879 | Remarks | Start Time | End Time | Time Taken | Start Time | End Time | Time Taken | Number of Records
0003_Master_Locations.dtsx | Converted, 26/12/23 | 2023-12-26 | 2023-12-29 | Yes | 2024-01-23 | Pass | Pass |  | 9:36 | 9:37 | 0:00 | 13:38 | 13:38 | 0:00 | Loading COSWIN FM_FACILITY and STORES LOCATIONS - 97
0004_Master_Person.dtsx | Converted, 26/12/23 | 2023-12-26 | 2023-12-29 | Yes | 2024-01-23 | Pass | Pass |  | 9:48 | 9:49 | 0:01 | 13:39 | 13:39 | 0:01 | PERSON - 2978
0005_Master_Meter.dtsx | Converted, 26/12/23 | 2023-12-26 | 2023-12-29 | Yes | 2024-01-23 |  | Pass |  | 9:50 | 9:55 | 0:05 | 13:39 | 13:47 | 0:08 | METER - 46544
0006_Master_Classification_ClassStructure.dtsx | Converted, 26/12/23 | 2023-12-26 | 2023-12-29 | Yes | 2024-01-23 | Pass | Pass |  | 9:56 | 9:56 | 0:00 | 13:47 | 13:47 | 0:00 | CLASSIFICATION - 1 CLASSSTRUCTURE - 1
0007_Master_AssetAttribute_ClassSpec_ClassSpecUseWith.dtsx | Converted, 26/12/23 | 2023-12-26 | 2023-12-29 | Yes | 2024-01-23 | Pass | Pass |  | 9:57 | 9:57 | 0:00 | 13:47 | 13:47 | 0:00 | ASSETATTRIBUTE - 18 CLASSSPEC - 18 CLASSSPECUSEWITH - 18
0008A_Master_FailureCode.dtsx | Converted, 26/12/23 | 2023-12-26 | 2023-12-29 | Yes | 2024-01-23 | Pass | Pass |  | 10:10 | 10:15 | 0:04 | 13:47 | 13:49 | 0:02 | FAILURECODE - 11919
0008B_Master_FailureList.dtsx | [6 empty] | Pass |  |  |  |  | 13:49 | 13:59 | 0:10 | FAILURELIST - 60852
0009_Master_Routes.dtsx | Converted, 26/12/23 | 2023-12-26 | 2023-12-29 | Yes | 2024-01-23 | Pass | Pass |  | 10:25 | 10:26 | 0:01 | 13:59 | 14:01 | 0:02 | ROUTES - 9086
0010_Master_Item_ItemOrgInfo.dtsx | Converted, 26/12/23 | 2023-12-26 | 2023-12-29 | Yes | 2024-01-23 |  | Pass |  | 14:29 | 14:34 | 0:05 | 14:01 | 14:13 | 0:12 | ITEM - 63507 ITEMORGINFO - 63507
0011_Master_CompMaster_CompContactMstr.dtsx | Converted, 26/12/23 | 2023-12-26 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 10:24 | 10:25 | 0:01 | 14:14 | 14:15 | 0:02 | COMPMASTER - 4941 COMPCONTACTMSTR - 4904
0012_Master_Companies_CompContact.dtsx | Converted, 26/12/23 | 2023-12-26 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 12:02 | 12:02 | 0:00 | 14:15 | 14:16 | 0:00 | COMPANIES - 4941 COMPCONTACT - 4904
0013_Master_Craft_CraftSkill.dtsx | Converted, 26/12/23 | 2023-12-26 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 12:08 | 12:08 | 0:00 | 14:16 | 14:16 | 0:00 | CRAFT - 345 CRAFTSKILL - 345 CRAFTRATE - 345
0014_Master_PersonGroup.dtsx | Converted, 26/12/23 | 2023-12-26 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 12:28 | 12:28 | 0:00 | 14:16 | 14:16 | 0:00 | PERSONGROUP - 600
0015_Master_PersonGroupTeam.dtsx | Converted, 26/12/23 | 2023-12-26 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 12:33 | 12:34 | 0:01 | 14:16 | 14:17 | 0:01 | PERSONGROUPTEAM - 8290
0016_Master_Labor.dtsx | Converted, 26/12/23 | 2023-12-26 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 13:56 | 13:56 | 0:00 | 14:17 | 14:18 | 0:00 | LABOR - 2786
0017_Master_AMCrewType_AMCrew_AMCrewLabor.dtsx | Converted, 29/12/23 | 2023-12-29 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 14:13 | 14:14 | 0:01 | 14:24 | 14:24 | 0:01 | AMCREWT - 2 AMCREW - 555 AMCREWLABOR - 2790
0018_Master_MeasureUnit.dtsx | Converted, 29/12/23 | 2023-12-29 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 14:17 | 14:17 | 0:00 | 14:27 | 14:27 | 0:00 | MEASUREUNIT - 160 CONVERSION - 260
0019A_Master_GL_CC.dtsx | Converted, 29/12/23 | 2023-12-29 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 14:23 | 14:23 | 0:00 | 14:34 | 14:34 | 0:00 | GLCOMPONENTS - 161
0019B_Master_ChartOfAsscounts.dtsx | [6 empty] | Pass |  |  |  |  | 14:47 | 14:47 | 0:00 | CHARTOFACCOUNTS - 260
0020_Master_Workzone.dtsx | Converted, 29/12/23 | 2023-12-29 | 2023-12-29 | Yes | 2024-01-24 |  |  |  | 14:27 | 14:27 | 0:00
0021_Master_ItemStruct.dtsx | Converted, 29/12/23 | 2023-12-29 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 14:32 | 14:32 | 0:00 | 14:48 | 14:48 | 0:00 | ITEMSTRUCT - 0
0022_Master_Commodities.dtsx | Converted, 29/12/23 | 2023-12-29 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 14:44 | 14:44 | 0:00 | 14:49 | 14:50 | 0:00 | COMMODITIES - 167
0023_Master_AltItem.dtsx | [6 empty] | Pass |  |  |  |  | 14:53 | 14:53 | 0:00 | ALTITEM - 246
0501_Misc_Currency.dtsx | [6 empty] | Pass |  |  |  |  | 14:56 | 14:56 | 0:00 | CURRENCY - 26 Update the Currency Table for Existing Currency using Currency_Update.csv ste_cswnctrycd, ste_cswnctryname, STE_CSWNDPT
0502_Misc_Exchange.dtsx | [6 empty] | Pass |  |  |  |  | 14:59 | 14:59 | 0:00 | EXCHANGE - 26
0503_Misc_Qualification.dtsx | Converted, 4/1/24 | 2024-01-04 | 2024-01-05 | Yes | 2024-01-30 |  | Pass |  | 16:45 | 16:45 | 0:00 | 15:01 | 15:01 | 0:00 | QUALIFICATION - 30
0504_Misc_PPCraftRate.dtsx | Converted, 4/1/24 | 2024-01-04 | 2024-01-05 | Yes | 2024-01-30 |  | Pass | - | 16:47 | 16:47 | 0:00 | 15:02 | 15:03 | 0:01 | PPCRAFTRATE - 3450
0505_Misc_LaborQual.dtsx | Converted, 4/1/24 | 2024-01-04 | 2024-01-05 | Yes | 2024-01-30 |  | Pass | - | 16:59 | 16:59 | 0:00 | 15:04 | 15:04 | 0:00 | LABORQUAL - 237
0506_Misc_Attendance.dtsx | Converted, 4/1/24 | 2024-01-04 | 2024-01-05 | Yes | 2024-01-30 |  | Pass |  | 17:23 | 17:23 | 0:00 | 15:06 | 15:06 | 0:00 | ATTENDANCE - 45
0507_Misc_Address.dtsx | Converted, 4/1/24 | 2024-01-04 | 2024-01-05 | Yes | 2024-01-30 |  | Pass | - | 17:24 | 17:24 | 0:00 | 15:07 | 15:07 | 0:00 | ADDRESS - 2
0509_Misc_WorkType.dtsx | Converted, 4/1/24 | 2024-01-05 | 2024-01-05 | Yes | 2024-01-30 |  | Pass |  | 17:58 | 17:59 | 0:00 | 15:22 | 15:22 | 0:00 | WORKTYPE - 25
0511_Misc_JobPlan_JPAssetsPLink_JobTask.dtsx | Converted, 5/1/24 | 2024-01-05 | 2024-01-05 | Yes | 2024-01-31 |  | Pass | Only Executing the Data Flow for JOB_DIR to create unique jobplans in Maximo based on Coswin JOB ID. | 11:46 | 12:10 | 0:23 | 15:25 | 15:29 | 0:04 | JOBPLAN - 21163
0101_Asset_Asset.dtsx | Converted, 29/12/23 | 2023-12-29 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 15:22 | 15:53 | 0:31 | 15:32 | 16:25 | 0:53 | ASSET - 250571 PLUSTASSETALIAS - 250571
0102_Asset_AssetLocUserCust.dtsx | Converted, 29/12/23 | 2023-12-29 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 16:08 | 16:08 | 0:00 | 12:34 | 12:34 | 0:00 | ASSETLOCUSERCUST - 6
0103_Asset_AssetMeter.dtsx | Converted, 29/12/23 | 2023-12-29 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 16:18 | 16:20 | 0:02 | 16:38 | 16:42 | 0:04 | ASSETMETER - 21727
0104_Asset_STE_CSWNASSETSLHIST.dtsx | Converted, 11/1/24 | 2024-01-11 | 2024-01-11 | Yes | 2024-01-24 |  | Pass |  | 16:22 | 16:32 | 0:10 | 18:33 | 18:53 | 0:21 | 125909
0105_Asset_AssetTrans.dtsx | Converted, 29/12/23 | 2023-12-29 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 16:47 | 17:19 | 0:31 | 13:58 | 15:18 | 1:20 | ASSETTRANS - 484449
0106_Asset_AssetSpec.dtsx | Converted, 29/12/23 | 2023-12-29 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 17:48 | 17:48 | 0:00 | 9:46 | 9:46 | 0:00 | ASSETSPEC - 399
0107_Asset_SpareParts.dtsx | Converted, 29/12/23 | 2023-12-29 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 17:52 | 17:53 | 0:01 | 9:48 | 9:54 | 0:07 | EQ_LEVL 0 Spareparts = 4169 Non EQ_LEVL 0 Spareparts = 11324 Oracle Records = 15493
0108_Asset_RouteStop.dtsx | Converted, 29/12/23 | 2023-12-29 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 17:58 | 18:09 | 0:11 | 9:55 | 10:46 | 0:51 | ROUTE_STOP - 133122
0109_Asset_AssetAncestor.dtsx | Converted, 29/12/23 | 2023-12-29 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 18:53 | 19:36 | 0:43 | 15:55 | 17:54 | 1:59 | ASSETANCESTOR - 634359
0110_Asset_AssetWorkzone.dtsx | Converted, 29/12/23 | 2023-12-29 | 2023-12-29 | Yes | 2024-01-24 |  |  |  | 19:42 | 19:59 | 0:17
0111_Asset_TLOAMASSETGRP.dtsx | Converted, 29/12/23 | 2023-12-29 | 2023-12-29 | Yes | 2024-01-24 |  | Pass |  | 20:02 | 20:18 | 0:16 | 18:51 | 19:29 | 0:38 | TLOAMASSETGRP - 250571
0:40
0201_Inventory_Inventory.dtsx | Converted, 2/1/24 | 2024-01-02 | 2024-01-05 | Yes | 2024-01-24 |  |  |  | 20:29 | 20:31 | 0:02 | 9:59 | 10:03 | 0:03 | INVENTORY - 28543
0202_Inventory_InvVendor.dtsx | Converted, 2/1/24 | 2024-01-02 | 2024-01-05 | Yes | 2024-01-24 |  |  |  | 20:54 | 21:01 | 0:07 | 10:13 | 10:27 | 0:13 | INVVENDOR - 108190
0203_Inventory_InvBalances.dtsx | Converted, 2/1/24 | 2024-01-02 | 2024-01-05 | Yes | 2024-01-24 |  |  | Legacy Data contains BIN_REF that is greater than 8 characters in the Maximo INVBALANCES table. Propose to change the BINNUM in INVBALANCES to match the length in the legacy DB. | 21:18 | 21:21 | 0:02 | 11:09 | 11:16 | 0:07 | INVBALANCES - 29767 INVLOT - 28643
0204_Inventory_InvCost.dtsx | Converted, 2/1/24 | 2024-01-02 | 2024-01-05 | Yes | 2024-01-24 |  |  |  | 21:24 | 21:26 | 0:02 | 11:19 | 11:23 | 0:03 | INVCOST - 28543
0205_Inventory_MR_MRLine.dtsx | Converted, 2/1/24 | 2024-01-02 | 2024-01-05 | Yes | 2024-01-25 |  |  | Legacy Data has DEM_REF up to 10 chars mapped to MR.MRNUM which is only 8 chars. Propose to extend length of MRNUM within MR Table. | 9:11 | 9:22 | 0:11 | 1:49 | 2:14 | 0:26
0301_PO_Contract_ContractLine.dtsx | Converted, 2/1/24 | 2024-01-02 | 2024-01-05 | Yes | 2024-01-25 |  |  |  | 10:18 | 10:18 | 0:00 | 2:14 | 2:14 | 0:00
0302_PO_Contract_ContractLine_Blanket.dtsx | Converted, 2/1/24 | 2024-01-02 | 2024-01-05 | Yes | 2024-01-25 |  |  |  | 10:29 | 10:29 | 0:00 | 2:15 | 2:15 | 0:00
0303_PO_PR_PRLine_PRCost.dtsx | Converted, 2/1/24 | 2024-01-02 | 2024-01-05 | Yes | 2024-01-25 |  |  | Description Contains Unicode characters. | 11:45 | 11:53 | 0:08 | 2:15 | 2:35 | 0:20
0304_PO_RFQ_RFQLine.dtsx | Converted, 2/1/24 | 2024-01-02 | 2024-01-05 | Yes | 2024-01-25 |  |  | RFQ.RFQNUM length increase from 8 to 15. | 13:29 | 13:53 | 0:24 | 2:35 | 3:28 | 0:53
0305_PO_RFQVendor_QuotationLine.dtsx | Converted, 3/1/24 | 2024-01-02 | 2024-01-05 | Yes | 2024-01-25 |  |  |  | 14:06 | 14:33 | 0:27 | 3:29 | 3:43 | 0:14
0306_PO_PO_POLine_POCost.dtsx | Converted, 3/1/24 | 2024-01-03 | 2024-01-05 | Yes | 2024-01-25 |  |  |  | 15:00 | 15:11 | 0:11 | 3:43 | 3:52 | 0:09
0307_PO_Invoice_InvoiceLine_InvoiceCost.dtsx | Converted, 3/1/24 | 2024-01-03 | 2024-01-05 | Yes | 2024-01-25 |  |  | To increase INVOICE.INVOICENUM to 13 chars. Legacy DB has max length of INV_REF = 10, NEG_INV adds "NI-" to the INV_REF. | 16:39 | 16:52 | 0:13 | 13:42 | 14:17 | 0:35
0308_PO_MATRECTRANS.dtsx | Converted, 3/1/24 | 2024-01-03 | 2024-01-05 | Yes | 2024-01-25 |  |  |  | 17:07 | 17:15 | 0:08 | 14:24 | 14:42 | 0:17 | 118021
0309_PO_ContractPurch.dtsx | Converted, 3/1/24 | 2024-01-03 | 2024-01-05 | Yes | 2024-01-25 |  |  |  | 17:21 | 17:21 | 0:00 | 14:42 | 14:42 | 0:00 | 98
0401_WO_Workorder.dtsx | Converted, 3/1/24 | 2024-01-03 | 2024-01-05 | Yes | 2024-01-29 |  |  | Update Followup WO Node requires SQL revamp. Refer to SSIS_SQLUpdates_In_Packages. [DONE] DF - CHILDREN is creating multiple workorder with the same STE_CSWNWOID. Seems like it is creating individual action as a separate workorder. This is casuing the SQL statement to fail as it is returning multiple workorder num with the same STE_CSWNWOID. | 18:37 | 20:33 | 1:56 | 18:30 | 1:48 | 7:12 | WORKORDER - 401876
0402_WO_WOActivity.dtsx | Converted, 4/1/24 | 2024-01-03 | 2024-01-05 | Yes | 2024-01-30 |  |  |  | 11:49 | 11:49 | 0:00 | 14:42 | 18:26 | 3:44 | WORKORDER - 403403
0403_WO_LabTrans.dtsx | Converted, 4/1/24 | 2024-01-03 | 2024-01-05 | Yes | 2024-01-30 |  |  |  | 12:00 | 12:47 | 0:47 | 18:26 | 20:34 | 2:08 | LABTRANS - 912584 LABORCRAFTRATE - 1093
0405_WO_SR.dtsx | Converted, 4/1/24 | 2024-01-03 | 2024-01-05 | Yes | 2024-01-30 |  |  | Update FOllowUp Ticket Node requires SQL revamp. [DONE] Update Followup WO Node requires SQL revamp. [DONE] | 13:51 | 14:12 | 0:21 | 20:34 | 23:28 | 2:55 | TICKET - 692904 TKSERVICEADDRESS - 692904
0406_WO_FailureReport.dtsx | Converted, 4/1/24 | 2024-01-03 | 2024-01-05 | Yes | 2024-01-30 |  |  |  | 14:48 | 15:42 | 0:53 | 16:13 | 17:44 | 1:32 | FAILUREREPORT - 679944
0407_WO_RelatedRecord.dtsx | Converted, 4/1/24 | 2024-01-04 | 2024-01-05 | Yes | 2024-01-30 |  |  |  | 15:54 | 15:56 | 0:02 | 23:29 | 1:05 | 1:37 | 161901 | 23:29
0408_WO_WPLabor_WPMaterial.dtsx | Converted, 4/1/24 | 2024-01-04 | 2024-01-05 | Yes | 2024-01-30 |  |  |  | 16:06 | 16:18 | 0:12 | 1:05 | 1:32 | 0:26 | SQL Insert
0409_WO_MATUSETRANS.dtsx | Converted, 4/1/24 | 2024-01-04 | 2024-01-05 | Yes | 2024-01-30 |  |  |  | 16:25 | 16:35 | 0:10 | 2:40 | 2:59 | 0:19 | 135239
0503_Misc_Qualification.dtsx | Converted, 4/1/24 | 2024-01-04 | 2024-01-05 | Yes | 2024-01-30 |  | Pass |  | 16:45 | 16:45 | 0:00 | 11:52 | 11:52 | 0:00 | 30
0504_Misc_PPCraftRate.dtsx | Converted, 4/1/24 | 2024-01-04 | 2024-01-05 | Yes | 2024-01-30 |  | Pass | - | 16:47 | 16:47 | 0:00 | 12:00 | 12:00 | 0:01 | 3450
0505_Misc_LaborQual.dtsx | Converted, 4/1/24 | 2024-01-04 | 2024-01-05 | Yes | 2024-01-30 |  | Pass | - | 16:59 | 16:59 | 0:00 | 12:05 | 12:05 | 0:00 | 237
0506_Misc_Attendance.dtsx | Converted, 4/1/24 | 2024-01-04 | 2024-01-05 | Yes | 2024-01-30 |  | Pass |  | 17:23 | 17:23 | 0:00 | 12:35 | 12:35 | 0:00 | 45
0507_Misc_Address.dtsx | Converted, 4/1/24 | 2024-01-04 | 2024-01-05 | Yes | 2024-01-30 |  | Pass | - | 17:24 | 17:24 | 0:00 | 12:30 | 12:30 | 0:00
0508_Misc_MeterReading.dtsx | Converted, 4/1/24 | 2024-01-05 | 2024-01-05 | Yes | 2024-01-30 |  |  | METERREADING.READING length and scale is not updated as per AttributeMappingForDM.xlsx. Possible limitiation for DB2. 29-Jan-24: SSIS Package completed without issues. | 17:32 | 17:46 | 0:14 | 3:00 | 3:08 | 0:08 | METERREADING - 57788
0509_Misc_WorkType.dtsx | Converted, 4/1/24 | 2024-01-05 | 2024-01-05 | Yes | 2024-01-30 |  |  |  | 17:58 | 17:59 | 0:00 | 3:08 | 3:08 | 0:00 | 25
0510_Misc_ServiceItems.dtsx | Converted, 5/1/24 | 2024-01-05 | 2024-01-05 | Yes | 2024-01-30 |  |  | Execute SQL Task Node requires SQL revamp. [DONE] | 18:04 | 18:04 | 0:00 | 3:08 | 3:09 | 0:00 | SQL Insers
0511_Misc_JobPlan_JPAssetsPLink_JobTask.dtsx | Converted, 5/1/24 | 2024-01-05 | 2024-01-05 | Yes | 2024-01-31 |  |  | Update WO's JPNUM Ref Node requires SQL revamp. [DONE] | 11:46 | 12:10 | 0:23 | 10:10 | 11:46 | 1:35 | JOBPLAN - 102557 Update WO JPNUM - 1hr6mins33secs JPASSETSPLINK - 102307 JOBTASK - 29759
0512_Misc_JobLabor.dtsx | Converted, 5/1/24 | 2024-01-05 | 2024-01-05 | Yes | 2024-01-31 |  |  | - | 12:21 | 12:21 | 0:00
0513_Misc_JobMaterial.dtsx | Converted, 5/1/24 | 2024-01-05 | 2024-01-05 | Yes | 2024-01-31 |  |  | Requires preceding JOB tables to migrate first. | 13:43 | 13:43 | 0:01
0514_Misc_PM_PMMeter_PMSeasons.dtsx | Converted, 5/1/24 | 2024-01-05 | 2024-01-05 | Yes | 2024-01-31 |  |  | Update WO's JPNUM Ref Node requires SQL revamp. [DONE] PMMETER.LASTPMWOGENREAD data type, length and scale is not updated as per AttributeMappingForDM.xlsx. Possible limitiation for DB2 | 14:11 | 14:19 | 0:08 | 11:46 | 12:30 | 0:44 | PM - 32096 Update WO PMNUM - 29mins39secs PMMETER - 292 PMSEASONS - 32096 PMANCESTOR - 32096 Update PM NEL1902-2378 - 33secs
0515_Misc_Shift_ShiftPatternDay.dtsx | Converted, 5/1/24 | 2024-01-05 | 2024-01-05 | Yes | 2024-01-31 |  |  | - | 14:23 | 14:23 | 0:00
0601_LD_CompMaster.dtsx | Converted, 8/1/24 | 2024-01-05 | 2024-01-05 | Yes | 2024-01-31 |  |  | - |  |  | 0:00 | 12:24 | 12:30 | 0:07 | SUPPLIER_ HO_ADDR - 4747 SUPPLIER_ MAIL_ADDR - 4752 SUPPLIER_ REMARKS - 1118 DIR_SUPP HO_ADDR - 6 DIR_SUPP MAIL_ADDR - 49 DIR_MANF HO_ADDR - 29 DIR_MANF MAIL_ADDR - 32 DIR_SUBC HO_ADDR - 1 DIR_SUBC MAIL_ADDR - 1
0602_LD_Asset.dtsx | Converted, 8/1/24 | 2024-01-05 | 2024-01-05 | Yes | 2024-02-01 |  |  | - | 15:33 | 15:59 | 0:26 | 12:46 | 13:06 | 0:20 | 149652
0603_LD_Contract.dtsx | Converted, 8/1/24 | 2024-01-08 | 2024-01-12 | Yes | 2024-02-01 |  |  | - | 9:38 | 9:38 | 0:00 | 15:18 | 15:18 | 0:00 | 98
0604_LD_PR.dtsx | Converted, 8/1/24 | 2024-01-08 | 2024-01-12 | Yes | 2024-02-01 |  |  | - | 14:25 | 14:29 | 0:04
0605A_LD_Workorder_Worklog.dtsx | [11 empty] | 10:23 | 11:46 | 1:23 | 349769
0605_LD_Workorder.dtsx | Converted, 8/1/24 | 2024-01-08 | 2024-01-12 | Yes | 2024-02-01 |  |  | - | 11:00 | 11:45 | 0:45 | 17:54 | 20:20 | 2:26 | WO - 330907
0606_LD_SR.dtsx | Converted, 8/1/24 | 2024-01-08 | 2024-01-12 | Yes | 2024-02-01 |  |  | - | 11:44 | 12:10 | 0:26 | 20:20 | 22:27 | 2:07 | SR - 690031
0607_LD_PO.dtsx | Converted, 8/1/24 | 2024-01-08 | 2024-01-12 | Yes | 2024-02-01 |  |  | - | 12:21 | 12:27 | 0:06 | 18:35 | 18:43 | 0:09 | PO - REMARKS 50289 PO - FOLLOWUP 1259
0608_LD_RFQ_RFQLine.dtsx | Converted, 8/1/24 | 2024-01-08 | 2024-01-12 | Yes | 2024-02-01 |  |  | - | 12:36 | 13:14 | 0:39 | 8:54 | 9:44 | 0:50 | RFQ - 35910 RFQLINE - 147877
0609_LD_Item.dtsx | Converted, 8/1/24 | 2024-01-08 | 2024-01-12 | Yes | 2024-02-01 |  |  | - |  |  | 0:00 | 13:45 | 13:59 | 0:14 | NS_ITEM RMK - 5037 NSITEM LD - 31541 ITEM RMK - 1067 ITEM LD - 12976
0610_LD_Invoice.dtsx | Converted, 8/1/24 | 2024-01-08 | 2024-01-12 | Yes | 2024-02-01 |  |  | - | 14:10 | 14:15 | 0:05 | 14:40 | 14:47 | 0:06 | 49237
0611_LD_PO_BILLTO.dtsx | [11 empty] | 17:19 | 17:38 | 0:19
0701_Others_AuditTables1.dtsx | Converted, 10/1/24 | 2024-01-08 | 2024-01-12 | Yes | 2024-01-12 | Pass |  | - |  |  | 0:00
0702_Others_AuditTables2.dtsx | Converted, 10/1/24 | 2024-01-08 | 2024-01-12 | Yes | 2024-01-12 | Pass |  | - |  |  | 0:00
0703_Others_AuditTables3.dtsx | Converted, 10/1/24 | 2024-01-09 | 2024-01-12 | Yes | 2024-01-12 | Pass |  | - |  |  | 0:00
0704_Others_AuditTables4.dtsx | Converted, 10/1/24 | 2024-01-09 | 2024-01-12 | Yes | 2024-01-12 | Pass |  | - |  |  | 0:00
0705_Others_AuditTables5.dtsx | Converted, 10/1/24 | 2024-01-09 | 2024-01-12 | Yes | 2024-01-12 | Pass |  | - |  |  | 0:00
0706_Others_TransactionTables1.dtsx | Converted, 10/1/24 | 2024-01-09 | 2024-01-12 | Yes | 2024-01-12 | Pass |  | - |  |  | 0:00
0707_Others_TransactionTables2.dtsx | Converted, 10/1/24 | 2024-01-09 | 2024-01-12 | Yes | 2024-01-12 | Pass |  | - |  |  | 0:00
0708_Others_TransactionTables3.dtsx | Converted, 10/1/24 | 2024-01-09 | 2024-01-12 | Yes | 2024-01-12 | Pass |  | - |  |  | 0:00
0709_Others_TransactionTables4.dtsx | Converted, 10/1/24 | 2024-01-09 | 2024-01-12 | Yes | 2024-01-12 | Pass |  | - |  |  | 0:00
0710_Others_TransactionTables5.dtsx | Converted, 10/1/24 | 2024-01-09 | 2024-01-12 | Yes | 2024-01-12 | Pass |  | - |  |  | 0:00
0711_Others_TransactionTables6.dtsx | Converted, 10/1/24 | 2024-01-09 | 2024-01-12 | Yes | 2024-01-12 | Pass |  | - |  |  | 0:00
0712_Others_TransactionTables7.dtsx | Converted, 10/1/24 | 2024-01-09 | 2024-01-12 | Yes | 2024-01-12 | Pass |  | - |  |  | 0:00
0713_Others_TransactionTables8.dtsx | Converted, 10/1/24 | 2024-01-09 | 2024-01-12 | Yes | 2024-01-12 | Pass |  | - |  |  | 0:00
0714_Others_MasterTables1.dtsx | Converted, 10/1/24 | 2024-01-09 | 2024-01-12 | Yes | 2024-01-12 | Pass |  | - |  |  | 0:00
0715_Others_MasterTables2.dtsx | Converted, 10/1/24 | 2024-01-09 | 2024-01-12 | Yes | 2024-01-12 | Pass |  | - |  |  | 0:00
0716_Others_Supplier.dtsx | Converted, 10/1/24 | 2024-01-09 | 2024-01-12 | Yes | 2024-01-12 | Pass |  | - |  |  | 0:00
| 99/106 | 93.4% |  | 99/99 | 100%

## Activity
# | Activity | Notes
1 | Testing/Updating to MAS 8.7.9 | WIP. Small Risk
2 | Fixing FAT feedback | Master Done. Don’t touch test case 009, 010, 014, 015. Gareth will check. Esther will give access to migrated Maximo data to check PR remark
3 | Updating for DELTA Migration | Make sure SSIS script can run/complete in 24 hours

## Migration Plan
First Iteration | Second Iteration (Opt 1) | Second Iteration (Opt 2) | Duration
Get October Dump File | Get December Dump File | Get December Dump File | 16 hours
Restore October Dump to Local Oracle DB | Restore December Dump to Local Oracle DB | Restore December Dump to Local Oracle DB
Do Migration to MAS 8.7 DB2 | Check for Delta Data in Oracle DB | Do Full Migration (Dec Data) to DB2 Staging | 32 hours | 24 hours
| Migrate Delta Data to MAS 8.7 DB2 | Check for Delta Data between DB2 Staging (Dec) and MAS 8.7 (Oct) |  | 8 hours
Update MAS 8.7 for delta data
| # | Activity |  | Duration | Coswin Running | MAS Running
| 1 | Get Dec Dump File | First Iteration | 3 Days | X
| 2 | Restore Dec Dump to Local Oracle DB | First Iteration |  | X
| 3 | Do Migration to MAS 8.7 DB2 | First Iteration |  | X
| 4 | Maximo configuration | First Iteration |  | X | X
| 5 | User Testing/Data Validation | First Iteration | 1-2 Days | X | X
| 6 | Backup Iteration1 MAS DB | Parallel Run |  | X | X
| 7 | Parallel Run (>= 1 week) | Parallel Run |  | X | X
| 8 | Restore Iteration1 MAS DB Backup (Make sure configuration changes during Parallel Run ARE carried over) | Parallel Run |  | X | X
| 9 | Get Dec2 Dump File | Second Iteration (Delta) | <= 2 days |  | X
| 10 | Restore Dec2 Dump to Local Oracle DB | Second Iteration (Delta) |  |  | X
| 11 | Delta Migration (Opt1/Opt2) | Second Iteration (Delta) |  |  | X
| 12 | Cut-off | Cut-off |  |  | X

## SSIS_Scripts
Script Name | Converted?
0002_Check_MaximoDB_000.sql | Y
0003_Master_Locations_000.sql | Y
0003_Master_Locations_001.sql | Y
0003_Master_Locations_002.sql | Y
0003_Master_Locations_003.sql | Y
0003_Master_Locations_004.sql | Y
0003_Master_Locations_005.sql | Y
0003_Master_Locations_006.sql | Y
0004_Master_Person_000.sql | Y
0004_Master_Person_001.sql | Y
0004_Master_Person_002.sql | Y
0004_Master_Person_003.sql | Y
0004_Master_Person_004.sql | Y
0004_Master_Person_005.sql | Y
0004_Master_Person_006.sql | Y
0004_Master_Person_007.sql | Y
0004_Master_Person_008.sql | Y
0005_Master_Meter_000.sql | Y
0005_Master_Meter_001.sql | Y
0005_Master_Meter_002.sql | Y
0005_Master_Meter_003.sql | Y
0006_Master_Classification_ClassStructure_000.sql | Y
0006_Master_Classification_ClassStructure_001.sql | Y
0006_Master_Classification_ClassStructure_002.sql | Y
0006_Master_Classification_ClassStructure_003.sql | Y
0007_Master_AssetAttribute_ClassSpec_ClassSpecUseWith_000.sql | Y
0007_Master_AssetAttribute_ClassSpec_ClassSpecUseWith_001.sql | Y
0007_Master_AssetAttribute_ClassSpec_ClassSpecUseWith_002.sql | Y
0007_Master_AssetAttribute_ClassSpec_ClassSpecUseWith_003.sql | Y
0007_Master_AssetAttribute_ClassSpec_ClassSpecUseWith_004.sql | Y
0008_Master_FailureCode_FailureList_000.sql | Y
0008_Master_FailureCode_FailureList_001.sql | Y
0008_Master_FailureCode_FailureList_002.sql | Y
0008_Master_FailureCode_FailureList_003.sql | Y
0008_Master_FailureCode_FailureList_004.sql | Y
0009_Master_Routes_000.sql | Y
0009_Master_Routes_001.sql | Y
0009_Master_Routes_002.sql | Y
0009_Master_Routes_003.sql | Y
0010_Master_Item_ItemOrgInfo_000.sql | Y
0010_Master_Item_ItemOrgInfo_001.sql | Y
0010_Master_Item_ItemOrgInfo_002.sql | Y
0010_Master_Item_ItemOrgInfo_003.sql | Y
0010_Master_Item_ItemOrgInfo_004.sql | Y
0011_Master_CompMaster_CompContactMstr_000.sql | Y
0011_Master_CompMaster_CompContactMstr_001.sql | Y
0011_Master_CompMaster_CompContactMstr_002.sql | Y
0011_Master_CompMaster_CompContactMstr_003.sql | Y
0011_Master_CompMaster_CompContactMstr_004.sql | Y
0012_Master_Companies_CompContact_000.sql | Y
0013_Master_Craft_CraftSkill_000.sql | Y
0014_Master_PersonGroup_000.sql | Y
0014_Master_PersonGroup_001.sql | Y
0015_Master_PersonGroupTeam_000.sql | Y
0015_Master_PersonGroupTeam_001.sql | Y
0015_Master_PersonGroupTeam_002.sql | Y
0016_Master_Labor_000.sql | Y
0017_Master_AMCrewType_AMCrew_AMCrewLabor_000.sql | Y
0017_Master_AMCrewType_AMCrew_AMCrewLabor_001.sql | Y
0018_Master_MeasureUnit_000.sql | Y
0019_Master_ChartOfAccounts_000.sql | Y
0020_Master_Workzone_000.sql | Y
0021_Master_ItemStruct_000.sql | Y
0021_Master_ItemStruct_001.sql | Y
0022_Master_Commodities_000.sql | Y
0022_Master_Commodities_001.sql | Y
0022_Master_Commodities_002.sql | Y
0101_Asset_Asset_000.sql | Y
0101_Asset_Asset_001.sql | Y
0101_Asset_Asset_002.sql | Y
0101_Asset_Asset_003.sql | Y
0101_Asset_Asset_004.sql | Y
0102_Asset_AssetLocUserCust_000.sql | Y
0102_Asset_AssetLocUserCust_001.sql | Y
0102_Asset_AssetLocUserCust_002.sql | Y
0103_Asset_AssetMeter_000.sql | Y
0103_Asset_AssetMeter_001.sql | Y
0103_Asset_AssetMeter_002.sql | Y
0103_Asset_AssetMeter_003.sql | Y
0104_Asset_STE_CSWNASSETSLHIST_000.sql | Y
0105_Asset_AssetTrans_000.sql | Y
0105_Asset_AssetTrans_001.sql | Y
0105_Asset_AssetTrans_002.sql | Y
0106_Asset_AssetSpec_000.sql | Y
0106_Asset_AssetSpec_001.sql | Y
0106_Asset_AssetSpec_002.sql | Y
0106_Asset_AssetSpec_003.sql | Y
0107_Asset_SpareParts_000.sql | Y
0107_Asset_SpareParts_001.sql | Y
0107_Asset_SpareParts_002.sql | Y
0108_Asset_RouteStop_000.sql | Y
0108_Asset_RouteStop_001.sql | Y
0108_Asset_RouteStop_002.sql | Y
0108_Asset_RouteStop_003.sql | Y
0109_Asset_AssetAncestor_000.sql | Y
0109_Asset_AssetAncestor_001.sql | Y
0110_Asset_AssetWorkzone_000.sql | Y
0111_Asset_TLOAMASSETGRP_000.sql | Y
0201_Inventory_Inventory_000.sql | Y
0201_Inventory_Inventory_001.sql | Y
0202_Inventory_InvVendor_000.sql | Y
0203_Inventory_InvBalances_000.sql | Y
0204_Inventory_InvCost_000.sql | Y
0205_Inventory_MR_MRLine_000.sql | Y
0205_Inventory_MR_MRLine_001.sql | Y
0301_PO_Contract_ContractLine_000.sql | Y
0301_PO_Contract_ContractLine_001.sql | Y
0301_PO_Contract_ContractLine_Blanket_000.sql | Y
0302_PO_Contract_ContractLine_Blanket_001.sql | Y
0303_PO_PR_PRLine_PRCost_000.sql | Y
0303_PO_PR_PRLine_PRCost_001.sql | Y
0303_PO_PR_PRLine_PRCost_002.sql | Y
0303_PO_PR_PRLine_PRCost_003.sql | Y
0303_PO_PR_PRLine_PRCost_004.sql | Y
0304_PO_RFQ_RFQLine_000.sql | Y
0304_PO_RFQ_RFQLine_001.sql | Y
0304_PO_RFQ_RFQLine_002.sql | Y
0305_PO_RFQVendor_QuotationLine_000.sql | Y
0305_PO_RFQVendor_QuotationLine_001.sql | Y
0306_PO_PO_POLine_POCost_000.sql | Y
0306_PO_PO_POLine_POCost_001.sql | Y
0306_PO_PO_POLine_POCost_002.sql | Y
0306_PO_PO_POLine_POCost_003.sql | Y
0306_PO_PO_POLine_POCost_004.sql | Y
0307_PO_Invoice_InvoiceLine_InvoiceCost_000.sql | Y
0307_PO_Invoice_InvoiceLine_InvoiceCost_001.sql | Y
0307_PO_Invoice_InvoiceLine_InvoiceCost_002.sql | Y
0307_PO_Invoice_InvoiceLine_InvoiceCost_003.sql | Y
0308_PO_MATRECTRANS_000.sql | Y
0308_PO_MATRECTRANS_001.sql | Y
0308_PO_MATRECTRANS_002.sql | Y
0309_PO_ContractPurch_000.sql | Y
0401_WO_Workorder_000.sql | Y
0401_WO_Workorder_001.sql | Y
0401_WO_Workorder_002.sql | Y
0401_WO_Workorder_003.sql | Y
0402_WO_WOActivity_000.sql | Y
0402_WO_WOActivity_001.sql | Y
0403_WO_Labtrans_000.sql | Y
0403_WO_Labtrans_001.sql | Y
0405_WO_SR_000.sql | Y
0405_WO_SR_001.sql | Y
0405_WO_SR_002.sql | Y
0405_WO_SR_003.sql | Y
0406_WO_FailureReport_000.sql | Y
0406_WO_FailureReport_001.sql | Y
0407_WO_RelatedRecord_000.sql | Y
0407_WO_RelatedRecord_001.sql | Y
0407_WO_RelatedRecord_002.sql | Y
0408_WO_WPLabor_WPMaterial_000.sql | Y
0408_WO_WPLabor_WPMaterial_001.sql | Y
0409_WO_MATUSETRANS_000.sql | Y
0409_WO_MATUSETRANS_001.sql | Y
0409_WO_MATUSETRANS_002.sql | Y
0501_Misc_Currency_000.sql | Y
0502_Misc_Exchange_000.sql | Y
0503_Misc_Qualification_000.sql | Y
0504_Misc_PPCraftRate_000.sql | Y
0505_Misc_LaborQual_000.sql | Y
0506_Misc_Attendance_000.sql | Y
0507_Misc_Address_000.sql | Y
0507_Misc_Address_001.sql | Y
0508_Misc_MeterReading_000.sql | Y
0509_Misc_WorkType_000.sql | Y
0510_Misc_ServiceItems_000.sql | Y
0511_Misc_JobPlan_JPAssetsPLink_JobTask_000.sql | Y
0511_Misc_JobPlan_JPAssetsPLink_JobTask_001.sql | Y
0511_Misc_JobPlan_JPAssetsPLink_JobTask_002.sql | Y
0511_Misc_JobPlan_JPAssetsPLink_JobTask_003.sql | Y
0512_Misc_JobLabor_000.sql | Y
0513_Misc_JobMaterial_000.sql | Y
0513_Misc_JobMaterial_001.sql | Y
0514_Misc_PM_PMMeter_PMSeasons_000.sql | Y
0514_Misc_PM_PMMeter_PMSeasons_001.sql | Y
0515_Misc_Shift_ShiftPatternDay_000.sql | Y
0601_LD_CompMaster_000.sql | Y
0601_LD_CompMaster_001.sql | Y
0602_LD_Asset_000.sql | Y
0603_LD_Contract_000.sql | Y
0604_LD_PR_000.sql | Y
0605_LD_Workorder_000.sql | Y
0606_LD_SR_000.sql | Y
0606_LD_SR_001.sql | Y
0607_LD_PO_000.sql | Y
0608_LD_RFQ_RFQLine_000.sql | Y
0609_LD_Item_000.sql | Y
0610_LD_Invoice_000.sql | Y
0701_Others_AuditTables1_000.sql | Y
0702_Others_AuditTables2_000.sql | Y
0703_Others_AuditTables3_000.sql | Y
0704_Others_AuditTables4_000.sql | Y
0705_Others_AuditTables5_000.sql | Y
0706_Others_TransactionTables1_000.sql | Y
0707_Others_TransactionTables2_000.sql | Y
0708_Others_TransactionTables3_000.sql | Y
0709_Others_TransactionTables4_000.sql | Y
0710_Others_TransactionTables5_000.sql | Y
0711_Others_TransactionTables6_000.sql | Y
0712_Others_TransactionTables7_000.sql | Y
0713_Others_TransactionTables8_000.sql | Y
0714_Others_MasterTables1_000.sql | Y
0715_Others_MasterTables2_000.sql | Y
0716_Others_Supplier_000.sql | Y
100%

## SSIS_SQLUpdates_in_Packages
SSIS Package Name | Original SQL | Converted SQL | Converted?
0401_WO_Workorder.dtsx | update a set origrecordid=b.wonum , origrecordclass = 'WORKORDER' from dbo.workorder a join dbo.workorder b on b.ste_cswnwoid = a.STE_MIGRATIONPREVWOID where coalesce(a.STE_MIGRATIONPREVWOID,0) != 0 -- avoid recursive reference and a.STE_MIGRATIONPREVWOID!=a.ste_cswnwoid and a.STE_MIGRATIONID is not null; | MERGE INTO workorder A USING (SELECT wonum, ste_cswnwoid from WORKORDER) B ON (b.ste_cswnwoid = A.STE_MIGRATIONPREVWOID) WHEN MATCHED AND A.STE_MIGRATIONPREVWOID != a.ste_cswnwoid and A.STE_MIGRATIONID IS NOT NULL AND coalesce(a.STE_MIGRATIONPREVWOID,0) != 0 THEN UPDATE SET A.ORIGRECORDID = b.WONUM, A.ORIGRECORDCLASS = 'WORKORDER' ; | Y | RESOLVED: Encountered Error. Suggest to research further in https://stackoverflow.com/questions/26245315/using-db2-merge-error-code-788-sql-state-21506
0405_WO_SR.dtsx | -- SR-SRCWO update a set a.origrecordid = b.wonum , a.origrecordclass = 'WORKORDER' from ticket a join workorder b on b.ste_cswnwoid=a.STE_MIGRATIONSRCWO where coalesce(a.STE_MIGRATIONSRCWO,'0') != '0' and a.origrecordid is null and a.STE_MIGRATIONID is not null; | MERGE INTO ticket A USING (SELECT wonum, ste_cswnwoid from WORKORDER) B ON (b.ste_cswnwoid = A.STE_MIGRATIONSRCWO) WHEN MATCHED AND a.origrecordid is null and a.STE_MIGRATIONID is not null AND coalesce(a.STE_MIGRATIONSRCWO,'0') != '0' THEN UPDATE SET A.ORIGRECORDID = b.WONUM, A.ORIGRECORDCLASS = 'WORKORDER' ; | Y
0405_WO_SR.dtsx | -- WO-REQNO update a set a.origrecordid = b.ticketid , a.origrecordclass = 'SR' from workorder a join ticket b on b.ticketid=a.STE_MIGRATIONREQNO where coalesce(a.STE_MIGRATIONREQNO,'0') != '0' and a.origrecordid is null and a.STE_MIGRATIONID is not null; -- SR-WOREF (belum dari WO-REQNO) update a set a.origrecordid = b.ticketid , a.origrecordclass = 'SR' from workorder a join ticket b on a.ste_cswnwoid=b.STE_MIGRATIONWOREF where coalesce(b.STE_MIGRATIONWOREF,'0') != '0' and a.origrecordid is null and a.STE_MIGRATIONID is not null; | MERGE INTO WORKORDER A USING (SELECT ticketid from TICKET) B ON (b.ticketid = A.STE_MIGRATIONREQNO) WHEN MATCHED AND a.origrecordid is null and a.STE_MIGRATIONID is not null AND coalesce(a.STE_MIGRATIONREQNO,'0') != '0' THEN UPDATE SET A.ORIGRECORDID = b.ticketid, A.ORIGRECORDCLASS = 'SR' ; MERGE INTO WORKORDER A USING (SELECT ticketid, ste_migrationworef FROM ( SELECT ticketid, STE_MIGRATIONWOREF, ROW_NUMBER() OVER(PARTITION BY STE_MIGRATIONWOREF ORDER BY ticketid asc) AS row_number FROM ticket WHERE coalesce(STE_MIGRATIONWOREF,'0') != '0' ) C WHERE ROW_NUMBER = 1) B ON (a.ste_cswnwoid=b.STE_MIGRATIONWOREF) WHEN MATCHED AND a.origrecordid is null and a.STE_MIGRATIONID is not null AND coalesce(b.STE_MIGRATIONWOREF,'0') != '0' THEN UPDATE SET A.ORIGRECORDID = b.ticketid, A.ORIGRECORDCLASS = 'SR' ; | Y
0510_Misc_ServiceItems.dtsx | update i set i.itemtype='STDSERVICE' from dbo.item i join dbo.commodities c on c.commodity = i.commoditygroup where i.STE_MIGRATIONSOURCE='NSITEM' and c.STE_MIGRATIONRESTAG = 78; | MERGE INTO ITEM A USING (SELECT commodity, ste_migrationrestag FROM commodities WHERE STE_MIGRATIONRESTAG = 78) B ON (b.commodity = A.commoditygroup) WHEN MATCHED AND A.STE_MIGRATIONSOURCE = 'NSITEM' THEN UPDATE SET A.ITEMTYPE = 'STDSERVICE' ; | Y
0511_Misc_JobPlan_JPAssetsPLink_JobTask.dtsx | update a set a.jpnum = b.jpnum from workorder a join jobplan b on b.ste_cswnjobid=a.ste_cswnjobid and b.ste_cweqcode=a.ste_cswneqpcode where a.ste_cswnjobid is not null and a.ste_cswneqpcode is not null and a.STE_MIGRATIONID is not null; | MERGE INTO WORKORDER A USING (SELECT JPNUM, STE_CSWNJOBID, STE_CWEQCODE FROM JOBPLAN) B ON (B.STE_CSWNJOBID = A.STE_CSWNJOBID AND b.ste_cweqcode=a.ste_cswneqpcode) WHEN MATCHED AND a.ste_cswnjobid is not NULL AND a.ste_cswneqpcode is not NULL AND a.STE_MIGRATIONID is not null THEN UPDATE SET A.jpnum = B.jpnum | Y
0514_Misc_PM_PMMeter_PMSeasons.dtsx | update a set a.pmnum = b.pmnum from workorder a join pm b on b.ste_cswnjobid=a.ste_cswnjobid and b.ste_cweqcode=a.ste_cswneqpcode where a.ste_cswnjobid is not null and a.ste_cswneqpcode is not null and a.STE_MIGRATIONID is not null; | MERGE INTO WORKORDER A USING (SELECT pmnum, ste_cswnjobid, ste_cweqcode FROM PM) B ON (B.STE_CSWNJOBID = A.STE_CSWNJOBID AND b.ste_cweqcode=a.ste_cswneqpcode) WHEN MATCHED AND a.ste_cswnjobid is not NULL AND a.ste_cswneqpcode is not NULL AND a.STE_MIGRATIONID is not null THEN UPDATE SET A.pmnum = B.pmnum | Y
100%